## Year to Date
Catalyze |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 6033745.0343 | 7478720.123 | -1444975.0887 | -19.32% | 13358093.54 | -7324348.5057 | -54.83%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Fresno - 3150 Shaw Ave | CA | 302802.5 | 300762.92 | 2039.58 | 0.6781% | 336743.68 | -33941.18 | -10.08%
Adelanto - 1 Sheep Creek Road | CA | 698121 | 899827.54 | -201706.54 | -22.42% | 2794868.45 | -1198363.45 | -42.88%
Blackstone - 83 Federal Street | MA | 1021429 | 1250983.5 | -229554.5 | -18.35% | 2263183.6 | -471279.3 | -20.82%
Charlton - 299 Worcester Road | MA | 106387.5 | 122897.92 | -16510.42 | -13.43% | 195041.82 | -17768.79 | -9.11%
Wareham - 8 Thatcher Drive | MA | 26732.625 | 32689.431 | -5956.806 | -18.22% | 54449.759 | -9322.204 | -17.12%
West Yarmouth - 42 Mid Tech | MA | 21092.2942 | 26594.646 | -5502.3518 | -20.69% | 46631.671 | -6768.8868 | -14.52%
Harrison - 130 Union Street | NY | 38110 | 49114.896 | -11004.896 | -22.41% | 72651.72 | -8334.25 | -11.47%
Staten Island - Ellis Storage | NY | 90871.75 | 116168.46 | -25296.71 | -21.78% | 163418.53 | -11927.27 | -7.299%
Amherst - 595 Scholles Road | NY | 1004650 | 1305937.17 | -301287.17 | -23.07% | 2466753 | -509052 | -20.64%
Lancaster 1 - Gunnville Road | NY | 993680 | 1203596.5 | -209916.5 | -17.44% | 1772590.6 | -32020 | -1.806%
Lancaster 2 - Shisler Road | NY | 951657 | 1317386.2 | -365729.2 | -27.76% | 1939774.5 | -167958.1 | -8.659%
Fullerton - 200 W Orangethorpe | CA | 228387.8652 | 237208.44 | -8820.5748 | -3.718% | 390408.07 | -40178.8048 | -10.29%
El Paso - 10500 Railroad Drive | TX | 302499.25 | 350397.5 | -47898.25 | -13.67% | 478928.97 | -28355.72 | -5.921%
Friona - 900 Millard Ave | TX | 247324.25 | 265155 | -17830.75 | -6.725% | 382649.17 | -10606.32 | -2.772%

## 1st Qtr
Catalyze |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 5923301.1 | 7368149.323 | -1444848.223 | -19.61% | 8460490.51 | -2537189.41 | -29.99%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Fresno - 3150 Shaw Ave | CA | 192358.5656 | 190192.12 | 2166.4456 | 1.139% | 217612.88 | -25254.3144 | -11.61%
Adelanto - 1 Sheep Creek Road | CA | 698121 | 899827.54 | -201706.54 | -22.42% | 1896484.45 | -1198363.45 | -63.19%
Blackstone - 83 Federal Street | MA | 1021429 | 1250983.5 | -229554.5 | -18.35% | 1492708.3 | -471279.3 | -31.57%
Charlton - 299 Worcester Road | MA | 106387.5 | 122897.92 | -16510.42 | -13.43% | 124156.29 | -17768.79 | -14.31%
Wareham - 8 Thatcher Drive | MA | 26732.625 | 32689.431 | -5956.806 | -18.22% | 36054.829 | -9322.204 | -25.86%
West Yarmouth - 42 Mid Tech | MA | 21092.2942 | 26594.646 | -5502.3518 | -20.69% | 27861.181 | -6768.8868 | -24.3%
Harrison - 130 Union Street | NY | 38110 | 49114.896 | -11004.896 | -22.41% | 46444.25 | -8334.25 | -17.94%
Staten Island - Ellis Storage | NY | 90871.75 | 116168.46 | -25296.71 | -21.78% | 102799.02 | -11927.27 | -11.6%
Amherst - 595 Scholles Road | NY | 1004650 | 1305937.17 | -301287.17 | -23.07% | 1513702 | -509052 | -33.63%
Lancaster 1 - Gunnville Road | NY | 993680 | 1203596.5 | -209916.5 | -17.44% | 1025700 | -32020 | -3.122%
Lancaster 2 - Shisler Road | NY | 951657 | 1317386.2 | -365729.2 | -27.76% | 1119615.1 | -167958.1 | -15%
Fullerton - 200 W Orangethorpe | CA | 228387.8652 | 237208.44 | -8820.5748 | -3.718% | 268566.67 | -40178.8048 | -14.96%
El Paso - 10500 Railroad Drive | TX | 302499.25 | 350397.5 | -47898.25 | -13.67% | 330854.97 | -28355.72 | -8.57%
Friona - 900 Millard Ave | TX | 247324.25 | 265155 | -17830.75 | -6.725% | 257930.57 | -10606.32 | -4.112%

## 2nd Qtr
Catalyze |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 3586730.2794 | 4172026.29 | -585296.0106 | -14.03% | 4897603.03 | -1310872.7506 | -26.77%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Fresno - 3150 Shaw Ave | CA | 110443.9344 | 110570.8 | -126.8656 | -0.1147% | 119130.8 | -8686.8656 | -7.292%
Adelanto - 1 Sheep Creek Road | CA | 402561 | 693821 | -291260 | -41.98% | 898384 | -495823 | -55.19%
Blackstone - 83 Federal Street | MA | 606024 | 680455.2 | -74431.2 | -10.94% | 770475.3 | -164451.3 | -21.34%
Charlton - 299 Worcester Road | MA | 56399 | 57742.91 | -1343.91 | -2.327% | 70885.53 | -14486.53 | -20.44%
Wareham - 8 Thatcher Drive | MA | 16925.875 | 17111.19 | -185.315 | -1.083% | 18394.93 | -1469.055 | -7.986%
West Yarmouth - 42 Mid Tech | MA | 16282.5227 | 16635.1 | -352.5773 | -2.119% | 18770.49 | -2487.9673 | -13.25%
Harrison - 130 Union Street | NY | 21737.375 | 23442.16 | -1704.785 | -7.272% | 26207.47 | -4470.095 | -17.06%
Staten Island - Ellis Storage | NY | 56581 | 60019.33 | -3438.33 | -5.729% | 60619.51 | -4038.51 | -6.662%
Amherst - 595 Scholles Road | NY | 718270 | 768638 | -50368 | -6.553% | 953051 | -234781 | -24.63%
Lancaster 1 - Gunnville Road | NY | 557874 | 635837.5 | -77963.5 | -12.26% | 746890.6 | -189016.6 | -25.31%
Lancaster 2 - Shisler Road | NY | 609258 | 678559.1 | -69301.1 | -10.21% | 820159.4 | -210901.4 | -25.71%
Fullerton - 200 W Orangethorpe | CA | 118417.1973 | 125423.7 | -7006.5027 | -5.586% | 121841.4 | -3424.2027 | -2.81%
El Paso - 10500 Railroad Drive | TX | 160423.625 | 160278.5 | 145.125 | 0.09055% | 148074 | 12349.625 | 8.34%
Friona - 900 Millard Ave | TX | 135532.75 | 143491.8 | -7959.05 | -0.055467 | 124718.6 | 10814.15 | 0.086708

## 3rd Qtr
Catalyze |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Fresno - 3150 Shaw Ave | CA | 0 | 0 | 0 |  |  | 0
Adelanto - 1 Sheep Creek Road | CA | 0 | 0 | 0 |  |  | 0
Blackstone - 83 Federal Street | MA | 0 | 0 | 0 |  |  | 0
Charlton - 299 Worcester Road | MA | 0 | 0 | 0 |  |  | 0
Wareham - 8 Thatcher Drive | MA | 0 | 0 | 0 |  |  | 0
West Yarmouth - 42 Mid Tech | MA | 0 | 0 | 0 |  |  | 0
Harrison - 130 Union Street | NY | 0 | 0 | 0 |  |  | 0
Staten Island - Ellis Storage | NY | 0 | 0 | 0 |  |  | 0
Amherst - 595 Scholles Road | NY | 0 | 0 | 0 |  |  | 0
Lancaster 1 - Gunnville Road | NY | 0 | 0 | 0 |  |  | 0
Lancaster 2 - Shisler Road | NY | 0 | 0 | 0 |  |  | 0
Fullerton - 200 W Orangethorpe | CA | 0 | 0 | 0 |  |  | 0
El Paso - 10500 Railroad Drive | TX | 0 | 0 | 0 |  |  | 0
Friona - 900 Millard Ave | TX | 0 | 0 | 0 |  |  | 0

## 4th Qtr
Catalyze |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Fresno - 3150 Shaw Ave | CA | 0 | 0 | 0 |  |  | 0
Adelanto - 1 Sheep Creek Road | CA | 0 | 0 | 0 |  |  | 0
Blackstone - 83 Federal Street | MA | 0 | 0 | 0 |  |  | 0
Charlton - 299 Worcester Road | MA | 0 | 0 | 0 |  |  | 0
Wareham - 8 Thatcher Drive | MA | 0 | 0 | 0 |  |  | 0
West Yarmouth - 42 Mid Tech | MA | 0 | 0 | 0 |  |  | 0
Harrison - 130 Union Street | NY | 0 | 0 | 0 |  |  | 0
Staten Island - Ellis Storage | NY | 0 | 0 | 0 |  |  | 0
Amherst - 595 Scholles Road | NY | 0 | 0 | 0 |  |  | 0
Lancaster 1 - Gunnville Road | NY | 0 | 0 | 0 |  |  | 0
Lancaster 2 - Shisler Road | NY | 0 | 0 | 0 |  |  | 0
Fullerton - 200 W Orangethorpe | CA | 0 | 0 | 0 |  |  | 0
El Paso - 10500 Railroad Drive | TX | 0 | 0 | 0 |  |  | 0
Friona - 900 Millard Ave | TX | 0 | 0 | 0 |  |  | 0

## Jan
Catalyze |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 592532.4922 | 833649.635 | -241117.1428 | -28.92% | 1493236.849 | -900704.3568 | -60.32% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA | 40368.4375 | 39837.75 | 530.6875 | 1.332% | 48161.71 | -7793.2725 | -16.18% | 1.Inverter 5 tripped offline on 01/19/2024 at 12:30 & back online at 14:00. | 1.SR080353
Adelanto - 1 Sheep Creek Road | CA | 80417 | 352340 | -271923 | -77.18% | 479912 | -399495 | -83.24% | 1. Site frequently experiencing outages due to its ongoing curtailment by CAISO | 1. SR077480, SR079342
Blackstone - 83 Federal Street | MA | 106968 | 0 | 106968 |  | 352931.5 | -245963.5 | -69.69% | 1. SIte was offline from 01/15/2024 - 01/17/2024. | 1. SR080251
Charlton - 299 Worcester Road | MA | 11889 | 21739.23 | -9850.23 | -45.31% | 32151.25 | -20262.25 | -63.02% | 1. Site was offline on 01/27/2024 & back online on 01/29/2024. | 1. SR080523
Wareham - 8 Thatcher Drive | MA | 5780.1687 | 7080.061 | -1299.8923 | -18.36% | 8785.329 | -3005.1603 | -34.21%
West Yarmouth - 42 Mid Tech | MA | 4426.7571 | 5459.478 | -1032.7209 | -18.92% | 6769.56 | -2342.8029 | -34.61%
Harrison - 130 Union Street | NY | 5693.0625 | 9025.686 | -3332.6235 | -36.92% | 10708.14 | -5015.0775 | -46.83%
Staten Island - Ellis Storage | NY | 12897.375 | 21330.59 | -8433.215 | -39.54% | 23412.4 | -10515.025 | -44.91%
Amherst - 595 Scholles Road | NY | 99935 | 131383.6 | -31448.6 | -23.94% | 286492 | -186557 | -65.12% | 1. Site tripped offlline at 01/31/2024 at 09:30 & back online at 11:41. 2. Inverter 1 was offline on 01/10/2024 & back online at 01/11/2024 at 16:30. | 1.SR080616 2. SR080129
Lancaster 1 - Gunnville Road | NY
Lancaster 2 - Shisler Road | NY
Fullerton - 200 W Orangethorpe | CA | 66219.8789 | 65950.86 | 269.0189 | 0.4079% | 75151.27 | -8931.3911 | -11.88%
El Paso - 10500 Railroad Drive | TX | 94436.375 | 110748.9 | -16312.525 | -14.73% | 95880.07 | -1443.695 | -1.506%
Friona - 900 Millard Ave | TX | 63501.4375 | 68753.48 | -5252.0425 | -7.639% | 72881.62 | -9380.1825 | -12.87% | 1. Inverter 6 tripping on & off throught out the month. 2. Inverter 7 has tripping event on 01/12,1/14,1/16,1/19. | 1. SR074295 2. SR079995

## Feb
Catalyze |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 2118917.295 | 2947649.778 | -828732.483 | -28.12% | 2750893.591 | -631976.296 | -22.97%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA | 58842.25 | 57965.88 | 876.37 | 1.512% | 67323.77 | -8481.52 | -12.6% | 1. Inverter 5 tripped offline most of the days. | 1. SR080353
Adelanto - 1 Sheep Creek Road | CA | 300982 | 344128.54 | -43146.54 | -12.54% | 597256.79 | -296274.79 | -49.61% | 1. Expected data was not populated for multiple days due to a weather station issue. 2. Inverter 4 turned offline on 02/23 & continued. 3. Site frequently experiencing outages due to its ongoing curtailment by CAISO | 1. SR081023 2. SR081269 3. SR081208
Blackstone - 83 Federal Street | MA | 371405 | 591797.9 | -220392.9 | -37.24% | 474063.7 | -102658.7 | -21.66% | 1. Inverter tripped offline on 02/23/2024 & back online on 02/26/2024. | 1. SR081287
Charlton - 299 Worcester Road | MA | 41404 | 47717.86 | -6313.86 | -13.23% | 31813.95 | 9590.05 | 30.14% | 1. Inverter 1 is offline from 02/05 to 02/14 & tripped offline from 02/20 at 10:30 & back online on 02/26 at 16:30. 2. Inverter 13 tripping on and off during high irradiance days. | 1.SR080728 2. SR081303
Wareham - 8 Thatcher Drive | MA | 7001.2688 | 11238.1 | -4236.8312 | -37.7% | 11253.3 | -4252.0312 | -37.78%
West Yarmouth - 42 Mid Tech | MA | 4449.0054 | 8729.468 | -4280.4626 | -49.03% | 7749.511 | -3300.5056 | -42.59%
Harrison - 130 Union Street | NY | 10644.0445 | 17668.44 | -7024.3955 | -39.76% | 14230.04 | -3585.9955 | -25.2%
Staten Island - Ellis Storage | NY | 28780.5 | 41920.19 | -13139.69 | -31.34% | 28582.98 | 197.52 | 0.691%
Amherst - 595 Scholles Road | NY | 238762 | 462549 | -223787 | -48.38% | 462796 | -224034 | -48.41% | 1. Inverter 2 tripping on & off on 02/03 & 02/04 & continued offline from 02/05 to 02/28. 2. Site was taken offline on 02/27/2023 at 12:53 & back online on 02/28. | 1. SR080713 2. SR081369
Lancaster 1 - Gunnville Road | NY | 422356 | 522536.7 | -100180.7 | -19.17% | 381411.8 | 40944.2 | 10.73% | 1. Site tripped offline on 02/10 & back online on 02/12 at 15:15. | 1.SR080915
Lancaster 2 - Shisler Road | NY | 393093 | 577373.1 | -184280.1 | -31.92% | 412202.9 | -19109.9 | -4.636% | 1. Site tripped offline on 02/10 & back online on 02/12 at 15:15. 2. Inverter 4.4 is offline on 02/18 and back online next day. 3. Inverter 4.4 was derating on multiple days this month due to a fan fault... 3. Inverters 3.1 through 3.6, and inverters 3.8 through 3.10 started derating on 02/25 & continued. | 1. SR080916 2. SR081087 3. SR081047 4. SR081344
Fullerton - 200 W Orangethorpe | CA | 64169.3512 | 65724.88 | -1555.5288 | -2.367% | 81499 | -17329.6488 | -21.26%
El Paso - 10500 Railroad Drive | TX | 102707.75 | 113239.9 | -10532.15 | -9.301% | 101578.9 | 1128.85 | 1.111%
Friona - 900 Millard Ave | TX | 74321.125 | 85059.82 | -10738.695 | -12.62% | 79130.95 | -4809.825 | -6.078% | 1. Inverter 6 tripping on & off throught out the month. | 1.SR074295

## Mar
Catalyze |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 3211851.3128 | 3586849.91 | -374998.5972 | -10.45% | 4216360.07 | -1004508.7572 | -23.82%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA | 93147.8781 | 92388.49 | 759.3881 | 0.822% | 102127.4 | -8979.5219 | -8.792% | 1. Site was offline on 03/20 between 10:50am to 12:15pm 2. Inverter 5 has tripping events on daily bases | 1. SR082279 2. SR082780
Adelanto - 1 Sheep Creek Road | CA | 316722 | 203359 | 113363 | 55.75% | 819315.66 | -502593.66 | -61.34% | 1. Weather station reporting zero from 03/01 and resolved on 03/20 at 13:00 due to that expected energy is low 2. Sit was offline on 03/27 between 08:00am to 12:00 pm 3. Inverter 4 is offline throughout the month, breaker need to be replaced | 1. SR081023 2. SR082819 3. SR081269
Blackstone - 83 Federal Street | MA | 543056 | 659185.6 | -116129.6 | -17.62% | 665713.1 | -122657.1 | -18.42% | 1. Inverter tripped offline on 03/24 at 12:00pm and back online on 03/25 at 10:15am | 1. SR082618
Charlton - 299 Worcester Road | MA | 53094.5 | 53440.83 | -346.33 | -0.6481% | 60191.09 | -7096.59 | -11.79%
Wareham - 8 Thatcher Drive | MA | 13951.1875 | 14371.27 | -420.0825 | -2.923% | 16016.2 | -2065.0125 | -12.89%
West Yarmouth - 42 Mid Tech | MA | 12216.5316 | 12405.7 | -189.1684 | -1.525% | 13342.11 | -1125.5784 | -8.436%
Harrison - 130 Union Street | NY | 21772.893 | 22420.77 | -647.877 | -2.89% | 21506.07 | 266.823 | 1.241%
Staten Island - Ellis Storage | NY | 49193.875 | 52917.68 | -3723.805 | -7.037% | 50803.64 | -1609.765 | -3.169%
Amherst - 595 Scholles Road | NY | 665953 | 712004.57 | -46051.57 | -6.468% | 764414 | -98461 | -12.88%
Lancaster 1 - Gunnville Road | NY | 571324 | 681059.8 | -109735.8 | -16.11% | 644288.2 | -72964.2 | -11.32% | 1. Site tripped offline on 03/10 at 17:30 and back online on 03/11 at 11:00am 2. Site tripped offline on 03/13 at 12:25pm and back online on 03/14 at 08:35am | 1. SR081733 2. SR081870
Lancaster 2 - Shisler Road | NY | 558564 | 740013.1 | -181449.1 | -24.52% | 707412.2 | -148848.2 | -21.04% | 1. Inverters 3.1 to 3.10 are derating from 02/26 to 03/09. 2. Site tripped offline, Voltages available at the meter. Possible main breaker trip at 12:15 on 03/13 and back online at 8:30 on 03/14. | 1. SR081344 2. SR081871
Fullerton - 200 W Orangethorpe | CA | 97998.635 | 105532.7 | -7534.065 | -7.139% | 111916.4 | -13917.765 | -12.44% | 1. Inverter 3 is derating on sunny days resolved on 03/26 2. Site was offline on 03/13 between 08:30am to 09:15 | 1. SR081571 2. SR081844
El Paso - 10500 Railroad Drive | TX | 105355.125 | 126408.7 | -21053.575 | -16.66% | 133396 | -28040.875 | -21.02% | 1. Site tripped offline due to missing "Phase A voltages" at 11:45 on 03/17 and back online at 10:30 on 03/25. | 1. SR081970
Friona - 900 Millard Ave | TX | 109501.6875 | 111341.7 | -1840.0125 | -1.653% | 105918 | 3583.6875 | 3.383% | 1. Inverter 6 tripping on & off on 03/05, 03/18, 03/25, 03/26. | 1. SR074295

## Apr
Catalyze |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 3586730.2794 | 4172026.29 | -585296.0106 | -14.03% | 4897603.03 | -1310872.7506 | -26.77%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA | 110443.9344 | 110570.8 | -126.8656 | -0.1147% | 119130.8 | -8686.8656 | -7.292% | 1. Inverter 5 has tripping events on daily bases. | 1. SR082780
Adelanto - 1 Sheep Creek Road | CA | 402561 | 693821 | -291260 | -41.98% | 898384 | -495823 | -55.19% | 1. Inverter 4 is offline throughout the month, breaker need to be replaced | 1. SR081269
Blackstone - 83 Federal Street | MA | 606024 | 680455.2 | -74431.2 | -10.94% | 770475.3 | -164451.3 | -21.34%
Charlton - 299 Worcester Road | MA | 56399 | 57742.91 | -1343.91 | -2.327% | 70885.53 | -14486.53 | -20.44% | 1. Inverter 6 tripped offline on 04/28 at 6:30AM and back online on 04/28 at 7:45am | 1. SR083896
Wareham - 8 Thatcher Drive | MA | 16925.875 | 17111.19 | -185.315 | -1.083% | 18394.93 | -1469.055 | -7.986%
West Yarmouth - 42 Mid Tech | MA | 16282.5227 | 16635.1 | -352.5773 | -2.119% | 18770.49 | -2487.9673 | -13.25%
Harrison - 130 Union Street | NY | 21737.375 | 23442.16 | -1704.785 | -7.272% | 26207.47 | -4470.095 | -17.06% | 1. Site was offline from 13:15 to 15:00 on 04/29. 2. Site is offline on 04/03 at 18:45 and back online on 9:30am on 04/05 and again offline on 04/07 10:00am and back online on 04/07 at 12:30pm. | 1. SR083973 2. SR082599
Staten Island - Ellis Storage | NY | 56581 | 60019.33 | -3438.33 | -5.729% | 60619.51 | -4038.51 | -6.662%
Amherst - 595 Scholles Road | NY | 718270 | 768638 | -50368 | -6.553% | 953051 | -234781 | -24.63% | 1. Site tripped offline on 04/09 at 17:52 and back online on 04/10 at 16:00 2. Site tripped offline on 04/17 at 10:52 and back online on 12:00pm | 1. SR083278 2. SR083540
Lancaster 1 - Gunnville Road | NY | 557874 | 635837.5 | -77963.5 | -12.26% | 746890.6 | -189016.6 | -25.31% | 1. Inverter 1.3 is offline on 04/08 and back online on 04/08 at 15:15 2. All inverters tripped offline at 15:02 on 04/19 and back online on 04/22 at 8:30am | 1. SR083167 2. SR083639
Lancaster 2 - Shisler Road | NY | 609258 | 678559.1 | -69301.1 | -10.21% | 820159.4 | -210901.4 | -25.71% | 1. All inverters tripped offline at 15:02 on 04/19 and back online on 04/22 at 8:30am | 1. SR083640
Fullerton - 200 W Orangethorpe | CA | 118417.1973 | 125423.7 | -7006.5027 | -5.586% | 121841.4 | -3424.2027 | -2.81% | 1. Site is offline on 04/13 at 21:00 on 04/13/2024 and back online on 04/13 at 23:00. | 1. SR083388
El Paso - 10500 Railroad Drive | TX | 160423.625 | 160278.5 | 145.125 | 0.09055% | 148074 | 12349.625 | 8.34% | 1. Inverter 6 tripping on and off on 04/02, 04/06, 04/20, 04/22, 04/27, 04/29 & 04/30 with fault "Fault to stop DC wrong polarity." | 1. SR083891
Friona - 900 Millard Ave | TX | 135532.75 | 143491.8 | -7959.05 | -5.547% | 124718.6 | 10814.15 | 8.671% | 1. Inverter 6 tripping on & off 04/12, 04/14, 04/17, 04/18, 04/20, 04/21 & 04/27 | 1. SR074295

## May
Catalyze |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA
Adelanto - 1 Sheep Creek Road | CA
Blackstone - 83 Federal Street | MA
Charlton - 299 Worcester Road | MA
Wareham - 8 Thatcher Drive | MA
West Yarmouth - 42 Mid Tech | MA
Harrison - 130 Union Street | NY
Staten Island - Ellis Storage | NY
Amherst - 595 Scholles Road | NY
Lancaster 1 - Gunnville Road | NY
Lancaster 2 - Shisler Road | NY
Fullerton - 200 W Orangethorpe | CA
El Paso - 10500 Railroad Drive | TX
Friona - 900 Millard Ave | TX

## Jun
Catalyze |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA
Adelanto - 1 Sheep Creek Road | CA
Blackstone - 83 Federal Street | MA
Charlton - 299 Worcester Road | MA
Wareham - 8 Thatcher Drive | MA
West Yarmouth - 42 Mid Tech | MA
Harrison - 130 Union Street | NY
Staten Island - Ellis Storage | NY
Amherst - 595 Scholles Road | NY
Lancaster 1 - Gunnville Road | NY
Lancaster 2 - Shisler Road | NY
Fullerton - 200 W Orangethorpe | CA
El Paso - 10500 Railroad Drive | TX
Friona - 900 Millard Ave | TX

## Jul
Catalyze |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA
Adelanto - 1 Sheep Creek Road | CA
Blackstone - 83 Federal Street | MA
Charlton - 299 Worcester Road | MA
Wareham - 8 Thatcher Drive | MA
West Yarmouth - 42 Mid Tech | MA
Harrison - 130 Union Street | NY
Staten Island - Ellis Storage | NY
Amherst - 595 Scholles Road | NY
Lancaster 1 - Gunnville Road | NY
Lancaster 2 - Shisler Road | NY
Fullerton - 200 W Orangethorpe | CA
El Paso - 10500 Railroad Drive | TX
Friona - 900 Millard Ave | TX

## Aug
Catalyze |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA
Adelanto - 1 Sheep Creek Road | CA
Blackstone - 83 Federal Street | MA
Charlton - 299 Worcester Road | MA
Wareham - 8 Thatcher Drive | MA
West Yarmouth - 42 Mid Tech | MA
Harrison - 130 Union Street | NY
Staten Island - Ellis Storage | NY
Amherst - 595 Scholles Road | NY
Lancaster 1 - Gunnville Road | NY
Lancaster 2 - Shisler Road | NY
Fullerton - 200 W Orangethorpe | CA
El Paso - 10500 Railroad Drive | TX
Friona - 900 Millard Ave | TX

## Sep
Catalyze |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA
Adelanto - 1 Sheep Creek Road | CA
Blackstone - 83 Federal Street | MA
Charlton - 299 Worcester Road | MA
Wareham - 8 Thatcher Drive | MA
West Yarmouth - 42 Mid Tech | MA
Harrison - 130 Union Street | NY
Staten Island - Ellis Storage | NY
Amherst - 595 Scholles Road | NY
Lancaster 1 - Gunnville Road | NY
Lancaster 2 - Shisler Road | NY
Fullerton - 200 W Orangethorpe | CA
El Paso - 10500 Railroad Drive | TX
Friona - 900 Millard Ave | TX

## Oct
Catalyze |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA
Adelanto - 1 Sheep Creek Road | CA
Blackstone - 83 Federal Street | MA
Charlton - 299 Worcester Road | MA
Wareham - 8 Thatcher Drive | MA
West Yarmouth - 42 Mid Tech | MA
Harrison - 130 Union Street | NY
Staten Island - Ellis Storage | NY
Amherst - 595 Scholles Road | NY
Lancaster 1 - Gunnville Road | NY
Lancaster 2 - Shisler Road | NY
Fullerton - 200 W Orangethorpe | CA
El Paso - 10500 Railroad Drive | TX
Friona - 900 Millard Ave | TX

## Nov
Catalyze |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA
Adelanto - 1 Sheep Creek Road | CA
Blackstone - 83 Federal Street | MA
Charlton - 299 Worcester Road | MA
Wareham - 8 Thatcher Drive | MA
West Yarmouth - 42 Mid Tech | MA
Harrison - 130 Union Street | NY
Staten Island - Ellis Storage | NY
Amherst - 595 Scholles Road | NY
Lancaster 1 - Gunnville Road | NY
Lancaster 2 - Shisler Road | NY
Fullerton - 200 W Orangethorpe | CA
El Paso - 10500 Railroad Drive | TX
Friona - 900 Millard Ave | TX

## Dec
Catalyze |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Fresno - 3150 Shaw Ave | CA
Adelanto - 1 Sheep Creek Road | CA
Blackstone - 83 Federal Street | MA
Charlton - 299 Worcester Road | MA
Wareham - 8 Thatcher Drive | MA
West Yarmouth - 42 Mid Tech | MA
Harrison - 130 Union Street | NY
Staten Island - Ellis Storage | NY
Amherst - 595 Scholles Road | NY
Lancaster 1 - Gunnville Road | NY
Lancaster 2 - Shisler Road | NY
Fullerton - 200 W Orangethorpe | CA
El Paso - 10500 Railroad Drive | TX
Friona - 900 Millard Ave | TX

## Sites
Portfolio: | Catalyze
Site DAS Name | Site | State | Update | DAS
CA Fresno - 3150 Shaw Ave - 19600 | Fresno - 3150 Shaw Ave | CA | AEF | PowerTrack
Sheep Creek Solar | Adelanto - 1 Sheep Creek Road | CA |  | Aderis
MA Blackstone - 83 Federal St - 18170 | Blackstone - 83 Federal Street | MA | AEF | PowerTrack
MA Charlton - 299 Worcester Rd - 18063 | Charlton - 299 Worcester Road | MA | AEF | PowerTrack
MA Wareham - 8 Thatcher Ln - 1010 | Wareham - 8 Thatcher Drive | MA | AEF | PowerTrack
MA West Yarmouth - 42 Mid-Tech Drive - 17944 | West Yarmouth - 42 Mid Tech | MA | AEF | PowerTrack
NY Harrison - 130 Union Ave - 18141 | Harrison - 130 Union Street | NY | AEF | PowerTrack
NY Staten Island - 1 Ellis St - 18195 | Staten Island - Ellis Storage | NY | AEF | PowerTrack
Amherst Community Solar | Amherst - 595 Scholles Road | NY |  | Aderis
Lancaster 1 - Gunnville Road | Lancaster 1 - Gunnville Road | NY |  | PowerTrack
Lancaster 2 - Shisler Road | Lancaster 2 - Shisler Road | NY |  | PowerTrack
Fullerton - 200 W Orangethorpe - 19603 | Fullerton - 200 W Orangethorpe | CA |  | PowerTrack
TX El Paso - 10500 Railroad Drive - 19648 | El Paso - 10500 Railroad Drive | TX | AEF | PowerTrack
TX Friona - 900 Millard Ave - 19506 | Friona - 900 Millard Ave | TX | AEF | PowerTrack