## Year to Date
Canton Ice House |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 385913.8031 | 0 | 385913.8031 | 0% | 0 | 385913.8031 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 385913.8031 | 0 | 385913.8031 |  | 0 | 385913.8031

## 1st Qtr
Canton Ice House |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 53753.287 | 0 | 53753.287 | 0% | 0 | 53753.287 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 53753.287 | 0 | 53753.287 |  | 0 | 53753.287

## 2nd Qtr
Canton Ice House |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 72238.341 | 0 | 72238.341 | 0% | 0 | 72238.341 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 72238.341 | 0 | 72238.341 |  |  | 72238.341

## 3rd Qtr
Canton Ice House |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 173103.1156 | 0 | 173103.1156 | 0% | 0 | 173103.1156 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 173103.1156 | 0 | 173103.1156 |  | 0 | 173103.1156

## 4th Qtr
Canton Ice House |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 86819.0596 | 0 | 86819.0596 | 0% | 0 | 86819.0596 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 86819.0596 | 0 | 86819.0596 |  | 0 | 86819.0596

## Jan
Canton Ice House |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 10619.76 | 0 | 10619.76 | 0% | 0 | 10619.76 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 10619.76 | 0 | 10619.76 |  | 0 | 10619.76 |  | 1. Inverter 9 was offline since 01/07. | 1. SR080386

## Feb
Canton Ice House |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 30895 | 0 | 30895 | 0% | 0 | 30895 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 30895 | 0 | 30895 |  | 0 | 30895 |  | 1. Inverter 9 is offline throughout the month. 2. Inverter 3 tripped offline at 11:30 on 02/16 & back online on 02/20 at 09:30 | 1.SR080386 2.SR081057

## Mar
Canton Ice House |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 12238.527 | 0 | 12238.527 | 0% | 0 | 12238.527 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 12238.527 | 0 | 12238.527 |  | 0 | 12238.527 |  | 1. Site tripped offline on 03/12 at 09:30 & continued throughout the month. 2. Inverter 9 is offline throughout the month. 3. Inverters 1, 11, 13 are underproducing around 15kW each compared to its peers since 03/08. | 1.SR081798 2.SR080386 3. SR081706

## Apr
Canton Ice House |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site tripped offline on 03/12 at 09:30 & continued throughout the month. | 1.SR081798

## May
Canton Ice House |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 2063.197 | 0 | 2063.197 | 0% | 0 | 2063.197 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 2063.197 | 0 | 2063.197 |  | 0 | 2063.197 |  | 1. Site is offline from 03/12 and back online on 05/31. 2. Inverter 8,9,11 and 12 are offline from 05/31. 3. Inverters 1, 13 are underproducing around 15kW each compared to its peers since 03/08. | 1. SR081798 2. SR085347 3. SR081706

## Jun
Canton Ice House |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 70175.144 | 0 | 70175.144 | 0% | 0 | 70175.144 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 70175.144 | 0 | 70175.144 |  | 0 | 70175.144 |  | 1. Inverter 8,9,11 and 12 are offline from 05/31 and 8, 12 back online at 12:00PM on 06/06 and inverter 9 and 11 are back online on 06/25 after replacing relay boards. 2. Inverters 1, 13 are underproducing around 15kW each compared to its peers since 03/08. | 1. SR085347 2. SR081706

## Jul
Canton Ice House |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 69541.3551 | 0 | 69541.3551 | 0% | 0 | 69541.3551 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 69541.3551 | 0 | 69541.3551 |  | 0 | 69541.3551

## Aug
Canton Ice House |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 57395.8899 | 0 | 57395.8899 | 0% | 0 | 57395.8899 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 57395.8899 | 0 | 57395.8899 |  | 0 | 57395.8899 |  | 1.Inverter 8 is offline on 08/09 and back online at 12:45 on 08/30. Inverter 13 is offline on 08/15 and back online at 14:00 on 08/30. 2. Inverters 4,6 are tripped offline on 08/15 at 16:30PM and back online on 08/16. 3. Inverter 1 is derating due to multiple tripping. inverters 8 and 13 are being RMA'd and inverter 12 kept offline due to multiple breaker trip events on 08/22. | 1.SR088801 2.SR089140 3.SR089210

## Sep
Canton Ice House |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 46165.8706 | 0 | 46165.8706 | 0% | 0 | 46165.8706 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 46165.8706 | 0 | 46165.8706 |  | 0 | 46165.8706 |  | 1.Site is offline from 09/14 at 08:5 and back online on 09/16 at 08:45 | 1.SR090424

## Oct
Canton Ice House |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 44019.7201 | 0 | 44019.7201 | 0% | 0 | 44019.7201 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 44019.7201 | 0 | 44019.7201 |  | 0 | 44019.7201 |  | 1. Inverter 12 kept offline due to multiple breaker trip events since 08/22. | 1.SR089210

## Nov
Canton Ice House |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 26899.6351 | 0 | 26899.6351 | 0% | 0 | 26899.6351 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 26899.6351 | 0 | 26899.6351 |  | 0 | 26899.6351 |  | 1.Inverter 8 was tripped offline at 16:15 from 11/02 throughout the month 2.Inverter 5 was tripped offline at 11:00AM on 11/12 and came back online at 8:45AM on 11/13 3.Inverter 12 back online on 11:30AM on 11/12 | 1.SR092906 , SR089210 2.SR093173 3.SR088801

## Dec
Canton Ice House |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 15899.7044 | 0 | 15899.7044 | 0% | 0 | 15899.7044 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 15899.7044 | 0 | 15899.7044 |  | 0 | 15899.7044 |  | 1.Inverter 8 was tripped offline at 16:15 from 11/02 and being RMA'd on 12/17. | 1. SR089210, SR093239

## Sites
Portfolio: | Canton Ice House
Site DAS Name | Site | State | Update | DAS
Canton Ice House | MA: Canton - Canton Ice House | MA | AF | PowerTrack