## Year to Date
Crawford Realty |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 640338.8101 | 0 | 640338.8101 | 0% | 775969.14 | -135630.3299 | -17.48%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Leominster - Crawford Realty | MA | 640338.8101 | 0 | 640338.8101 |  | 775969.14 | -135630.3299 | -17.48%

## 1st Qtr
Crawford Realty |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 114973.46 | 0 | 114973.46 | 0% | 160155.33 | -45181.87 | -28.21%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Leominster - Crawford Realty | MA | 114973.46 | 0 | 114973.46 |  | 160155.33 | -45181.87 | -28.21%

## 2nd Qtr
Crawford Realty |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 223435.82 | 0 | 223435.82 | 0% | 254891.64 | -31455.82 | -12.34%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Leominster - Crawford Realty | MA | 223435.82 | 0 | 223435.82 |  | 254891.64 | -31455.82 | -12.34%

## 3rd Qtr
Crawford Realty |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 199464.23 | 0 | 199464.23 | 0% | 241389.56 | -41925.33 | -17.37%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Leominster - Crawford Realty | MA | 199464.23 | 0 | 199464.23 |  | 241389.56 | -41925.33 | -17.37%

## 4th Qtr
Crawford Realty |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 102465.3001 | 0 | 102465.3001 | 0% | 119532.61 | -17067.3099 | -14.28%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Leominster - Crawford Realty | MA | 102465.3001 | 0 | 102465.3001 |  | 119532.61 | -17067.3099 | -14.28%

## Jan
Crawford Realty |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 12170.51 | 0 | 12170.51 | 0% | 41972 | -29801.49 | -71%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 12170.51 | 0 | 12170.51 |  | 41972 | -29801.49 | -71%

## Feb
Crawford Realty |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 43982.7 | 0 | 43982.7 | 0% | 50056.05 | -6073.35 | -12.13%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 43982.7 | 0 | 43982.7 |  | 50056.05 | -6073.35 | -12.13% | 1. Inverter 2 left unit tripped offline on 12/13 and back online on 02/21 | 1. SR081019

## Mar
Crawford Realty |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 58820.25 | 0 | 58820.25 | 0% | 68127.28 | -9307.03 | -13.66%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 58820.25 | 0 | 58820.25 |  | 68127.28 | -9307.03 | -13.66% | 1.Inverter 2 left unit was offline on 03/13 and came back online on the same day at 14:00 | 1.SR081843

## Apr
Crawford Realty |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 66128.41 | 0 | 66128.41 | 0% | 78747.81 | -12619.4 | -16.03%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 66128.41 | 0 | 66128.41 |  | 78747.81 | -12619.4 | -16.03%

## May
Crawford Realty |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 75145.87 | 0 | 75145.87 | 0% | 88197.12 | -13051.25 | -14.8%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 75145.87 | 0 | 75145.87 |  | 88197.12 | -13051.25 | -14.8% | 1. Inverter 5 ( E in dwg)primary unit tripped offline on 05/12 at 16:45 throughout the month. | 1. SR084649

## Jun
Crawford Realty |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 82161.54 | 0 | 82161.54 | 0% | 87946.71 | -5785.17 | -6.578%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 82161.54 | 0 | 82161.54 |  | 87946.71 | -5785.17 | -6.578% | 1. Inverter 5 ( E in dwg)primary unit tripped offline on 05/12 at 16:45 throughout the month. | 1. SR084649

## Jul
Crawford Realty |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 83541.84 | 0 | 83541.84 | 0% | 88981.38 | -5439.54 | -6.113%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 83541.84 | 0 | 83541.84 |  | 88981.38 | -5439.54 | -6.113% | 1.Inverter 5 ( E in dwg)primary unit tripped offline on 05/12 at 16:45 and back online at 11:46 on 07/16. | 1.SR084649

## Aug
Crawford Realty |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 66481.85 | 0 | 66481.85 | 0% | 84063.75 | -17581.9 | -20.91%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 66481.85 | 0 | 66481.85 |  | 84063.75 | -17581.9 | -20.91% | 1. Inverter 4 (B) Right and left unit tripped on 8/18 | 1.SR089250

## Sep
Crawford Realty |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 49440.54 | 0 | 49440.54 | 0% | 68344.43 | -18903.89 | -27.66%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 49440.54 | 0 | 49440.54 |  | 68344.43 | -18903.89 | -27.66% | 1.Inverter 4 (B) Right and left unit tripped on 8/18 | 1.SR089250

## Oct
Crawford Realty |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 42689.38 | 0 | 42689.38 | 0% | 51502.41 | -8813.03 | -17.11%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 42689.38 | 0 | 42689.38 |  | 51502.41 | -8813.03 | -17.11% | 1. Inverter 4 (B) Right and left unit back online on 10/18/2024. 2. Inverter 3 Right unit tripped offline on 09/26/2024 through the month. | 1. SR089250 2. SR089250, SR092051

## Nov
Crawford Realty |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 36747.8101 | 0 | 36747.8101 | 0% | 37839.04 | -1091.2299 | -2.884%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 36747.8101 | 0 | 36747.8101 |  | 37839.04 | -1091.2299 | -2.884% | 1. Inverter 3 Right unit back online at 12:00 on 11/12/2024. | 1. SR089250, SR092051

## Dec
Crawford Realty |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 23028.11 | 0 | 23028.11 | 0% | 30191.16 | -7163.05 | -23.73%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Leominster - Crawford Realty | MA | 23028.11 | 0 | 23028.11 |  | 30191.16 | -7163.05 | -23.73%

## Sites
Portfolio: | Crawford Realty
Site DAS Name | Site | State | Update | DAS
101 Crawford | MA: Leominster - Crawford Realty | MA | AF | PowerTrack