## Year to Date
Freepoint |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 8470391.8997 | 9398899.504 | -928507.6043 | -9.879% | 7070840.1997 | 1399551.7 | 19.79%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NY: Coxsackie - State Route 9 West | NY | 8470391.8997 | 9398899.504 | -928507.6043 | -9.879% | 7070840.1997 | 54807.8497 | 0.7751%

## 1st Qtr
Freepoint |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 1387741 | 1609829 | -222088 | -13.8% | 1820407 | -432666 | -23.77%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NY: Coxsackie - State Route 9 West | NY | 1387741 | 1609829 | -222088 | -13.8% | 1820407 | -432666 | -23.77%

## 2nd Qtr
Freepoint |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 2957044.9 | 3276346.839 | -319301.939 | -9.746% | 2637177.77 | 319867.13 | 12.13%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NY: Coxsackie - State Route 9 West | NY | 2957044.9 | 3276346.839 | -319301.939 | -9.746% | 2637177.77 | 319867.13 | 12.13%

## 3rd Qtr
Freepoint |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 2618606.6085 | 2684537.965 | -65931.3565 | -2.456% | 1630968.6297 | 987637.9788 | 60.56%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NY: Coxsackie - State Route 9 West | NY | 2618606.6085 | 2684537.965 | -65931.3565 | -2.456% | 1630968.6297 | -37102.1715 | -2.275%

## 4th Qtr
Freepoint |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 1506999.3912 | 1828185.7 | -321186.3088 | -17.57% | 982286.8 | 524712.5912 | 53.42%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NY: Coxsackie - State Route 9 West | NY | 1506999.3912 | 1828185.7 | -321186.3088 | -17.57% | 982286.8 | 204708.8912 | 20.84%

## Jan
Freepoint |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 218416 | 252237 | -33821 | -13.41% | 463971 | -245555 | -52.92%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 218416 | 252237 | -33821 | -13.41% | 463971 | -245555 | -52.92% | 1. Site tripped offline on 01/04/2024 at 08:30 & back online on 01/09/2024 at 09:45. 2. Site tripped offline due to Utility outage on 1/18 at 1:15 AM and back online at 5:00 AM on the same day | 1. SR079936 2. SR080309

## Feb
Freepoint |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 615270 | 719590 | -104320 | -14.5% | 588255 | 27015 | 4.592%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 615270 | 719590 | -104320 | -14.5% | 588255 | 27015 | 4.592%

## Mar
Freepoint |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 554055 | 638002 | -83947 | -13.16% | 768181 | -214126 | -27.87%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 554055 | 638002 | -83947 | -13.16% | 768181 | -214126 | -27.87% | 1. Site was offline from 03/11 to 03/14 at 10:45. 2. Site tripped offline at 15:40 on 03/25 & back online on 03/26 at 09:45. | 1. SR081759 2.SR082726

## Apr
Freepoint |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 736702 | 827800 | -91098 | -11% | 839914 | -103212 | -12.29%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 736702 | 827800 | -91098 | -11% | 839914 | -103212 | -12.29% | 1. Site is offline on 04/10 due to planned outage & back online on 04/11 at 08:30. 2. Site is offline on 04/16 from 09:15 to 10:30. 3. Site tripped offline on 04/22 at 10:30 & back online at 13:40 & again tripped offline at 14:00, back online at 17:15. | 1. SR083290 2. SR083482 3. SR083686

## May
Freepoint |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 1116473 | 1218952.94 | -102479.94 | -8.407% | 900955.66 | 215517.34 | 23.92%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 1116473 | 1218952.94 | -102479.94 | -8.407% | 900955.66 | 215517.34 | 23.92% | 1. Site is offline on 05/15 at 20:30 due to relay open and later technician closed the relay at site and back online on 05/16 at 12:15pm | 1. SR084756

## Jun
Freepoint |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 1103869.9 | 1229593.899 | -125723.999 | -10.22% | 896308.11 | 207561.79 | 23.16%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 1103869.9 | 1229593.899 | -125723.999 | -10.22% | 896308.11 | 207561.79 | 23.16% | 1. Inverter 2.12 is offline on 06/09 and it has been RMA'd and back online on 06/24 at 11:30AM. | 1. SR085776

## Jul
Freepoint |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 915922.35 | 997665.265 | -81742.915 | -8.193% | 968048.88 | -52126.53 | -5.385%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 915922.35 | 997665.265 | -81742.915 | -8.193% | 968048.88 | -52126.53 | -5.385% | 1.Site was offline on 07/01 at 7:15PM and back online on 07/02 at 11:00AM 2.Site was offline on 07/07 at 10:00AM and back online on 07/09 at 6:15PM 3.Inverter 2.11 tripped offline on 07/10 at 11:15 through out the day and again tripped offline on 07/11,07/12,07/13 at 16:15 and resolving overnight. 4.Site was offline on 07/14 at 1:30PM and back online on 07/15 at 8:00AM 5.Site was offline on 07/26 at 11:30AM and back online on 07/27 at 09:15AM and again offline on 07/28 at 09:30AM and back online on 07/29 at 08:15AM | 1.SR087223 2.SR087442 3.SR087565 4.SR087662 5.SR088277

## Aug
Freepoint |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 823514.6497 | 819928.2 | 3586.4497 | 0.4374% | 924127.4 | -100612.7503 | -10.89%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 823514.6497 | 819928.2 | 3586.4497 | 0.4374% | 924127.4 | -100612.7503 | -10.89% | 1. Site offline at 11:00 from 8/10 and back online on 8/12 at 08:45. | 1. SR088874

## Sep
Freepoint |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 879169.6088 | 866944.5 | 12225.1088 | 1.41% | 763532.5 | 115637.1088 | 15.15%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 879169.6088 | 866944.5 | 12225.1088 | 1.41% | 763532.5 | 115637.1088 | 15.15%

## Oct
Freepoint |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 786213.3912 | 931800.9 | -145587.5088 | -15.62% | 567159.2 | 219054.1912 | 38.62%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 786213.3912 | 931800.9 | -145587.5088 | -15.62% | 567159.2 | 219054.1912 | 38.62% | 1. Site was taken offline by EPC from 15:00 to 17:45 on 10/02 2. Site is offline on 01:00 and back online at 03:30 on 10/11 3. Inverters 1.17 & 2.11 are underperforming approximately 7 kW from 10/06 and issue resolved on 10/21. | 1.PM6558 2.SR092029 3. SR092251

## Nov
Freepoint |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 434986 | 527369.5 | -92383.5 | -17.52% | 415127.6 | 19858.4 | 4.784%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 434986 | 527369.5 | -92383.5 | -17.52% | 415127.6 | 19858.4 | 4.784% | 1. Site tripped offline at 13:00 on 11/09 and and back online at 07:45 on 11/11 2. Inverter 2.11 is offline from 09:30AM to 11:15AM on 11/08. | 1. SR093113 2. SR092815

## Dec
Freepoint |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 285800 | 369015.3 | -83215.3 | -22.55% | 320003.7 | -34203.7 | -10.69%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NY: Coxsackie - State Route 9 West | NY | 285800 | 369015.3 | -83215.3 | -22.55% | 320003.7 | -34203.7 | -10.69%

## Sites
Portfolio: | Freepoint
Site DAS Name | Site | State | Update | DAS
Coxsackie | NY: Coxsackie - State Route 9 West | NY | AEF | PowerTrack