## Year to Date
Lake Havasu USD |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 672096 | 692408.93 | -20312.93 | -2.934% | 0 | 672096 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu - District Office | AZ | 336978 | 317701.19 | 19276.81 | 6.068% | 0 | 336978 | 0%
AZ: Lake Havasu - HS Library | AZ | 153213 | 152239.41 | 973.59 | 0.6395% | 0 | 153213 | 0%
AZ: Lake Havasu- Performing Arts | AZ | 181905 | 222468.33 | -40563.33 | -18.23% | 0 | 181905 | 0%

## 1st Qtr
Lake Havasu USD |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 140423 | 132268.19 | 8154.81 | 6.165% | 0 | 140423 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu - District Office | AZ | 66512 | 52524.83 | 13987.17 | 26.63% | 0 | 66512 | 0%
AZ: Lake Havasu - HS Library | AZ | 31104 | 35099.29 | -3995.29 | -11.38% | 0 | 31104 | 0%
AZ: Lake Havasu- Performing Arts | AZ | 42807 | 44644.07 | -1837.07 | -4.115% | 0 | 42807 | 0%

## 2nd Qtr
Lake Havasu USD |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 216026 | 226225.04 | -10199.04 | -4.508% | 0 | 216026 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu - District Office | AZ | 106156 | 106173.38 | -17.38 | -0.01637% | 0 | 106156
AZ: Lake Havasu - HS Library | AZ | 48611 | 47676.27 | 934.73 | 1.961% | 0 | 48611
AZ: Lake Havasu- Performing Arts | AZ | 61259 | 72375.39 | -11116.39 | -15.36% | 0 | 61259

## 3rd Qtr
Lake Havasu USD |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 179853 | 200677.49 | -20824.49 | -10.38% | 0 | 179853 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu - District Office | AZ | 98186 | 94630.36 | 3555.64 | 3.757% | 0 | 98186
AZ: Lake Havasu - HS Library | AZ | 43586 | 42115.03 | 1470.97 | 3.493% | 0 | 43586
AZ: Lake Havasu- Performing Arts | AZ | 38081 | 63932.1 | -25851.1 | -40.44% | 0 | 38081

## 4th Qtr
Lake Havasu USD |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 135794 | 133238.21 | 2555.79 | 1.918% | 0 | 135794 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu - District Office | AZ | 66124 | 64372.62 | 1751.38 | 2.721% | 0 | 66124
AZ: Lake Havasu - HS Library | AZ | 29912 | 27348.82 | 2563.18 | 9.372% | 0 | 29912
AZ: Lake Havasu- Performing Arts | AZ | 39758 | 41516.77 | -1758.77 | -4.236% | 0 | 39758

## Jan
Lake Havasu USD |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 38644 | 38384.19 | 259.81 | 0.6769% | 0 | 38644 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 18583 | 18392.83 | 190.17 | 1.034% | 0 | 18583 | 0%
AZ: Lake Havasu - HS Library | AZ | 8688 | 7939.29 | 748.71 | 9.43% | 0 | 8688 | 0%
AZ: Lake Havasu- Performing Arts | AZ | 11373 | 12052.07 | -679.07 | -5.634% | 0 | 11373 | 0%

## Feb
Lake Havasu USD |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 40625 | 42480 | -1855 | -4.367% | 0 | 40625 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 17960 | 20518 | -2558 | -12.47% | 0 | 17960
AZ: Lake Havasu - HS Library | AZ | 9669 | 8722 | 947 | 10.86% | 0 | 9669
AZ: Lake Havasu- Performing Arts | AZ | 12996 | 13240 | -244 | -1.843% | 0 | 12996

## Mar
Lake Havasu USD |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 61154 | 51404 | 9750 | 18.97% | 0 | 61154 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 29969 | 13614 | 16355 | 120.1% | 0 | 29969
AZ: Lake Havasu - HS Library | AZ | 12747 | 18438 | -5691 | -30.87% | 0 | 12747
AZ: Lake Havasu- Performing Arts | AZ | 18438 | 19352 | -914 | -4.723% | 0 | 18438

## Apr
Lake Havasu USD |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 68122 | 72788.5 | -4666.5 | -6.411% | 0 | 68122 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 32166 | 34364.78 | -2198.78 | -6.398% | 0 | 32166
AZ: Lake Havasu - HS Library | AZ | 15724 | 15259.27 | 464.73 | 3.046% | 0 | 15724
AZ: Lake Havasu- Performing Arts | AZ | 20232 | 23164.45 | -2932.45 | -12.66% | 0 | 20232 |  | 1. Meter is reporting negative values 04/10 | 1. SR087003

## May
Lake Havasu USD |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 78445 | 78950.12 | -505.12 | -0.6398% | 0 | 78445 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 37903 | 37016.06 | 886.94 | 2.396% | 0 | 37903
AZ: Lake Havasu - HS Library | AZ | 16928 | 16653.19 | 274.81 | 1.65% | 0 | 16928
AZ: Lake Havasu- Performing Arts | AZ | 23614 | 25280.87 | -1666.87 | -6.593% | 0 | 23614 |  | 1. Meter is reporting negative values 04/10 | 1. SR087003

## Jun
Lake Havasu USD |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 69459 | 74486.42 | -5027.42 | -6.749% | 0 | 69459 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 36087 | 34792.54 | 1294.46 | 3.721% | 0 | 36087
AZ: Lake Havasu - HS Library | AZ | 15959 | 15763.81 | 195.19 | 1.238% | 0 | 15959
AZ: Lake Havasu- Performing Arts | AZ | 17413 | 23930.07 | -6517.07 | -27.23% | 0 | 17413 |  | 1. Meter is reporting negative values 04/10 | 1. SR087003

## Jul
Lake Havasu USD |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 49228 | 72341.81 | -23113.81 | -31.95% | 0 | 49228 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 34796 | 33888.19 | 907.81 | 2.679% | 0 | 34796 |  | 1. Weather station is shaded every morning from 07/15. | 1. SR087715, SR088955
AZ: Lake Havasu - HS Library | AZ | 15423 | 15271.26 | 151.74 | 0.9936% | 0 | 15423
AZ: Lake Havasu- Performing Arts | AZ | -991 | 23182.36 | -24173.36 | -104.3% | 0 | -991 |  | 1. Meter is reporting negative value from 07/25 | 1. SR087003

## Aug
Lake Havasu USD |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 67775 | 66969.89 | 805.11 | 1.202% | 0 | 67775 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 32797 | 31599.17 | 1197.83 | 3.791% | 0 | 32797 |  | 1. Meter A has an intermittent communications issue from 08/12. | 1. SR088955
AZ: Lake Havasu - HS Library | AZ | 14631 | 14046.96 | 584.04 | 4.158% | 0 | 14631
AZ: Lake Havasu- Performing Arts | AZ | 20347 | 21323.76 | -976.76 | -4.581% | 0 | 20347 |  | 1. Meter is reporting negative value from 07/25 | 1. SR087003

## Sep
Lake Havasu USD |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 62850 | 61365.79 | 1484.21 | 2.419% | 0 | 62850 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 30593 | 29143 | 1450 | 4.975% | 0 | 30593 |  | 1. Meter A has an intermittent communications issue from 08/12 and resolved on 09/04. | 1. SR088955
AZ: Lake Havasu - HS Library | AZ | 13532 | 12796.81 | 735.19 | 5.745% | 0 | 13532
AZ: Lake Havasu- Performing Arts | AZ | 18725 | 19425.98 | -700.98 | -3.608% | 0 | 18725 |  | 1. Meter is reporting accturate value from 07/25 | 1. SR087003

## Oct
Lake Havasu USD |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 54632 | 52486.19 | 2145.81 | 4.088% | 0 | 54632 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 26551 | 25434.15 | 1116.85 | 4.391% | 0 | 26551 |  | 1.Weather station is shaded every morning | 1.SR087715
AZ: Lake Havasu - HS Library | AZ | 11879 | 10743.15 | 1135.85 | 10.57% | 0 | 11879
AZ: Lake Havasu- Performing Arts | AZ | 16202 | 16308.89 | -106.89 | -0.6554% | 0 | 16202

## Nov
Lake Havasu USD |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 43335 | 42353.97 | 981.03 | 2.316% | 0 | 43335 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 21161 | 20545.83 | 615.17 | 2.994% | 0 | 21161 |  | 1.Weather station is shaded every morning | 1.SR087715
AZ: Lake Havasu - HS Library | AZ | 9581 | 8660.76 | 920.24 | 10.63% | 0 | 9581
AZ: Lake Havasu- Performing Arts | AZ | 12593 | 13147.38 | -554.38 | -4.217% | 0 | 12593

## Dec
Lake Havasu USD |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 37827 | 38398.05 | -571.05 | -1.487% | 0 | 37827 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu - District Office | AZ | 18412 | 18392.64 | 19.36 | 0.1053% | 0 | 18412 |  | 1.Weather station is shaded every morning | 1.SR087715
AZ: Lake Havasu - HS Library | AZ | 8452 | 7944.91 | 507.09 | 6.383% | 0 | 8452
AZ: Lake Havasu- Performing Arts | AZ | 10963 | 12060.5 | -1097.5 | -9.1% | 0 | 10963

## Sites
Portfolio: | Lake Havasu USD
Site DAS Name | Site | State | Update | DAS
AZ: Lake Havasu - District Office | AZ: Lake Havasu - District Office | AZ
AZ: Lake Havasu - HS Library | AZ: Lake Havasu - HS Library | AZ
AZ: Lake Havasu- Performing Arts | AZ: Lake Havasu- Performing Arts | AZ