## Year to Date
Marana USD |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 3777766 | 0 | 3777766 | 0% | 0 | 3777766 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Marana - Degrazia ES | AZ | 276245 | 0 | 276245 | 0% | 0 | 276245 | 0%
AZ: Marana - Gladden Farms Ph 2 | AZ | 298370 | 0 | 298370 | 0% | 0 | 298370 | 0%
AZ: Marana - Marana High School | AZ | 238993 | 0 | 238993 | 0% | 0 | 238993 | 0%
AZ: Marana - Mountain View HS Exp. | AZ | 1624141 | 0 | 1624141 | 0% | 0 | 1624141 | 0%
AZ: Marana - Rattlesnake Ridge ES | AZ | 157929 | 0 | 157929 | 0% | 0 | 157929 | 0%
AZ: Marana - Roadrunner ES | AZ | 135671 | 0 | 135671 | 0% | 0 | 135671 | 0%
AZ: Marana - Thornydale Elementary | AZ | 181098 | 0 | 181098 | 0% | 0 | 181098 | 0%
AZ: Marana - Tortolita MS | AZ | 482795 | 0 | 482795 | 0% | 0 | 482795 | 0%
AZ: Marana - Picture Rocks Intermediat | AZ | 382524 | 0 | 382524 | 0% | 0 | 382524 | 0%

## 1st Qtr
Marana USD |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 857250 | 0 | 857250 | 0% | 0 | 857250 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Marana - Degrazia ES | AZ | 54234 | 0 | 54234 | 0% | 0 | 54234 | 0%
AZ: Marana - Gladden Farms Ph 2 | AZ | 49713 | 0 | 49713 | 0% | 0 | 49713 | 0%
AZ: Marana - Marana High School | AZ | 92114 | 0 | 92114 | 0% | 0 | 92114 | 0%
AZ: Marana - Mountain View HS Exp. | AZ | 340237 | 0 | 340237 | 0% | 0 | 340237 | 0%
AZ: Marana - Rattlesnake Ridge ES | AZ | 42567 | 0 | 42567 | 0% | 0 | 42567 | 0%
AZ: Marana - Roadrunner ES | AZ | 50827 | 0 | 50827 | 0% | 0 | 50827 | 0%
AZ: Marana - Thornydale Elementary | AZ | 36998 | 0 | 36998 | 0% | 0 | 36998 | 0%
AZ: Marana - Tortolita MS | AZ | 104614 | 0 | 104614 | 0% | 0 | 104614 | 0%
AZ: Marana - Picture Rocks Intermediat | AZ | 85946 | 0 | 85946 | 0% | 0 | 85946 | 0%

## 2nd Qtr
Marana USD |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 1068298 | 0 | 1068298 | 0% | 0 | 1068298 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Marana - Degrazia ES | AZ | 92600 | 0 | 92600 |  |  | 92600
AZ: Marana - Gladden Farms Ph 2 | AZ | 99569 | 0 | 99569 |  |  | 99569
AZ: Marana - Marana High School | AZ | 8609 | 0 | 8609 |  |  | 8609
AZ: Marana - Mountain View HS Exp. | AZ | 485458 | 0 | 485458 |  |  | 485458
AZ: Marana - Rattlesnake Ridge ES | AZ | 56115 | 0 | 56115 |  |  | 56115
AZ: Marana - Roadrunner ES | AZ | 0 | 0 | 0 |  |  | 0
AZ: Marana - Thornydale Elementary | AZ | 64914 | 0 | 64914 |  |  | 64914
AZ: Marana - Tortolita MS | AZ | 140325 | 0 | 140325 |  |  | 140325
AZ: Marana - Picture Rocks Intermediat | AZ | 120708 | 0 | 120708 |  |  | 120708

## 3rd Qtr
Marana USD |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 870375 | 0 | 870375 | 0% | 0 | 870375 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Marana - Degrazia ES | AZ | 63950 | 0 | 63950 |  | 0 | 63950
AZ: Marana - Gladden Farms Ph 2 | AZ | 87265 | 0 | 87265 |  | 0 | 87265
AZ: Marana - Marana High School | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: Marana - Mountain View HS Exp. | AZ | 438518 | 0 | 438518 |  | 0 | 438518
AZ: Marana - Rattlesnake Ridge ES | AZ | 3659 | 0 | 3659 |  | 0 | 3659
AZ: Marana - Roadrunner ES | AZ | 10845 | 0 | 10845 |  | 0 | 10845
AZ: Marana - Thornydale Elementary | AZ | 39653 | 0 | 39653 |  | 0 | 39653
AZ: Marana - Tortolita MS | AZ | 132968 | 0 | 132968 |  | 0 | 132968
AZ: Marana - Picture Rocks Intermediat | AZ | 93517 | 0 | 93517 |  | 0 | 93517

## 4th Qtr
Marana USD |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 981843 | 0 | 981843 | 0% | 0 | 981843 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Marana - Degrazia ES | AZ | 65461 | 0 | 65461 |  | 0 | 65461
AZ: Marana - Gladden Farms Ph 2 | AZ | 61823 | 0 | 61823 |  | 0 | 61823
AZ: Marana - Marana High School | AZ | 138270 | 0 | 138270 |  | 0 | 138270
AZ: Marana - Mountain View HS Exp. | AZ | 359928 | 0 | 359928 |  | 0 | 359928
AZ: Marana - Rattlesnake Ridge ES | AZ | 55588 | 0 | 55588 |  | 0 | 55588
AZ: Marana - Roadrunner ES | AZ | 73999 | 0 | 73999 |  | 0 | 73999
AZ: Marana - Thornydale Elementary | AZ | 39533 | 0 | 39533 |  | 0 | 39533
AZ: Marana - Tortolita MS | AZ | 104888 | 0 | 104888 |  | 0 | 104888
AZ: Marana - Picture Rocks Intermediat | AZ | 82353 | 0 | 82353 |  | 0 | 82353

## Jan
Marana USD |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 240925 | 0 | 240925 | 0% | 0 | 240925 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 15252 | 0 | 15252 | 0% | 0 | 15252 | 0%
AZ: Marana - Gladden Farms Ph 2 | AZ | 12109 | 0 | 12109 | 0% | 0 | 12109 | 0% | 1. Inverter C2 was offline for whole month and the inverter RMA'd 2. Inverter A1 was offline for whole month | 1. SR077925 2. SR079708
AZ: Marana - Marana High School | AZ | 23382 | 0 | 23382 | 0% | 0 | 23382 | 0% | 1. Array A and C are running but not communicating, and Array B and G are offline due to Structure damage | 1. SR075233, SR075779
AZ: Marana - Mountain View HS Exp. | AZ | 100460 | 0 | 100460 | 0% | 0 | 100460 | 0%
AZ: Marana - Rattlesnake Ridge ES | AZ | 4897 | 0 | 4897 | 0% | 0 | 4897 | 0% | 1. Site was offline due to fire accident from May 2023 and back online on 01/18/2024 | 1. SR071245
AZ: Marana - Roadrunner ES | AZ | 21507 | 0 | 21507 | 0% | 0 | 21507 | 0% | 1. Inverter A2 was offline on 01/22 and 1/23 due to ground faults | 1. SR078885
AZ: Marana - Thornydale Elementary | AZ | 10517 | 0 | 10517 | 0% | 0 | 10517 | 0%
AZ: Marana - Tortolita MS | AZ | 28275 | 0 | 28275 | 0% | 0 | 28275 | 0% | 1. Inverter C2 was back online from 01/23 | 1. SRO75975
AZ: Marana - Picture Rocks Intermediat | AZ | 24526 | 0 | 24526 | 0% | 0 | 24526 | 0%

## Feb
Marana USD |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 264671 | 0 | 264671 | 0% | 0 | 264671 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 16822 | 0 | 16822 |  | 0 | 16822
AZ: Marana - Gladden Farms Ph 2 | AZ | 13631 | 0 | 13631 |  | 0 | 13631 |  | 1. Inverter C2 was offline for whole month 2. Inverter A1 was offline from 01/09 replaced on 02/28 | 1. SR077925 2. SR079708
AZ: Marana - Marana High School | AZ | 25498 | 0 | 25498 |  | 0 | 25498
AZ: Marana - Mountain View HS Exp. | AZ | 108379 | 0 | 108379 |  | 0 | 108379
AZ: Marana - Rattlesnake Ridge ES | AZ | 16195 | 0 | 16195 |  | 0 | 16195
AZ: Marana - Roadrunner ES | AZ | 13863 | 0 | 13863 |  | 0 | 13863
AZ: Marana - Thornydale Elementary | AZ | 9239 | 0 | 9239 |  | 0 | 9239 |  | 1.Inverter A3 tripped offline at 10:15 on 02/15 & back online at 02/20 at 15:00 | 1.SR081030
AZ: Marana - Tortolita MS | AZ | 34032 | 0 | 34032 |  | 0 | 34032
AZ: Marana - Picture Rocks Intermediat | AZ | 27012 | 0 | 27012 |  | 0 | 27012

## Mar
Marana USD |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 351654 | 0 | 351654 | 0% | 0 | 351654 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 22160 | 0 | 22160 |  | 0 | 22160
AZ: Marana - Gladden Farms Ph 2 | AZ | 23973 | 0 | 23973 |  | 0 | 23973 |  | 1. Inverter C2 was replaced on 03/19 | 1. SR077925
AZ: Marana - Marana High School | AZ | 43234 | 0 | 43234 |  | 0 | 43234 |  | 1. Inverter A5 replaced on 03/18 but not communicating in AP 2. Inverter C1 replaced on 03/12 but not communicating in AP 3. Inverter A2 replaced on 03/19 but not communicating in AP | 1. SR081612 2. SR081791 3. SR081996
AZ: Marana - Mountain View HS Exp. | AZ | 131398 | 0 | 131398 |  | 0 | 131398 |  | 1. Inverter A4 is tripped offline mid of the day from 03/04 almost through out the month | 1. SR082498
AZ: Marana - Rattlesnake Ridge ES | AZ | 21475 | 0 | 21475 |  | 0 | 21475
AZ: Marana - Roadrunner ES | AZ | 15457 | 0 | 15457 |  | 0 | 15457
AZ: Marana - Thornydale Elementary | AZ | 17242 | 0 | 17242 |  | 0 | 17242
AZ: Marana - Tortolita MS | AZ | 42307 | 0 | 42307 |  | 0 | 42307 |  | 1. Meter is capturing around 80% production of inverters | 1. SR082837
AZ: Marana - Picture Rocks Intermediat | AZ | 34408 | 0 | 34408 |  | 0 | 34408

## Apr
Marana USD |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 370051 | 0 | 370051 | 0% | 0 | 370051 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 28307 | 0 | 28307 |  | 0 | 28307
AZ: Marana - Gladden Farms Ph 2 | AZ | 33231 | 0 | 33231 |  | 0 | 33231
AZ: Marana - Marana High School | AZ | 8609 | 0 | 8609 |  | 0 | 8609 |  | 1. Site stopped communicating at 20:30 on 04/05 and is still not communicating. Data logger need to be replaced | 1. SR080878
AZ: Marana - Mountain View HS Exp. | AZ | 158739 | 0 | 158739 |  | 0 | 158739
AZ: Marana - Rattlesnake Ridge ES | AZ | 28996 | 0 | 28996 |  | 0 | 28996
AZ: Marana - Roadrunner ES | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Meter stopped communicating from 03/25 and is being RMA'd | 1. SR081189
AZ: Marana - Thornydale Elementary | AZ | 21773 | 0 | 21773 |  | 0 | 21773
AZ: Marana - Tortolita MS | AZ | 49894 | 0 | 49894 |  | 0 | 49894
AZ: Marana - Picture Rocks Intermediat | AZ | 40502 | 0 | 40502 |  | 0 | 40502

## May
Marana USD |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 385438 | 0 | 385438 | 0% | 0 | 385438 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 34811 | 0 | 34811 |  | 0 | 34811
AZ: Marana - Gladden Farms Ph 2 | AZ | 35553 | 0 | 35553 |  | 0 | 35553
AZ: Marana - Marana High School | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site stopped communicating at 20:30 on 04/05 throughout the month. Data logger need to be replaced | 1. SR080878
AZ: Marana - Mountain View HS Exp. | AZ | 175229 | 0 | 175229 |  | 0 | 175229
AZ: Marana - Rattlesnake Ridge ES | AZ | 27119 | 0 | 27119 |  | 0 | 27119 |  | 1. Site tripped offline at 07:00 on 05/26 due to arc event on B phase on PV utility meter and is still offline | 1. SR085173
AZ: Marana - Roadrunner ES | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Meter stopped communicating from 03/25 and is being RMA'd | 1. SR081189
AZ: Marana - Thornydale Elementary | AZ | 23247 | 0 | 23247 |  | 0 | 23247
AZ: Marana - Tortolita MS | AZ | 46390 | 0 | 46390 |  | 0 | 46390
AZ: Marana - Picture Rocks Intermediat | AZ | 43089 | 0 | 43089 |  | 0 | 43089

## Jun
Marana USD |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 312809 | 0 | 312809 | 0% | 0 | 312809 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 29482 | 0 | 29482 |  | 0 | 29482
AZ: Marana - Gladden Farms Ph 2 | AZ | 30785 | 0 | 30785 |  | 0 | 30785
AZ: Marana - Marana High School | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site stopped communicating at 20:30 on 04/05 and throughout the month. Data logger need to be replaced | 1. SR080878
AZ: Marana - Mountain View HS Exp. | AZ | 151490 | 0 | 151490 |  | 0 | 151490 |  | 1. Inverter A4 tripped offline on 06/11,06/13,06/14,06/15 and back online from 06/16 | 1. SR085956
AZ: Marana - Rattlesnake Ridge ES | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site is offline from 05/26 throughout the month due to arc event on B phase on PV utility meter. | 1. SR085173
AZ: Marana - Roadrunner ES | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Meter stopped communicating from 03/25 and is being RMA'd | 1. SR081189
AZ: Marana - Thornydale Elementary | AZ | 19894 | 0 | 19894 |  | 0 | 19894
AZ: Marana - Tortolita MS | AZ | 44041 | 0 | 44041 |  | 0 | 44041
AZ: Marana - Picture Rocks Intermediat | AZ | 37117 | 0 | 37117 |  | 0 | 37117

## Jul
Marana USD |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 315907 | 0 | 315907 | 0% | 0 | 315907 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 29307 | 0 | 29307 |  | 0 | 29307
AZ: Marana - Gladden Farms Ph 2 | AZ | 31498 | 0 | 31498 |  | 0 | 31498 |  | 1. Inverter C2 is offline from 07/04. | 1. SR087379
AZ: Marana - Marana High School | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site stopped communicating at 20:30 on 04/05 and throughout the month. Data logger need to be replaced | 1. SR080878
AZ: Marana - Mountain View HS Exp. | AZ | 148548 | 0 | 148548 |  | 0 | 148548 |  | 1. Inverter D1 tripped offline at 10:15AM on 07/05 being RMA'd. | 1. SR087401
AZ: Marana - Rattlesnake Ridge ES | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site is offline from 05/26 throughout the month due to arc event on B phase on PV utility meter. | 1. SR085173
AZ: Marana - Roadrunner ES | AZ | 218 | 0 | 218 |  | 0 | 218 |  | 1. Meter stopped communicating from 03/25 and is being RMA'd | 1. SR081189
AZ: Marana - Thornydale Elementary | AZ | 20929 | 0 | 20929 |  | 0 | 20929
AZ: Marana - Tortolita MS | AZ | 46916 | 0 | 46916 |  | 0 | 46916
AZ: Marana - Picture Rocks Intermediat | AZ | 38491 | 0 | 38491 |  | 0 | 38491

## Aug
Marana USD |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 260147 | 0 | 260147 | 0% | 0 | 260147 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 21754 | 0 | 21754 |  | 0 | 21754
AZ: Marana - Gladden Farms Ph 2 | AZ | 27759 | 0 | 27759 |  | 0 | 27759 |  | 1. Inverter C2 is offline from 07/04 being RMA'd. | 1. SR087379
AZ: Marana - Marana High School | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Inverters G1 & G2 RMAd from 08/13. | 1. SR088993
AZ: Marana - Mountain View HS Exp. | AZ | 142121 | 0 | 142121 |  | 0 | 142121 |  | 1. Inverter D1 tripped offline on 07/05 and back online on 08/09. 2. Some modules are damaged and needs to be replaced. 3. Inverter A4 tripped offline at 01:15PM on 08/24 and back online on 08/28. | 1. SR087401 2. SR088847 3. SR089499
AZ: Marana - Rattlesnake Ridge ES | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site is offline from 05/26 throughout the month due to arc event on B phase on PV utility meter. | 1. SR085173
AZ: Marana - Roadrunner ES | AZ | 330 | 0 | 330 |  | 0 | 330 |  | 1. Inverter 3 tripped offline at 5:30-5:45am on 08/01/2024 2.Meter stopped communicating from 03/25 and later replaced on 08/13 | 1.SR088498 2.SR081189
AZ: Marana - Thornydale Elementary | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: Marana - Tortolita MS | AZ | 42590 | 0 | 42590 |  | 0 | 42590
AZ: Marana - Picture Rocks Intermediat | AZ | 25593 | 0 | 25593 |  | 0 | 25593 |  | 1. Meter 2 is not communicating from 08/01 | 1. SR088507

## Sep
Marana USD |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 294321 | 0 | 294321 | 0% | 0 | 294321 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 12889 | 0 | 12889 |  | 0 | 12889
AZ: Marana - Gladden Farms Ph 2 | AZ | 28008 | 0 | 28008 |  | 0 | 28008 |  | 1. Inverter C2 experienced frequent trip events from 07/04. Inverter was replaced on 09/10. 2. Inverters B1 and C1 is underperforming approximately 5kW compared to its peers from 09/06 and issue resolved on 09/10. | 1. SR087379 2. SR090068
AZ: Marana - Marana High School | AZ | 0 | 0 | 0 |  | 0 | 0 |  | 1. Inverter G3 is offline from 09/17 and back online on 09/18. 2. Inverter D1 tripped offline at 17:15 on 9/12/24 and was kept offline through the month. | 1. SR090657 2. SR093461
AZ: Marana - Mountain View HS Exp. | AZ | 147849 | 0 | 147849 |  | 0 | 147849
AZ: Marana - Rattlesnake Ridge ES | AZ | 3659 | 0 | 3659 |  | 0 | 3659
AZ: Marana - Roadrunner ES | AZ | 10297 | 0 | 10297 |  | 0 | 10297 |  | 1. Meter is showing negative readings from 09/12 and meter is back to normal reading from 09/18. | 1. SR090317
AZ: Marana - Thornydale Elementary | AZ | 18724 | 0 | 18724 |  | 0 | 18724
AZ: Marana - Tortolita MS | AZ | 43462 | 0 | 43462 |  | 0 | 43462
AZ: Marana - Picture Rocks Intermediat | AZ | 29433 | 0 | 29433 |  | 0 | 29433 |  | 1. Meter 2 is not communicating from 08/01. Meter 2 was replaced and communication issue resolved from 09/18. | 1. SR088507

## Oct
Marana USD |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 376284 | 0 | 376284 | 0% | 0 | 376284 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 31473 | 0 | 31473 |  | 0 | 31473
AZ: Marana - Gladden Farms Ph 2 | AZ | 24805 | 0 | 24805 |  | 0 | 24805
AZ: Marana - Marana High School | AZ | 41584 | 0 | 41584 |  | 0 | 41584 |  | 1. Inverter D1 kept offline from 09/13. 2. Inverters A to C was offline through the month. | 1. SR093461 2. SR090066
AZ: Marana - Mountain View HS Exp. | AZ | 138213 | 0 | 138213 |  | 0 | 138213 |  | 1. Inverter A1 underperforming by 4 kW from 09/17/24. | 1. SR095235
AZ: Marana - Rattlesnake Ridge ES | AZ | 25854 | 0 | 25854 |  | 0 | 25854 |  | 1. Inverter A2 was underperforming approximately 4kW compared to its peers from 10/28/2024. | 1. SR094916
AZ: Marana - Roadrunner ES | AZ | 26458 | 0 | 26458 |  | 0 | 26458 |  | 1. Meter has been reporting data conswastently with the inverters since 12:30 PM on 10/10. | 1. SR091906
AZ: Marana - Thornydale Elementary | AZ | 16238 | 0 | 16238 |  | 0 | 16238
AZ: Marana - Tortolita MS | AZ | 40063 | 0 | 40063 |  | 0 | 40063
AZ: Marana - Picture Rocks Intermediat | AZ | 31596 | 0 | 31596 |  | 0 | 31596 |  | 1. Inverter A1 underperforming by 9 kW from 9/4/24. | 1. SR095044

## Nov
Marana USD |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 292788 | 0 | 292788 | 0% | 0 | 292788 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 16989 | 0 | 16989 |  | 0 | 16989
AZ: Marana - Gladden Farms Ph 2 | AZ | 18763 | 0 | 18763 |  | 0 | 18763 |  | 1. Site tripped offline at 13:45 on 11/27/2024 and back online at 16:00 on 11/29. | 1. SR093696
AZ: Marana - Marana High School | AZ | 33718 | 0 | 33718 |  | 0 | 33718 |  | 1. Inverter D1 kept offline from 09/13. 2. Inverters A to C was offline through the month. | 1. SR093461 2. SR090066, SR093461
AZ: Marana - Mountain View HS Exp. | AZ | 112148 | 0 | 112148 |  | 0 | 112148 |  | 1. Inverter A1 underperforming by 4 kW from 09/17/24. | 1. SR095235
AZ: Marana - Rattlesnake Ridge ES | AZ | 15738 | 0 | 15738 |  | 0 | 15738 |  | 1. Inverter A2 was underperforming approximately 4kW compared to its peers from 10/28/2024. | 1. SR094916
AZ: Marana - Roadrunner ES | AZ | 24317 | 0 | 24317 |  | 0 | 24317 |  |  | 1. SR091906
AZ: Marana - Thornydale Elementary | AZ | 12306 | 0 | 12306 |  | 0 | 12306
AZ: Marana - Tortolita MS | AZ | 33006 | 0 | 33006 |  | 0 | 33006
AZ: Marana - Picture Rocks Intermediat | AZ | 25803 | 0 | 25803 |  | 0 | 25803 |  | 1. Inverter A1 underperforming by 9 kW from 9/4/24. | 1. SR095044

## Dec
Marana USD |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 312771 | 0 | 312771 | 0% | 0 | 312771 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Marana - Degrazia ES | AZ | 16999 | 0 | 16999 |  | 0 | 16999
AZ: Marana - Gladden Farms Ph 2 | AZ | 18255 | 0 | 18255 |  | 0 | 18255
AZ: Marana - Marana High School | AZ | 62968 | 0 | 62968 |  | 0 | 62968 |  | 1. Inverters A to C were back online at 14:30 on 12/09, except for Inverter A4, C3, C7, & C8. 2. Inverter C3 was back online on 12/10/2024, went offline again on 12/12, and was back online on 12/13. It went offline again on 12/18 and was back online on 12/19. It went offline again on 12/27 and was back online on 12/28. It tripped offline at 9:00 AM on 12/31. 3. Inverters C1, C7, C8 are back online at 10:45am on 12/20 and inverter A4 back online at 8:00AM on 12/21. 4. Inverter D1 kept offline from 09/13. | 1. SR090066, SR093461 2. SR094543 3. SR094821 4. SR093461
AZ: Marana - Mountain View HS Exp. | AZ | 109567 | 0 | 109567 |  | 0 | 109567 |  | 1. Inverter A1 underperforming by 4 kW from 09/17/24. | 1. SR095235
AZ: Marana - Rattlesnake Ridge ES | AZ | 13996 | 0 | 13996 |  | 0 | 13996 |  | 1. Inverter A3 has been offline since 1:30 PM on 12/22/2024. 2. Inverter A2 was producing equally with its peers since 12/20. | 1. SR095024 2. SR094916
AZ: Marana - Roadrunner ES | AZ | 23224 | 0 | 23224 |  | 0 | 23224
AZ: Marana - Thornydale Elementary | AZ | 10989 | 0 | 10989 |  | 0 | 10989
AZ: Marana - Tortolita MS | AZ | 31819 | 0 | 31819 |  | 0 | 31819
AZ: Marana - Picture Rocks Intermediat | AZ | 24954 | 0 | 24954 |  | 0 | 24954 |  | 1. Inverter A1 was producing equally with its peers since 12/31. | 1. SR095044

## Sites
Portfolio: | Marana USD
Site DAS Name | State | Update | DAS
AZ: Marana - Degrazia ES | AZ
AZ: Marana - Gladden Farms Ph 2 | AZ
AZ: Marana - Marana High School | AZ
AZ: Marana - Mountain View HS Exp. | AZ
AZ: Marana - Rattlesnake Ridge ES | AZ
AZ: Marana - Roadrunner ES | AZ
AZ: Marana - Thornydale Elementary | AZ
AZ: Marana - Tortolita MS | AZ
AZ: Marana - Picture Rocks Intermediat | AZ