## Year to Date
Yankee Sprinkler |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 197896.689 | 0 | 197896.689 | 0% | 216591.348 | -18694.659 | -8.631%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Yankee Phase 1 | MA | 183997.889 | 0 | 183997.889 |  | 216591.348 | -32593.459 | -15.05%
Yankee Phase 2 | MA | 13898.8 | 0 | 13898.8 |  | 0 | 13898.8

## 1st Qtr
Yankee Sprinkler |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 41603.64 | 0 | 41603.64 | 0% | 40231.33 | 1372.31 | 3.411%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Yankee Phase 1 | MA | 27704.84 | 0 | 27704.84 |  | 40231.33 | -12526.49 | -31.14%
Yankee Phase 2 | MA | 13898.8 | 0 | 13898.8 |  | 0 | 13898.8

## 2nd Qtr
Yankee Sprinkler |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 102361.964 | 0 | 102361.964 | 0% | 74436.05 | 27925.914 | 37.52%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Yankee Phase 1 | MA | 68696.414 | 0 | 68696.414 |  | 74436.05 | -5739.636 | -7.711%
Yankee Phase 2 | MA | 33665.55 | 0 | 33665.55 |  | 0 | 33665.55

## 3rd Qtr
Yankee Sprinkler |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 91821.2814 | 0 | 91821.2814 | 0% | 71165.92 | 20655.3614 | 29.02%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Yankee Phase 1 | MA | 61384.8952 | 0 | 61384.8952 |  | 71165.92 | -9781.0248 | -13.74%
Yankee Phase 2 | MA | 30436.3862 | 0 | 30436.3862 |  | 0 | 30436.3862

## 4th Qtr
Yankee Sprinkler |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 40355.9349 | 0 | 40355.9349 | 0% | 30758.048 | 9597.8869 | 31.2%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Yankee Phase 1 | MA | 26211.7399 | 0 | 26211.7399 |  | 30758.048 | -4546.3081 | -14.78%
Yankee Phase 2 | MA | 14144.195 | 0 | 14144.195 |  | 0 | 14144.195

## Jan
Yankee Sprinkler |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 5686.9 | 0 | 5686.9 | 0% | 9297.53 | -3610.63 | -38.83%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 3764 | 0 | 3764 |  | 9297.53 | -5533.53 | -59.52%
Yankee Phase 2 | MA | 1922.9 | 0 | 1922.9 |  | 0 | 1922.9

## Feb
Yankee Sprinkler |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 12645.24 | 0 | 12645.24 | 0% | 12570 | 75.24 | 0.5986%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 8538.14 | 0 | 8538.14 |  | 12570 | -4031.86 | -32.08%
Yankee Phase 2 | MA | 4107.1 | 0 | 4107.1 |  | 0 | 4107.1 |  | 1. Inverter 2 tripped offline on 02/03 at 16:00 & back online on 02/06 at 14:25. | 1. SR080701

## Mar
Yankee Sprinkler |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 23271.5 | 0 | 23271.5 | 0% | 18363.8 | 4907.7 | 26.72%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 15402.7 | 0 | 15402.7 |  | 18363.8 | -2961.1 | -16.12%
Yankee Phase 2 | MA | 7868.8 | 0 | 7868.8 |  | 0 | 7868.8

## Apr
Yankee Sprinkler |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 30220.784 | 0 | 30220.784 | 0% | 21548.33 | 8672.454 | 40.25%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 20103.084 | 0 | 20103.084 |  | 21548.33 | -1445.246 | -6.707%
Yankee Phase 2 | MA | 10117.7 | 0 | 10117.7 |  | 0 | 10117.7

## May
Yankee Sprinkler |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 33683.7 | 0 | 33683.7 | 0% | 26153.75 | 7529.95 | 28.79%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 22663.12 | 0 | 22663.12 |  | 26153.75 | -3490.63 | -13.35% | 1. Site was offline due to utility outage from 05:15 to 10:15 AM on 05/28 but inverter 5 and 3 were not back online when site came back online. Inverter 5 was back online at 14:45 on 05/28 and inverter 3 was back online on next day | 1. SR085207
Yankee Phase 2 | MA | 11020.58 | 0 | 11020.58 |  | 0 | 11020.58 |  | 1. Site was offline on 05/28 due to utility outage and later came back online on 05/29. 2. Inverter 2 tripped offline at 16:45 on 05/22 and back online at 11:45 on 05/23 | 1. SR085206 2. SR085049

## Jun
Yankee Sprinkler |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 38457.48 | 0 | 38457.48 | 0% | 26733.97 | 11723.51 | 43.85%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 25930.21 | 0 | 25930.21 |  | 26733.97 | -803.76 | -3.007%
Yankee Phase 2 | MA | 12527.27 | 0 | 12527.27 |  | 0 | 12527.27

## Jul
Yankee Sprinkler |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 34774.7162 | 0 | 34774.7162 | 0% | 27442.12 | 7332.5962 | 26.72%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 23380.83 | 0 | 23380.83 |  | 27442.12 | -4061.29 | -14.8%
Yankee Phase 2 | MA | 11393.8862 | 0 | 11393.8862 |  | 0 | 11393.8862

## Aug
Yankee Sprinkler |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 32180.4103 | 0 | 32180.4103 | 0% | 24783.15 | 7397.2603 | 29.85%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 21486.0652 | 0 | 21486.0652 |  | 24783.15 | -3297.0848 | -13.3%
Yankee Phase 2 | MA | 10694.345 | 0 | 10694.345 |  | 0 | 10694.345

## Sep
Yankee Sprinkler |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 24866.1549 | 0 | 24866.1549 | 0% | 18940.65 | 5925.5049 | 31.28%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 16518 | 0 | 16518 |  | 18940.65 | -2422.65 | -12.79%
Yankee Phase 2 | MA | 8348.155 | 0 | 8348.155 |  | 0 | 8348.155

## Oct
Yankee Sprinkler |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 20626.0399 | 0 | 20626.0399 | 0% | 14719.57 | 5906.4699 | 40.13%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 13662.2749 | 0 | 13662.2749 |  | 14719.57 | -1057.2951 | -7.183%
Yankee Phase 2 | MA | 6963.765 | 0 | 6963.765 |  | 0 | 6963.765 |  | 1. Inverter 1 is performing low compared to peers due to several optimizers underperformance. | 1.SR092525

## Nov
Yankee Sprinkler |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 12043.1601 | 0 | 12043.1601 | 0% | 8622.888 | 3420.2721 | 39.67%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 7733.8601 | 0 | 7733.8601 |  | 8622.888 | -889.0279 | -10.31% | 1. Site tripped offline at 06:15 AM to 13:30 on 11/10 2. Site tripped offline at 06:45AM to 09:15AM on 11/28 | 1.SR093121 2. SR093700
Yankee Phase 2 | MA | 4309.3 | 0 | 4309.3 |  | 0 | 4309.3 |  | 1. Site tripped offline at 06:00 AM on 11/10 and back online at 07:00 on 11/11 2. Site tripped offline at 06:45AM on 11/28 and back online on 11/29 | 1. SR093120 2. SR093701

## Dec
Yankee Sprinkler |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 7686.7349 | 0 | 7686.7349 | 0% | 7415.59 | 271.1449 | 3.656%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Yankee Phase 1 | MA | 4815.6048 | 0 | 4815.6048 |  | 7415.59 | -2599.9852 | -35.06%
Yankee Phase 2 | MA | 2871.13 | 0 | 2871.13 |  | 0 | 2871.13

## Sites
Portfolio: | Yankee Sprinkler
Site DAS Name | Site | State | Update | DAS
Yankee Sprinkler Phase 1 | Yankee Phase 1 | MA |  | PowerTrack
Yankee Sprinkler Phase 2 | Yankee Phase 2 | MA |  | PowerTrack