## Year to Date
38 DN |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 3977782.25 | 5658062.23 | -1680279.98 | -29.7% | 5241855.09 | -1264072.84 | -24.11%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 242503 | 207367.6 | 35135.4 | 16.94% | 293749.1 | -51246.1 | -17.45%
Barton Acres | MA | 140015 | 244885.34 | -104870.34 | -42.82% | 167633.43 | -27618.43 | -16.48%
Bowden | MA | 309315 | 398903.9 | -89588.9 | -22.46% | 384551.2 | -75236.2 | -19.56%
Blair Wire Village | MA | 150889 | 264179.88 | -113290.88 | -42.88% | 191298.34 | -40409.34 | -21.12%
Boutilier | MA | 418029 | 507903.5 | -89874.5 | -17.7% | 460177 | -42148 | -9.159%
Cherry Valley | MA | 138012 | 257641.22 | -119629.22 | -46.43% | 181710 | -43698 | -24.05%
Cohasse | MA | 143621 | 240526.14 | -96905.14 | -40.29% | 249939.1 | -106318.1 | -42.54%
ISM Dighton Solar 2 | MA | 369601 | 446240.7 | -76639.7 | -17.17% | 422669.7 | -53068.7 | -12.56%
Dudley River 1 | MA | 162350 | 207552.9 | -45202.9 | -21.78% | 193665.63 | -31315.63 | -16.17%
Dudley River 2 | MA | 158989 | 208432.07 | -49443.07 | -23.72% | 186479.73 | -27490.73 | -14.74%
Dudley River 3 | MA | 175322 | 210823.73 | -35501.73 | -16.84% | 190163.09 | -14841.09 | -7.804%
Flint Pond | MA | 69387.5 | 115721.3 | -46333.8 | -40.04% | 81017.44 | -11629.94 | -14.35%
Incom | MA | 328359 | 487074.4 | -158715.4 | -32.59% | 483929.1 | -155570.1 | -32.15%
JH | MA | 149558 | 247035.23 | -97477.23 | -39.46% | 235771.4 | -86213.4 | -36.57%
Ledeaux | MA | 136227 | 185824.07 | -49597.07 | -26.69% | 220465.19 | -84238.19 | -38.21%
Palombo A | MA | 322527 | 507436.2 | -184909.2 | -36.44% | 542314 | -219787 | -40.53%
Palombo B | MA | 144816 | 243020.55 | -98204.55 | -40.41% | 173675.39 | -28859.39 | -16.62%
St Josephs Church | MA | 139586 | 249741.42 | -110155.42 | -44.11% | 207488.72 | -67902.72 | -32.73%
Sunset A | MA | 71562.5 | 122829.32 | -51266.82 | -41.74% | 78920.08 | -7357.58 | -9.323%
Sunset B | MA | 63980.25 | 92401.08 | -28420.83 | -30.76% | 77977.35 | -13997.1 | -17.95%
Woodchuck | MA | 143133 | 212521.68 | -69388.68 | -32.65% | 218260.1 | -75127.1 | -34.42%

## 1st Qtr
38 DN |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 3977782.25 | 5658062.23 | -1680279.98 | -29.7% | 5241855.09 | -1264072.84 | -24.11%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 242503 | 207367.6 | 35135.4 | 16.94% | 293749.1 | -51246.1 | -17.45%
Barton Acres | MA | 140015 | 244885.34 | -104870.34 | -42.82% | 167633.43 | -27618.43 | -16.48%
Bowden | MA | 309315 | 398903.9 | -89588.9 | -22.46% | 384551.2 | -75236.2 | -19.56%
Blair Wire Village | MA | 150889 | 264179.88 | -113290.88 | -42.88% | 191298.34 | -40409.34 | -21.12%
Boutilier | MA | 418029 | 507903.5 | -89874.5 | -17.7% | 460177 | -42148 | -9.159%
Cherry Valley | MA | 138012 | 257641.22 | -119629.22 | -46.43% | 181710 | -43698 | -24.05%
Cohasse | MA | 143621 | 240526.14 | -96905.14 | -40.29% | 249939.1 | -106318.1 | -42.54%
ISM Dighton Solar 2 | MA | 369601 | 446240.7 | -76639.7 | -17.17% | 422669.7 | -53068.7 | -12.56%
Dudley River 1 | MA | 162350 | 207552.9 | -45202.9 | -21.78% | 193665.63 | -31315.63 | -16.17%
Dudley River 2 | MA | 158989 | 208432.07 | -49443.07 | -23.72% | 186479.73 | -27490.73 | -14.74%
Dudley River 3 | MA | 175322 | 210823.73 | -35501.73 | -16.84% | 190163.09 | -14841.09 | -7.804%
Flint Pond | MA | 69387.5 | 115721.3 | -46333.8 | -40.04% | 81017.44 | -11629.94 | -14.35%
Incom | MA | 328359 | 487074.4 | -158715.4 | -32.59% | 483929.1 | -155570.1 | -32.15%
JH | MA | 149558 | 247035.23 | -97477.23 | -39.46% | 235771.4 | -86213.4 | -36.57%
Ledeaux | MA | 136227 | 185824.07 | -49597.07 | -26.69% | 220465.19 | -84238.19 | -38.21%
Palombo A | MA | 322527 | 507436.2 | -184909.2 | -36.44% | 542314 | -219787 | -40.53%
Palombo B | MA | 144816 | 243020.55 | -98204.55 | -40.41% | 173675.39 | -28859.39 | -16.62%
St Josephs Church | MA | 139586 | 249741.42 | -110155.42 | -44.11% | 207488.72 | -67902.72 | -32.73%
Sunset A | MA | 71562.5 | 122829.32 | -51266.82 | -41.74% | 78920.08 | -7357.58 | -9.323%
Sunset B | MA | 63980.25 | 92401.08 | -28420.83 | -30.76% | 77977.35 | -13997.1 | -17.95%
Woodchuck | MA | 143133 | 212521.68 | -69388.68 | -32.65% | 218260.1 | -75127.1 | -34.42%

## 2nd Qtr
38 DN |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 0 | 0 | 0 |  |  | 0
Barton Acres | MA | 0 | 0 | 0 |  |  | 0
Bowden | MA | 0 | 0 | 0 |  |  | 0
Blair Wire Village | MA | 0 | 0 | 0 |  |  | 0
Boutilier | MA | 0 | 0 | 0 |  |  | 0
Cherry Valley | MA | 0 | 0 | 0 |  |  | 0
Cohasse | MA | 0 | 0 | 0 |  |  | 0
ISM Dighton Solar 2 | MA | 0 | 0 | 0 |  |  | 0
Dudley River 1 | MA | 0 | 0 | 0 |  |  | 0
Dudley River 2 | MA | 0 | 0 | 0 |  |  | 0
Dudley River 3 | MA | 0 | 0 | 0 |  |  | 0
Flint Pond | MA | 0 | 0 | 0 |  |  | 0
Incom | MA | 0 | 0 | 0 |  |  | 0
JH | MA | 0 | 0 | 0 |  |  | 0
Ledeaux | MA | 0 | 0 | 0 |  |  | 0
Palombo A | MA | 0 | 0 | 0 |  |  | 0
Palombo B | MA | 0 | 0 | 0 |  |  | 0
St Josephs Church | MA | 0 | 0 | 0 |  |  | 0
Sunset A | MA | 0 | 0 | 0 |  |  | 0
Sunset B | MA | 0 | 0 | 0 |  |  | 0
Woodchuck | MA | 0 | 0 | 0 |  |  | 0

## 3rd Qtr
38 DN |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 0 | 0 | 0 |  |  | 0
Barton Acres | MA | 0 | 0 | 0 |  |  | 0
Bowden | MA | 0 | 0 | 0 |  |  | 0
Blair Wire Village | MA | 0 | 0 | 0 |  |  | 0
Boutilier | MA | 0 | 0 | 0 |  |  | 0
Cherry Valley | MA | 0 | 0 | 0 |  |  | 0
Cohasse | MA | 0 | 0 | 0 |  |  | 0
ISM Dighton Solar 2 | MA | 0 | 0 | 0 |  |  | 0
Dudley River 1 | MA | 0 | 0 | 0 |  |  | 0
Dudley River 2 | MA | 0 | 0 | 0 |  |  | 0
Dudley River 3 | MA | 0 | 0 | 0 |  |  | 0
Flint Pond | MA | 0 | 0 | 0 |  |  | 0
Incom | MA | 0 | 0 | 0 |  |  | 0
JH | MA | 0 | 0 | 0 |  |  | 0
Ledeaux | MA | 0 | 0 | 0 |  |  | 0
Palombo A | MA | 0 | 0 | 0 |  |  | 0
Palombo B | MA | 0 | 0 | 0 |  |  | 0
St Josephs Church | MA | 0 | 0 | 0 |  |  | 0
Sunset A | MA | 0 | 0 | 0 |  |  | 0
Sunset B | MA | 0 | 0 | 0 |  |  | 0
Woodchuck | MA | 0 | 0 | 0 |  |  | 0

## 4th Qtr
38 DN |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 0 | 0 | 0 |  |  | 0
Barton Acres | MA | 0 | 0 | 0 |  |  | 0
Bowden | MA | 0 | 0 | 0 |  |  | 0
Blair Wire Village | MA | 0 | 0 | 0 |  |  | 0
Boutilier | MA | 0 | 0 | 0 |  |  | 0
Cherry Valley | MA | 0 | 0 | 0 |  |  | 0
Cohasse | MA | 0 | 0 | 0 |  |  | 0
ISM Dighton Solar 2 | MA | 0 | 0 | 0 |  |  | 0
Dudley River 1 | MA | 0 | 0 | 0 |  |  | 0
Dudley River 2 | MA | 0 | 0 | 0 |  |  | 0
Dudley River 3 | MA | 0 | 0 | 0 |  |  | 0
Flint Pond | MA | 0 | 0 | 0 |  |  | 0
Incom | MA | 0 | 0 | 0 |  |  | 0
JH | MA | 0 | 0 | 0 |  |  | 0
Ledeaux | MA | 0 | 0 | 0 |  |  | 0
Palombo A | MA | 0 | 0 | 0 |  |  | 0
Palombo B | MA | 0 | 0 | 0 |  |  | 0
St Josephs Church | MA | 0 | 0 | 0 |  |  | 0
Sunset A | MA | 0 | 0 | 0 |  |  | 0
Sunset B | MA | 0 | 0 | 0 |  |  | 0
Woodchuck | MA | 0 | 0 | 0 |  |  | 0

## Jan
38 DN |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 1074735.7533 | 1953737.18 | -879001.4267 | -44.99% | 2327559.48 | -1252823.7267 | -53.83%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA | 124703.5 | 103355.9 | 21347.6 | 20.65% | 146126.1 | -21422.6 | -14.66% | 1. Inverter 28 was offline from 12/14 and back online on 01/25 | 1. SR079280
Barton Acres | MA | 31509 | 84215.44 | -52706.44 | -62.59% | 69453.12 | -37944.12 | -54.63%
Bowden | MA | 69313 | 124922.7 | -55609.7 | -44.52% | 167677.4 | -98364.4 | -58.66%
Blair Wire Village | MA | 38474 | 97645.68 | -59171.68 | -60.6% | 83112.14 | -44638.14 | -53.71% | 1. Relay tripped and site is experiencing an outage on 01/07 at 09:47 and reclosed at 18:30 | 1. SR079999
Boutilier | MA | 104475 | 117645.2 | -13170.2 | -11.19% | 190658.8 | -86183.8 | -45.2%
Cherry Valley | MA | 33861 | 93717.02 | -59856.02 | -63.87% | 77483 | -43622 | -56.3% | 1. Inverter B stopped communicating at 08:15 on 01/23 and technican reset the inverter at 12:00 2. Inverter B stopped communicating on 01/28 at 111:15 and and technician reset the inverter at 12:00. on 01/29 3. Site tripped offline at 10:45 on 01/07 and back online 23:15 same day. | 1. SR080405 2. SR080529 3. SR080002
Cohasse | MA | 37057 | 86836.54 | -49779.54 | -57.33% | 114180.6 | -77123.6 | -67.55% | 1. site tripped offline at 21:00 on 01/09 and back online at 8:30 on 01/10. | 1. SR080109
ISM Dighton Solar 2 | MA | 123864 | 178054.9 | -54190.9 | -30.43% | 195853.9 | -71989.9 | -36.76% | 1. SEL Relay 2 tripped offline at 23:00 on 01/30 and reclosed at 10:45 on 01/31 2. Planned outage on 01/25 at 9:00 and site reclosed at 17:00 on same day. | 1. SR080611 2. SR080054
Dudley River 1 | MA | 43519 | 68762.9 | -25243.9 | -36.71% | 83762.23 | -40243.23 | -48.04%
Dudley River 2 | MA | 44123 | 70139.57 | -26016.57 | -37.09% | 81919.43 | -37796.43 | -46.14%
Dudley River 3 | MA | 47297 | 71573.83 | -24276.83 | -33.92% | 84149.19 | -36852.19 | -43.79%
Flint Pond | MA | 16497.5 | 40276 | -23778.5 | -59.04% | 33543.68 | -17046.18 | -50.82% | 1. site offline on 01/07 at 05:00 and resolved at 07:15 | 1. SR079998
Incom | MA | 83086 | 159872.4 | -76786.4 | -48.03% | 220156.9 | -137070.9 | -62.26% | 1. Site was offline on 01/25 at 04:45 and reclosed at 16:00 | 1. SR080455
JH | MA | 32274 | 86355.93 | -54081.93 | -62.63% | 106218.7 | -73944.7 | -69.62%
Ledeaux | MA | 28537 | 58671.27 | -30134.27 | -51.36% | 98769.99 | -70232.99 | -71.11%
Palombo A | MA | 79689.0033 | 187942.8 | -108253.7967 | -57.6% | 250093 | -170403.9967 | -68.14%
Palombo B | MA | 32703 | 91961.55 | -59258.55 | -64.44% | 71768.39 | -39065.39 | -54.43%
St Josephs Church | MA | 37183 | 87772.32 | -50589.32 | -57.64% | 91531.02 | -54348.02 | -59.38%
Sunset A | MA | 16708.5 | 42789.35 | -26080.85 | -60.95% | 32696.87 | -15988.37 | -48.9% | 1. Relay tripped at 3:50 Am on 01/30 and auto reclosed in minutes | 1. SR080186
Sunset B | MA | 16074.25 | 29669.2 | -13594.95 | -45.82% | 32307.32 | -16233.07 | -50.25% | 1. Relay tripped at 3:50 Am on 01/30 and auto reclosed in minutes | 1. SR080187
Woodchuck | MA | 33788 | 71556.68 | -37768.68 | -52.78% | 96097.7 | -62309.7 | -64.84%

## Feb
38 DN |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 2903046.4967 | 3704325.05 | -801278.5533 | -21.63% | 2914295.61 | -11249.1133 | -0.386%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA | 117799.5 | 104011.7 | 13787.8 | 13.26% | 147623 | -29823.5 | -20.2% | 1. Inverter 25 tripped offline on 02/04/2024 at 13:30 & continued through out the month. 2. Inverter 9 & 29 starts late for the production throught the month. | 1. SR080716
Barton Acres | MA | 108506 | 160669.9 | -52163.9 | -32.47% | 98180.31 | 10325.69 | 10.52% | 1. Inverter 2 Combiner box 5 tripped offline on 02/16/2024 at 12:00 & back online on 02/17/2024 at 13:45. | 1.SR081069
Bowden | MA | 240002 | 273981.2 | -33979.2 | -12.4% | 216873.8 | 23128.2 | 10.66%
Blair Wire Village | MA | 112415 | 166534.2 | -54119.2 | -32.5% | 108186.2 | 4228.8 | 3.909% | 1. SIte tripped offline on 02/21/2024 at 03:15 & back online at 08:40AM 2. Site tripped offline on 02/28/2024 at 11:15 & back online at 13:15 3.Site tripped offline on 02/29/2024 at 12:30 & back online at 15:00 | 1.SR081148 2.SR081408 3.SR081459
Boutilier | MA | 313554 | 390258.3 | -76704.3 | -19.65% | 269518.2 | 44035.8 | 16.34%
Cherry Valley | MA | 104151 | 163924.2 | -59773.2 | -36.46% | 104227 | -76 | -0.07292% | 1. Inverter 2 has intermittent trips on 02/16, 02/17,02/18, 02/19, 02/20 ,back online at 12:20 on 02/20/2024. 2. Inverter 2 tripped offline on 02/06/2024 at 10:40 & back online at 12:05. | 1.SR081049 2.SR080405
Cohasse | MA | 106564 | 153689.6 | -47125.6 | -30.66% | 135758.5 | -29194.5 | -21.5%
ISM Dighton Solar 2 | MA | 245737 | 268185.8 | -22448.8 | -8.371% | 226815.8 | 18921.2 | 8.342% | 1. Site was taken offline on 02/27/2024 from 08:45 to 11:15 for maintenance & 2 back online at 14:00 PM. 2. Inverter 2 is offline from 11:30 to 16:30 on 02/26/2024. | 1.PM3945 2.PM6580
Dudley River 1 | MA | 118831 | 138790 | -19959 | -14.38% | 109903.4 | 8927.6 | 8.123% | 1. Inverter 1 combiner 5 is offline on 02/08/2024 & back online at 12:45 PM on same day. 2.(A) Inverter 1 CB 4 & 5 tripped offline on 02/16/2024 at 13:30 & back online on 02/17/2024 at 16:30. 2.(B) Inverter 1 CB 5 tripped oflfine on 02/20/2024 at 08:00 & back online at 16:15. 3. Inverter 1 CB 5 tripped oflfine on 02/21/2024 at 08:00 & back online at 12:00. 4. Inverter 1 CB 4 tripped offline on 02/29/2024 at 12:45 & back online 03/01/2024 at 08:15. | 1. SR080854. 2. SR081071 3. SR081152 4. SR081467
Dudley River 2 | MA | 114866 | 138292.5 | -23426.5 | -16.94% | 104560.3 | 10305.7 | 9.856% | 1. Inverter 2 CB 4 is offline on 02/17/2024 & back online on 02/20/2024 at 15:15. 2.(A)Inverter 1 was offline on 02/24/2024 & back online at 10:45 on same day. 2.(B) Inverter 1 was offline on 02/25/2024 & back online at 11:45 on same day. | 1. SR081074. 2. SR081288
Dudley River 3 | MA | 128025 | 139249.9 | -11224.9 | -8.061% | 106013.9 | 22011.1 | 20.76%
Flint Pond | MA | 52890 | 75445.3 | -22555.3 | -29.9% | 47473.76 | 5416.24 | 11.41% | 1. SIte tripped offline on 02/19/2024 at 09:45 & back online at 11:15. | 1.SR081103
Incom | MA | 245273 | 327202 | -81929 | -25.04% | 263772.2 | -18499.2 | -7.013% | 1. Site tripped offline on 02/07/2024 at 12:15 & back online at 14:00 | 1.SR080830
JH | MA | 117284 | 160679.3 | -43395.3 | -27.01% | 129552.7 | -12268.7 | -9.47%
Ledeaux | MA | 107690 | 127152.8 | -19462.8 | -15.31% | 121695.2 | -14005.2 | -11.51%
Palombo A | MA | 242837.9967 | 319493.4 | -76655.4033 | -23.99% | 292221 | -49383.0033 | -16.9%
Palombo B | MA | 112113 | 151059 | -38946 | -25.78% | 101907 | 10206 | 10.02%
St Josephs Church | MA | 102403 | 161969.1 | -59566.1 | -36.78% | 115957.7 | -13554.7 | -11.69%
Sunset A | MA | 54854 | 80039.97 | -25185.97 | -31.47% | 46223.21 | 8630.79 | 18.67% | 1. SIte tripped offline on 03/16/2024 at 06:45 & back online at 08:00. | 1.SR081036
Sunset B | MA | 47906 | 62731.88 | -14825.88 | -23.63% | 45670.03 | 2235.97 | 4.896% | 1. SIte tripped offline on 02/16/2024 at 06:45 & back online at 08:00. 2. Site was taken offline by USNE on 02/15/2024 from 08:15 to 13:30. 3. Combiner Box 2 tripped offline on 02/16/2024 at 14:15 & back online on 02/21/2024 at 10:00. | 1.SR081037 2.SR080941 3.SR081070
Woodchuck | MA | 109345 | 140965 | -31620 | -22.43% | 122162.4 | -12817.4 | -10.49% | 1.Inverter 1 Combiner box 4 tripped offline on 02/03/2024 at 12:00 & back online at 14:35. | 1.SR080694

## Mar
38 DN |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## May
38 DN |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## Apr
38 DN |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## Jun
38 DN |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## Jul
38 DN |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## Aug
38 DN |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## Sep
38 DN |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## Oct
38 DN |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## Nov
38 DN |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## Dec
38 DN |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA

## Sites
Portfolio: | 38 DN
Site DAS Name | Site | State | Update | DAS
6th St. | 6th St. | CA | AEF | PowerTrack
Barton Acres | Barton Acres | MA | AEF | PowerTrack
Bowden | Bowden | MA | AEF | PowerTrack
Blair Wire Village | Blair Wire Village | MA | AEF | PowerTrack
Boutilier | Boutilier | MA | AEF | PowerTrack
Cherry Valley | Cherry Valley | MA | AEF | PowerTrack
Cohasse | Cohasse | MA | AEF | PowerTrack
ISM Dighton Solar 2 | ISM Dighton Solar 2 | MA | AEF | PowerTrack
Dudley River 1 | Dudley River 1 | MA | AEF | PowerTrack
Dudley River 2 | Dudley River 2 | MA | AEF | PowerTrack
Dudley River 3 | Dudley River 3 | MA | AEF | PowerTrack
Flint Pond | Flint Pond | MA | AEF | PowerTrack
Incom | Incom | MA | AEF | PowerTrack
JH | JH | MA | AEF | PowerTrack
Ledeaux | Ledeaux | MA | AEF | PowerTrack
Palombo A | Palombo A | MA | AEF | PowerTrack
Palombo B | Palombo B | MA | AEF | PowerTrack
St Josephs Church | St Josephs Church | MA | AEF | PowerTrack
Sunset A | Sunset A | MA | AEF | PowerTrack
Sunset B | Sunset B | MA | AEF | PowerTrack
Woodchuck | Woodchuck | MA | AEF | PowerTrack