## Year to Date
Walden Renewables Dev't LLC |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 4826820.005 | 4913145.444 | -86325.439 | -1.757% | 5272534.72 | -445714.715 | -8.454%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
ME: Wells - Littlefield Solar | MAINE | 4826820.005 | 4913145.444 | -86325.439 | -1.757% | 5272534.72 | -445714.715 | -8.454%

## 1st Qtr
Walden Renewables Dev't LLC |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 1445400.005 | 1701799.954 | -256399.949 | -15.07% | 1751112.92 | -305712.915 | -17.46%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
ME: Wells - Littlefield Solar | MAINE | 1445400.005 | 1701799.954 | -256399.949 | -15.07% | 1751112.92 | -305712.915 | -17.46%

## 2nd Qtr
Walden Renewables Dev't LLC |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 2464875 | 2288937.7 | 175937.3 | 7.686% | 2585592.6 | -120717.6 | -4.669%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
ME: Wells - Littlefield Solar | MAINE | 2464875 | 2288937.7 | 175937.3 | 7.686% | 2585592.6 | -120717.6 | -4.669%

## 3rd Qtr
Walden Renewables Dev't LLC |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 916545 | 922407.79 | -5862.79 | -0.6356% | 935829.2 | -19284.2 | -2.061%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
ME: Wells - Littlefield Solar | MAINE | 916545 | 922407.79 | -5862.79 | -0.6356% | 935829.2 | -19284.2 | -2.061%

## 4th Qtr
Walden Renewables Dev't LLC |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
ME: Wells - Littlefield Solar | MAINE | 0 | 0 | 0 |  |  | 0

## Jan
Walden Renewables Dev't LLC |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 213608 | 396501.9 | -182893.9 | -46.13% | 419715.6 | -206107.6 | -49.11%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE | 213608 | 396501.9 | -182893.9 | -46.13% | 419715.6 | -206107.6 | -49.11% | 1. Inverter 22 was offline on 01/10, 01/25 to 01/27, 01/29, 01/31 | 1. SR079744

## Feb
Walden Renewables Dev't LLC |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 623639 | 682847 | -59208 | -8.671% | 571610.7 | 52028.3 | 9.102%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE | 623639 | 682847 | -59208 | -8.671% | 571610.7 | 52028.3 | 9.102% | 1.Inverter 22 was offline on 02/02. The technician reset it on the same day, and it is back online. | 1.SR079744

## Mar
Walden Renewables Dev't LLC |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 608153.005 | 622451.054 | -14298.049 | -2.297% | 759786.62 | -151633.615 | -19.96%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE | 608153.005 | 622451.054 | -14298.049 | -2.297% | 759786.62 | -151633.615 | -19.96% | 1. Inverter 32 started late on 03/06 & was offline on 03/15 & back online on 03/16. 2. Site is offline from 03/23 at 20:00 to 03/27 at 10:00. | 1. SR081601 2. SR082608

## Apr
Walden Renewables Dev't LLC |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 698240 | 705102 | -6862 | -0.9732% | 788000 | -89760 | -11.39%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE | 698240 | 705102 | -6862 | -0.9732% | 788000 | -89760 | -11.39% | 1. Site is offline due to storm from 04/04/24 at 05:00AM and back online at 13:00 on 04/08/24. 2. Inverter 31 is offline from 13:00 to 15:15 on 04/08/24. 3. Inverter 22 is offline due to "Insolation fault" on 04/13 from 07:00AM to 11:15AM. 4. Inverter 20 is derating about 43kW and reporting "fan fail" from 04/13 and need to replace fan. 5. Inverter 5 is offline from 07:00AM to 11:45AM on 04/17/24. 6. Inverter 33 is derating about 17kW and reporting "potential fan fault" on 04/18/24. | 1. SR083080 2. SR083205 3. SR083378 4. SR083431 5. SR083539 6. SR083601

## May
Walden Renewables Dev't LLC |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 872100 | 680511 | 191589 | 28.15% | 917000 | -44900 | -4.896%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE | 872100 | 680511 | 191589 | 28.15% | 917000 | -44900 | -4.896% | 1. Inverter 20 tripped offline at 15:15 on 05/21/24 and back online at 07:00AM on 05/31/24. 2. Inverter 32 late started on 05/06/24 due to an insulation fault 3. The weather station stopped communicating on 05/24 at 15:00, and a technician reset the Weather Station DAS and restored communication on 05/31 at 8:30 AM. Due to this, the expected energy values are low compared to the previous month. | 1. SR084988 2. SR081601 3. SR085273

## Jun
Walden Renewables Dev't LLC |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 894535 | 903324.7 | -8789.7 | -0.973% | 880592.6 | 13942.4 | 1.583%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE | 894535 | 903324.7 | -8789.7 | -0.973% | 880592.6 | 13942.4 | 1.583% | 1. Site was offline from 6pm of 06/23 and back online at 2pm of 06/24, it was offline due to the recloser being open from the customer's end 2. Inverters 21, 22 & 31 have started late i.e., at 10am on 06/27 | 1. SR086772 2. SR086893

## Jul
Walden Renewables Dev't LLC |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 916545 | 922407.79 | -5862.79 | -0.6356% | 935829.2 | -19284.2 | -2.061%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE | 916545 | 922407.79 | -5862.79 | -0.6356% | 935829.2 | -19284.2 | -2.061% | 1. Inverter 20 was underperforming approximately 30kW down compared its peers. 2. PAD 1 was tripped offline at 15:30 on 07/01 and back online at 10:15AM on 07/02 3. Site was offline from 05:45am to 11:30am on 07/14 4. Site was offline from 10:00am to 15:30 on 07/17 | 1. SR083431 2. SR087219 3. SR087653 4. SR087820

## Aug
Walden Renewables Dev't LLC |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE

## Sep
Walden Renewables Dev't LLC |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE

## Oct
Walden Renewables Dev't LLC |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE

## Nov
Walden Renewables Dev't LLC |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE

## Dec
Walden Renewables Dev't LLC |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
ME: Wells - Littlefield Solar | MAINE

## Sites
Portfolio: | Walden Renewables Dev't LLC
Site DAS Name | Site | State | Update | DAS
Littlefield Solar | ME: Wells - Littlefield Solar | MAINE | AEF | PowerTrack