## Year to Date
Canton Ice House |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 125991.628 | 0 | 125991.628 | 0% | 0 | 125991.628 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 125991.628 | 0 | 125991.628 |  | 0 | 125991.628

## 1st Qtr
Canton Ice House |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 53753.287 | 0 | 53753.287 | 0% | 0 | 53753.287 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 53753.287 | 0 | 53753.287 |  | 0 | 53753.287

## 2nd Qtr
Canton Ice House |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 72238.341 | 0 | 72238.341 | 0% | 0 | 72238.341 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 72238.341 | 0 | 72238.341 |  |  | 72238.341

## 3rd Qtr
Canton Ice House |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 0 | 0 | 0 |  |  | 0

## 4th Qtr
Canton Ice House |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Canton - Canton Ice House | MA | 0 | 0 | 0 |  |  | 0

## Jan
Canton Ice House |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 10619.76 | 0 | 10619.76 | 0% | 0 | 10619.76 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 10619.76 | 0 | 10619.76 |  | 0 | 10619.76 |  | 1. Inverter 9 was offline since 01/07. | 1. SR080386

## Feb
Canton Ice House |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 30895 | 0 | 30895 | 0% | 0 | 30895 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 30895 | 0 | 30895 |  | 0 | 30895 |  | 1. Inverter 9 is offline throughout the month. 2. Inverter 3 tripped offline at 11:30 on 02/16 & back online on 02/20 at 09:30 | 1.SR080386 2.SR081057

## Mar
Canton Ice House |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 12238.527 | 0 | 12238.527 | 0% | 0 | 12238.527 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 12238.527 | 0 | 12238.527 |  | 0 | 12238.527 |  | 1. Site tripped offline on 03/12 at 09:30 & continued throughout the month. 2. Inverter 9 is offline throughout the month. 3. Inverters 1, 11, 13 are underproducing around 15kW each compared to its peers since 03/08. | 1.SR081798 2.SR080386 3. SR081706

## Apr
Canton Ice House |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site tripped offline on 03/12 at 09:30 & continued throughout the month. | 1.SR081798

## May
Canton Ice House |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 2063.197 | 0 | 2063.197 | 0% | 0 | 2063.197 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 2063.197 | 0 | 2063.197 |  | 0 | 2063.197 |  | 1. Site is offline from 03/12 and back online on 05/31. 2. Inverter 8,9,11 and 12 are offline from 05/31. 3. Inverters 1, 13 are underproducing around 15kW each compared to its peers since 03/08. | 1. SR081798 2. SR085347 3. SR081706

## Jun
Canton Ice House |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 70175.144 | 0 | 70175.144 | 0% | 0 | 70175.144 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA | 70175.144 | 0 | 70175.144 |  | 0 | 70175.144 |  | 1. Inverter 8,9,11 and 12 are offline from 05/31 and 8, 12 back online at 12:00PM on 06/06 and inverter 9 and 11 are back online on 06/25 after replacing relay boards. 2. Inverters 1, 13 are underproducing around 15kW each compared to its peers since 03/08. | 1. SR085347 2. SR081706

## Jul
Canton Ice House |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA

## Aug
Canton Ice House |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA

## Sep
Canton Ice House |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA

## Oct
Canton Ice House |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA

## Nov
Canton Ice House |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA

## Dec
Canton Ice House |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Canton - Canton Ice House | MA

## Sites
Portfolio: | Canton Ice House
Site DAS Name | Site | State | Update | DAS
Canton Ice House | MA: Canton - Canton Ice House | MA | AF | PowerTrack