## Year to Date
Cave Creek USD |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 368627 | 318889.25 | 49737.75 | 15.6% | 0 | 368627 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Cave Creek - DWES | AZ | 224759 | 233764.31 | -9005.31 | -3.852% | 0 | 224759 | 0%
AZ: Cave Creek - HTES | AZ | 65853 | 85124.94 | -19271.94 | -22.64% | 0 | 65853 | 0%
AZ: Cave Creek - LMES | AZ | 78015 | 0 | 78015 | 0% | 0 | 78015 | 0%

## 1st Qtr
Cave Creek USD |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 235410 | 177803.88 | 57606.12 | 32.4% | 0 | 235410 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Cave Creek - DWES | AZ | 91542 | 92678.94 | -1136.94 | -1.227% | 0 | 91542 | 0%
AZ: Cave Creek - HTES | AZ | 65853 | 85124.94 | -19271.94 | -22.64% | 0 | 65853 | 0%
AZ: Cave Creek - LMES | AZ | 78015 | 0 | 78015 | 0% | 0 | 78015 | 0%

## 2nd Qtr
Cave Creek USD |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 351969.5 | 273880.5 | 78089 | 28.51% | 0 | 351969.5 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Cave Creek - DWES | AZ | 133217 | 141085.37 | -7868.37 | -5.577% |  | 133217 | 0%
AZ: Cave Creek - HTES | AZ | 98941.25 | 132795.13 | -33853.88 | -25.49% |  | 98941.25 | 0%
AZ: Cave Creek - LMES | AZ | 119811.25 | 0 | 119811.25 | 0% |  | 119811.25 | 0%

## 3rd Qtr
Cave Creek USD |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Cave Creek - DWES | AZ | 0 | 0 | 0 | 0% |  | 0 | 0%
AZ: Cave Creek - HTES | AZ | 0 | 0 | 0 | 0% |  | 0 | 0%
AZ: Cave Creek - LMES | AZ | 0 | 0 | 0 | 0% |  | 0 | 0%

## 4th Qtr
Cave Creek USD |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Cave Creek - DWES | AZ | 0 | 0 | 0 |  |  | 0
AZ: Cave Creek - HTES | AZ | 0 | 0 | 0 |  |  | 0
AZ: Cave Creek - LMES | AZ | 0 | 0 | 0 |  |  | 0

## Jan
Cave Creek USD |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 64323 | 48931.88 | 15391.12 | 31.45% | 0 | 64323 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ | 25401 | 25675.94 | -274.94 | -1.071% | 0 | 25401 | 0%
AZ: Cave Creek - HTES | AZ | 17366 | 23255.94 | -5889.94 | -25.33% | 0 | 17366 | 0% | 1. Inverter 1.7 is offline for whole month. | 1. SR075156
AZ: Cave Creek - LMES | AZ | 21556 | 0 | 21556 | 0% | 0 | 21556 | 0%

## Feb
Cave Creek USD |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 75073 | 56523 | 18550 | 32.82% | 0 | 75073 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ | 28950 | 29323 | -373 | -1.272% | 0 | 28950
AZ: Cave Creek - HTES | AZ | 21380 | 27200 | -5820 | -21.4% | 0 | 21380 |  | 1. Meter is not capturing full production of inverters 2. Inverter 1.7 is offline for whole month | 1. SR081116 2. SR075156
AZ: Cave Creek - LMES | AZ | 24743 | 0 | 24743 |  | 0 | 24743

## Mar
Cave Creek USD |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 96014 | 72349 | 23665 | 32.71% | 0 | 96014 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ | 37191 | 37680 | -489 | -1.298% | 0 | 37191
AZ: Cave Creek - HTES | AZ | 27107 | 34669 | -7562 | -21.81% | 0 | 27107 |  | 1. Inverter 1.7 is offline & RMA'd | 1. SR075156
AZ: Cave Creek - LMES | AZ | 31716 | 0 | 31716 |  | 0 | 31716

## Apr
Cave Creek USD |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 116907.5 | 89840.56 | 27066.94 | 30.13% | 0 | 116907.5 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ | 44830.5 | 46486.1 | -1655.6 | -3.561% | 0 | 44830.5
AZ: Cave Creek - HTES | AZ | 33191 | 43354.46 | -10163.46 | -23.44% | 0 | 33191 |  | 1. Meter is not capturing full production of inverters due to drop in phase B and phase C currents. But the SR is in closed state 2. Inverter 1.7 is offline and being RMA'd | 1. SR081116 2. SR075156
AZ: Cave Creek - LMES | AZ | 38886 | 0 | 38886 |  | 0 | 38886

## May
Cave Creek USD |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 123538.5 | 97361.58 | 26176.92 | 26.89% | 0 | 123538.5 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ | 48409 | 49907.09 | -1498.09 | -3.002% | 0 | 48409 |  | 1. Inverter 1-6 was offline on 05/22,05/30 | 1. SR085017
AZ: Cave Creek - HTES | AZ | 35656.75 | 47454.49 | -11797.74 | -24.86% | 0 | 35656.75 |  | 1. Meter is not capturing full production of inverters due to drop in phase B and phase C currents. But the SR was in closed state 2. Inverter 1.7 was replaced on 05/16 but it is still offline 3. Inverter 1.4 was offline on 05/18 and back online on 05/19. | 1. SR081116 2. SR075156 3. SR084829
AZ: Cave Creek - LMES | AZ | 39472.75 | 0 | 39472.75 |  | 0 | 39472.75 |  | 1. Site tripped offline at 13:30 on 05/21 and back online at 09:00 on 05/24 | 1. SR084994

## Jun
Cave Creek USD |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 111523.5 | 86678.36 | 24845.14 | 28.66% | 0 | 111523.5 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ | 39977.5 | 44692.18 | -4714.68 | -10.55% | 0 | 39977.5 |  | 1. Inverter 1-6 was derating during peak hours from 06/11. Inverter was also offline on 06/17,06/30 | 1. SR085017
AZ: Cave Creek - HTES | AZ | 30093.5 | 41986.18 | -11892.68 | -28.33% | 0 | 30093.5 |  | 1. Meter is not capturing full production of inverters due to drop in phase B and phase C currents. But the SR was in closed state. 2. Inverter 1.7 is still offline throughout the month 3. Inverter 1.4 was offline throughout the month | 1. SR081116 2. SR075156 3. SR084829
AZ: Cave Creek - LMES | AZ | 41452.5 | 0 | 41452.5 |  | 0 | 41452.5

## Jul
Cave Creek USD |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ
AZ: Cave Creek - HTES | AZ
AZ: Cave Creek - LMES | AZ

## Aug
Cave Creek USD |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ
AZ: Cave Creek - HTES | AZ
AZ: Cave Creek - LMES | AZ

## Sep
Cave Creek USD |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ
AZ: Cave Creek - HTES | AZ
AZ: Cave Creek - LMES | AZ

## Oct
Cave Creek USD |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ
AZ: Cave Creek - HTES | AZ
AZ: Cave Creek - LMES | AZ

## Nov
Cave Creek USD |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ
AZ: Cave Creek - HTES | AZ
AZ: Cave Creek - LMES | AZ

## Dec
Cave Creek USD |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Cave Creek - DWES | AZ
AZ: Cave Creek - HTES | AZ
AZ: Cave Creek - LMES | AZ

## Sites
Portfolio: | Cave Creek USD
Site DAS Name | Site | State | Update | DAS
AZ: Cave Creek - DWES | AZ: Cave Creek - DWES | AZ
AZ: Cave Creek - HTES | AZ: Cave Creek - HTES | AZ
AZ: Cave Creek - LMES | AZ: Cave Creek - LMES | AZ