## Year to Date
CITI |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 3851393 | 4040668.715 | -189275.715 | -4.684% | 12020592.196 | -8169199.196 | -67.96%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CA: Antioch Deer Valley - Citi | CA | 314978.75 | 330113 | -15134.25 | -4.585% | 330080.116 | -15100.366 | -4.575%
CA: Antioch MC CUP - Citi | CA | 362875.5 | 380766 | -17890.5 | -4.699% | 1162112.593 | -12056.349 | -1.037%
CA: Clovis - Citi | CA | 154790 | 148411 | 6379 | 4.298% | 502120.997 | -23439.167 | -4.668%
CA: Elk Grove MOB - Citi | CA | 226351 | 244939 | -18588 | -7.589% | 764651.533 | -15943.561 | -2.085%
CA: Elk Grove Promenade - Citi | CA | 108983.5 | 133398.715 | -24415.215 | -18.3% | 407848.749 | -25538.508 | -6.262%
CA: Fresno Sequioa - Citi | CA | 270913.25 | 265872 | 5041.25 | 1.896% | 828682.041 | -14907.428 | -1.799%
CA: Fresno MOB - Citi | CA | 107138 | 107580 | -442 | -0.4109% | 315537.639 | -1747.53 | -0.5538%
CA: Modesto Bangs - Citi | CA | 60911.62 | 63488 | -2576.38 | -4.058% | 198104.264 | -2931.012 | -1.48%
CA: Napa Data Center - Citi | CA | 63472.13 | 76672 | -13199.87 | -17.22% | 222637.073 | -13215.736 | -5.936%
CA: Petaluma MOB - Citi | CA | 154083.25 | 174957 | -20873.75 | -11.93% | 477402.3 | -24742.77 | -5.183%
CA: Pleasanton Tec Ctr - Citi | CA | 201975 | 250800 | -48825 | -19.47% | 745718.569 | -37017.968 | -4.964%
CA: Rancho Cordova - Citi | CA | 369775.5 | 375511 | -5735.5 | -1.527% | 1101842.077 | -11520.162 | -1.046%
CA: S Sacramento Wyndham - Citi | CA | 190604.75 | 210511 | -19906.25 | -9.456% | 616298.692 | -3945.614 | -0.6402%
CA: Sacramento Point West - Citi | CA | 339616 | 404674 | -65058 | -16.08% | 1270730.845 | -60477.519 | -4.759%
CA: San Jose FHC - Citi | CA | 72920.12 | 93317 | -20396.88 | -21.86% | 193397.113 | -10259.84 | -5.305%
CA: San Jose MOB - Citi | CA | 109423.25 | 148699 | -39275.75 | -26.41% | 416079.338 | -24509.279 | -5.891%
CA: Selma - Citi | CA | 78863.63 | 76746 | 2117.63 | 2.759% | 254452.387 | -8645.46 | -3.398%
CA: Vacaville Hospital | CA | 499858.25 | 554214 | -54355.75 | -9.808% | 1761334.635 | 6850.773 | 0.389%
CA: Manteca - KP Manteca Hospital | CA | 163859.5 | 0 | 163859.5 | 0% | 451561.235 | 29908.895 | 6.623%

## 1st Qtr
CITI |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 3630733.75 | 3825386.715 | -194652.965 | -5.088% | 3888648.141 | -257914.391 | -6.632%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CA: Antioch Deer Valley - Citi | CA | 94319.5 | 114831 | -20511.5 | -17.86% | 98098.656 | -3778.156 | -3.851%
CA: Antioch MC CUP - Citi | CA | 362875.5 | 380766 | -17890.5 | -4.699% | 374931.849 | -12056.349 | -3.216%
CA: Clovis - Citi | CA | 154790 | 148411 | 6379 | 4.298% | 178229.167 | -23439.167 | -13.15%
CA: Elk Grove MOB - Citi | CA | 226351 | 244939 | -18588 | -7.589% | 242294.561 | -15943.561 | -6.58%
CA: Elk Grove Promenade - Citi | CA | 108983.5 | 133398.715 | -24415.215 | -18.3% | 134522.008 | -25538.508 | -18.98%
CA: Fresno Sequioa - Citi | CA | 270913.25 | 265872 | 5041.25 | 1.896% | 285820.678 | -14907.428 | -5.216%
CA: Fresno MOB - Citi | CA | 107138 | 107580 | -442 | -0.4109% | 108885.53 | -1747.53 | -1.605%
CA: Modesto Bangs - Citi | CA | 60911.62 | 63488 | -2576.38 | -4.058% | 63842.632 | -2931.012 | -4.591%
CA: Napa Data Center - Citi | CA | 63472.13 | 76672 | -13199.87 | -17.22% | 76687.866 | -13215.736 | -17.23%
CA: Petaluma MOB - Citi | CA | 154083.25 | 174957 | -20873.75 | -11.93% | 178825.02 | -24742.77 | -13.84%
CA: Pleasanton Tec Ctr - Citi | CA | 201975 | 250800 | -48825 | -19.47% | 238992.968 | -37017.968 | -15.49%
CA: Rancho Cordova - Citi | CA | 369775.5 | 375511 | -5735.5 | -1.527% | 381294.662 | -11520.162 | -3.021%
CA: S Sacramento Wyndham - Citi | CA | 190604.75 | 210511 | -19906.25 | -9.456% | 194549.364 | -3945.614 | -2.028%
CA: Sacramento Point West - Citi | CA | 339616 | 404674 | -65058 | -16.08% | 400093.519 | -60477.519 | -15.12%
CA: San Jose FHC - Citi | CA | 72920.12 | 93317 | -20396.88 | -21.86% | 83179.96 | -10259.84 | -12.33%
CA: San Jose MOB - Citi | CA | 109423.25 | 148699 | -39275.75 | -26.41% | 133932.529 | -24509.279 | -18.3%
CA: Selma - Citi | CA | 78863.63 | 76746 | 2117.63 | 2.759% | 87509.09 | -8645.46 | -9.879%
CA: Vacaville Hospital | CA | 499858.25 | 554214 | -54355.75 | -9.808% | 493007.477 | 6850.773 | 1.39%
CA: Manteca - KP Manteca Hospital | CA | 163859.5 | 0 | 163859.5 | 0% | 133950.605 | 29908.895 | 22.33%

## 2nd Qtr
CITI |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 7381762.75 | 7509406.735 | -127643.985 | -1.7% | 8131944.055 | -750181.305 | -9.225%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CA: Antioch Deer Valley - Citi | CA | 220659.25 | 215282 | 5377.25 | 2.498% | 231981.46 | -11322.21 | -4.881%
CA: Antioch MC CUP - Citi | CA | 757441 | 734291 | 23150 | 3.153% | 787180.744 | -29739.744 | -3.778%
CA: Clovis - Citi | CA | 316814.5 | 312002 | 4812.5 | 1.542% | 323891.83 | -7077.33 | -2.185%
CA: Elk Grove MOB - Citi | CA | 486584.5 | 506248 | -19663.5 | -3.884% | 522356.972 | -35772.472 | -6.848%
CA: Elk Grove Promenade - Citi | CA | 256185.75 | 267090.735 | -10904.985 | -4.083% | 273326.741 | -17140.991 | -6.271%
CA: Fresno Sequioa - Citi | CA | 523930.25 | 527508 | -3577.75 | -0.6782% | 542861.363 | -18931.113 | -3.487%
CA: Fresno MOB - Citi | CA | 203098.5 | 215736 | -12637.5 | -5.858% | 206652.109 | -3553.609 | -1.72%
CA: Modesto Bangs - Citi | CA | 130541.38 | 153691 | -23149.62 | -15.06% | 134261.632 | -3720.252 | -2.771%
CA: Napa Data Center - Citi | CA | 128313.87 | 149198 | -20884.13 | -14% | 145949.207 | -17635.337 | -12.08%
CA: Petaluma MOB - Citi | CA | 325444.5 | 341582 | -16137.5 | -4.724% | 298577.28 | 26867.22 | 8.998%
CA: Pleasanton Tec Ctr - Citi | CA | 308543 | 487317 | -178774 | -36.69% | 506725.601 | -198182.601 | -39.11%
CA: Rancho Cordova - Citi | CA | 677515.5 | 677829 | -313.5 | -0.04625% | 720547.415 | -43031.915 | -5.972%
CA: S Sacramento Wyndham - Citi | CA | 425085.25 | 437275 | -12189.75 | -2.788% | 421749.328 | 3335.922 | 0.791%
CA: Sacramento Point West - Citi | CA | 759841 | 840410 | -80569 | -9.587% | 870637.326 | -110796.326 | -12.73%
CA: San Jose FHC - Citi | CA | 101222.38 | 110171 | -8948.62 | -8.122% | 110217.153 | -8994.773 | -8.161%
CA: San Jose MOB - Citi | CA | 242719 | 269342 | -26623 | -9.884% | 282146.809 | -39427.809 | -13.97%
CA: Selma - Citi | CA | 155678.12 | 162068 | -6389.88 | -3.943% | 166943.297 | -11265.177 | -6.748%
CA: Vacaville Hospital | CA | 1030002 | 1102366 | -72364 | -6.564% | 1268327.158 | -238325.158 | -18.79%
CA: Manteca - KP Manteca Hospital | CA | 332143 | 0 | 332143 |  | 317610.63 | 14532.37

## 3rd Qtr
CITI |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CA: Antioch Deer Valley - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Antioch MC CUP - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Clovis - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Elk Grove MOB - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Elk Grove Promenade - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Fresno Sequioa - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Fresno MOB - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Modesto Bangs - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Napa Data Center - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Petaluma MOB - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Pleasanton Tec Ctr - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Rancho Cordova - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: S Sacramento Wyndham - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Sacramento Point West - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: San Jose FHC - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: San Jose MOB - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Selma - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Vacaville Hospital | CA | 0 | 0 | 0 |  |  | 0
CA: Manteca - KP Manteca Hospital | CA

## 4th Qtr
CITI |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CA: Antioch Deer Valley - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Antioch MC CUP - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Clovis - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Elk Grove MOB - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Elk Grove Promenade - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Fresno Sequioa - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Fresno MOB - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Modesto Bangs - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Napa Data Center - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Petaluma MOB - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Pleasanton Tec Ctr - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Rancho Cordova - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: S Sacramento Wyndham - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Sacramento Point West - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: San Jose FHC - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: San Jose MOB - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Selma - Citi | CA | 0 | 0 | 0 |  |  | 0
CA: Vacaville Hospital | CA | 0 | 0 | 0 |  |  | 0
CA: Manteca - KP Manteca Hospital | CA

## Jan
CITI |  |  | PPA Modeled Output | Production VS Acual | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 761477 | 909284 | 0.84 | 875403 | -113926 | -13% | 819042 | -57566 | -7%
Site | State | Actual |  |  | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA | 23783 | 26935 | 88.3% | 26802 | -3019 | -11% | 25334 | -1550 | -6%
CA: Antioch MC CUP - Citi | CA | 77142 | 88103 | 87.56% | 87662 | -10520 | -12% | 82560 | -5418 | -7%
CA: Clovis - Citi | CA | 32833 | 30338 | 108.2% | 29586 | 3247 | 11% | 39906 | -7073 | -18%
CA: Elk Grove MOB - Citi | CA | 45130 | 55259 | 81.67% | 54986 | -9856 | -18% | 50117 | -4987 | -10%
CA: Elk Grove Promenade - Citi | CA | 22326 | 30535 | 73.12% | 30385 | -8059 | -27% | 28265 | -5939 | -21% | 1. Inverter 2.3 was offline for whole month. | 1. SR079094
CA: Fresno Sequioa - Citi | CA | 54029 | 54436 | 99.25% | 54179 | -150 | 0% | 60598 | -6569 | -11%
CA: Fresno MOB - Citi | CA | 23116 | 21918 | 105.5% | 21868 | 1248 | 6% | 24310 | -1194 | -5%
CA: Modesto Bangs - Citi | CA | 12386 | 12108 | 102.3% | 12166 | 220 | 2% | 13154 | -768 | -6%
CA: Napa Data Center - Citi | CA | 13911 | 18607 | 74.76% | 18187 | -4276 | -24% | 17420 | -3509 | -20% | 1. Inverter 3 was late started on 01/20 due to isolation fault. 2. Inverter 2 was late started on 01/23 due to isolation fault. | 1. SR080355 2. SR080409
CA: Petaluma MOB - Citi | CA | 33859 | 45402 | 74.58% | 43911 | -10052 | -23% | 41451 | -7593 | -18% | 1. Inverter 5 tripped offline on 1/27 at 12:00 PM and back online on 1/28. | 1. SR080526
CA: Pleasanton Tec Ctr - Citi | CA | 45268 | 61178 | 73.99% | 60582 | -15314 | -25% | 54215 | -8947 | -17%
CA: Rancho Cordova - Citi | CA | 81163 | 89790 | 90.39% | 89248 | -8086 | -9% | 85149 | -3987 | -5%
CA: S Sacramento Wyndham - Citi | CA | 38854 | 47416 | 81.94% | 47087 | -8233 | -17% | 39156 | -303 | -1%
CA: Sacramento Point West - Citi | CA | 61133 | 90699 | 67.4% | 90683 | -29551 | -33% | 84914 | -23781 | -28% | 1. Meter only captured 2/3rd of inverter production from 01/11 to 1/18 and later technician resolved the issue. 2. Inverter 1.1 offline on 01/17, 1/19. | 1. SR080147
CA: San Jose FHC - Citi | CA | 16856 | 22812 | 73.89% | 23498 | -6642 | -28% | 19495 | -2639 | -14% | 1. Inverter 8 is derating approximately 10kW. | 1. SR080602
CA: San Jose MOB - Citi | CA | 22891 | 37720 | 60.69% | 38233 | -15342 | -40% | 30904 | -8013 | -26% | 1. Inverter 2 is offline for whole month due to breaker over heating issue. | 1. PM4756
CA: Selma - Citi | CA | 16831 | 15404 | 109.3% | 15271 | 1560 | 10% | 19232 | -2401 | -12%
CA: Vacaville Hospital | CA | 105587 | 130651 | 80.82% | 131069 | -25482 | -19% | 102862 | 2725 | 3%
CA: Manteca - KP Manteca Hospital | CA | 34381 | 29973 | 114.7% | 0 | 34381 | 0% | 0 | 34381 | 0%

## Feb
CITI |  |  | PPA Modeled Output | Production VS Acual | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 1148130.9 | 909284 | 0.84 | 1139799.16 | 8331.74 | 0.731% | 1229355.344 | -81224.444 | -6.607%
Site | State | Actual |  |  | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA | 33559 | 33838 | 99% | 33671 | -112 | -0.3326% | 34392.865 | -833.865 | -2.425%
CA: Antioch MC CUP - Citi | CA | 110890 | 111656 | 99% | 111096 | -206 | -0.1854% | 113606.749 | -2716.749 | -2.391%
CA: Clovis - Citi | CA | 48875.75 | 46788 | 104% | 45628 | 3247.75 | 7.118% | 55784.006 | -6908.256 | -12.38%
CA: Elk Grove MOB - Citi | CA | 72294.5 | 74269 | 97% | 73903 | -1608.5 | -2.177% | 76074.415 | -3779.915 | -4.969%
CA: Elk Grove Promenade - Citi | CA | 34178.25 | 40582 | 84% | 40382.16 | -6203.91 | -15.36% | 42366.747 | -8188.497 | -19.33%
CA: Fresno Sequioa - Citi | CA | 87690.75 | 83832 | 105% | 83436 | 4254.75 | 5.099% | 90443.703 | -2752.953 | -3.044%
CA: Fresno MOB - Citi | CA | 33643.13 | 33738 | 100% | 33625 | 18.13 | 0.05392% | 33875.379 | -232.249 | -0.6856%
CA: Modesto Bangs - Citi | CA | 18676.37 | 20448 | 91% | 20450 | -1773.63 | -8.673% | 19457.064 | -780.694 | -4.012%
CA: Napa Data Center - Citi | CA | 19292 | 22694 | 85% | 22187 | -2895 | -13.05% | 23401.866 | -4109.866 | -17.56% | 1. Inverter 3 was late started on 02/20, 02/21, 02/22 due to isolation fault. | 1. SR081199
CA: Petaluma MOB - Citi | CA | 45005 | 52699 | 85% | 50968 | -5963 | -11.7% | 53496.513 | -8491.513 | -15.87% | 1. Inverter 4 has tripping event frequently from 02/02/2024 to 02/21/2024. | 1. SR080566
CA: Pleasanton Tec Ctr - Citi | CA | 61506.5 | 71770 | 86% | 71319 | -9812.5 | -13.76% | 73097.041 | -11590.541 | -15.86%
CA: Rancho Cordova - Citi | CA | 122166.5 | 116945 | 104% | 116239 | 5927.5 | 5.099% | 124611.564 | -2445.064 | -1.962%
CA: S Sacramento Wyndham - Citi | CA | 59864.25 | 63883 | 94% | 63439 | -3574.75 | -5.635% | 60517.139 | -652.889 | -1.079%
CA: Sacramento Point West - Citi | CA | 112885.5 | 122199 | 92% | 122195 | -9309.5 | -7.619% | 126300.285 | -13414.785 | -10.62%
CA: San Jose FHC - Citi | CA | 22462.87 | 25813 | 87% | 26589 | -4126.13 | -15.52% | 26197.634 | -3734.764 | -14.26% | 1. Inverter 8 was derating 10kW compared to peers. Inverter 8 was kept offline from 02/08 and replaced on 02/22 | 1. SR080602
CA: San Jose MOB - Citi | CA | 35183 | 41784 | 84% | 42352 | -7169 | -16.93% | 42492.879 | -7309.879 | -17.2% | 1. Inverter 2 was back online on 02/09/2024 | 1. SR080860
CA: Selma - Citi | CA | 24445.75 | 23767 | 103% | 23641 | 804.75 | 3.404% | 27180.013 | -2734.263 | -10.06%
CA: Vacaville Hospital | CA | 153862.75 | 157635 | 98% | 158679 | -4816.25 | -3.035% | 151744.479 | 2118.271 | 1.396%
CA: Manteca - KP Manteca Hospital | CA | 51649.03 | 48307 | 107% | 0 | 51649.03 |  | 54315.003 | -2665.973 | -4.908%

## Mar
CITI |  |  | PPA Modeled Output | Production VS Acual | Q1 Production Vs PPA | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 1721123.85 | 1908970 | 0.9 | 0.9 | 1810184.555 | -89060.705 | -4.92% | 1840250.797 | -119126.947 | -6.473%
Site | State | Actual |  |  |  | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA | 36977.5 | 54627 | 68% | 81.73% | 54358 | -17380.5 | -31.97% | 38371.791 | -1394.291 | -3.634% | 1. Site tripped offline on 03/15 at 16 :30 & back online on 03/21 at 15:15. | 1.SR081976
CA: Antioch MC CUP - Citi | CA | 174843.5 | 182925 | 96% | 94.82% | 182008 | -7164.5 | -3.936% | 178765.1 | -3921.6 | -2.194%
CA: Clovis - Citi | CA | 73081.25 | 75057 | 97% | 101.7% | 73197 | -115.75 | -0.1581% | 82539.161 | -9457.911 | -11.46%
CA: Elk Grove MOB - Citi | CA | 108926.5 | 116624 | 93% | 91.96% | 116050 | -7123.5 | -6.138% | 116103.146 | -7176.646 | -6.181%
CA: Elk Grove Promenade - Citi | CA | 52479.25 | 62941 | 83% | 81.3% | 62631.555 | -10152.305 | -16.21% | 63890.261 | -11411.011 | -17.86%
CA: Fresno Sequioa - Citi | CA | 129193.5 | 128865 | 100% | 101.4% | 128257 | 936.5 | 0.7302% | 134778.975 | -5585.475 | -4.144%
CA: Fresno MOB - Citi | CA | 50378.87 | 52132 | 97% | 99.4% | 52087 | -1708.13 | -3.279% | 50700.151 | -321.281 | -0.6337%
CA: Modesto Bangs - Citi | CA | 29849.25 | 30868 | 97% | 96.04% | 30872 | -1022.75 | -3.313% | 31231.568 | -1382.318 | -4.426%
CA: Napa Data Center - Citi | CA | 30269.13 | 37239 | 81% | 80.82% | 36298 | -6028.87 | -16.61% | 35866 | -5596.87 | -15.6%
CA: Petaluma MOB - Citi | CA | 75219.25 | 82799 | 91% | 85.18% | 80078 | -4858.75 | -6.068% | 83877.507 | -8658.257 | -10.32%
CA: Pleasanton Tec Ctr - Citi | CA | 95200.5 | 119386 | 80% | 80.04% | 118899 | -23698.5 | -19.93% | 111680.927 | -16480.427 | -14.76% | 1. inverter 12 tripped at 2 pm on 03/25 & back online on 03?26 at 16:00. | 1. SR082719
CA: Rancho Cordova - Citi | CA | 166446 | 171056 | 97% | 97.88% | 170024 | -3578 | -2.104% | 171534.098 | -5088.098 | -2.966% | 1. Inverter 1.1 tripped offline on 03/15 and back online on 03/18 | 1. SR081959
CA: S Sacramento Wyndham - Citi | CA | 91886.5 | 100686 | 91% | 89.91% | 99985 | -8098.5 | -8.1% | 94876.225 | -2989.725 | -3.151%
CA: Sacramento Point West - Citi | CA | 165597.5 | 191839 | 86% | 83.91% | 191796 | -26198.5 | -13.66% | 188879.234 | -23281.734 | -12.33% | 1. Inverter 5.5 tripped offline on 03/06 | 1. SR081815
CA: San Jose FHC - Citi | CA | 33601.25 | 41968 | 80% | 80.49% | 43230 | -9628.75 | -22.27% | 37487.326 | -3886.076 | -10.37%
CA: San Jose MOB - Citi | CA | 51349.25 | 67200 | 76% | 74.59% | 68114 | -16764.75 | -24.61% | 60535.65 | -9186.4 | -15.18%
CA: Selma - Citi | CA | 37586.88 | 38029 | 99% | 102.2% | 37834 | -247.12 | -0.6532% | 41097.077 | -3510.197 | -8.541%
CA: Vacaville Hospital | CA | 240408.5 | 264914 | 91% | 90.36% | 264466 | -24057.5 | -9.097% | 238400.998 | 2007.502 | 0.8421%
CA: Manteca - KP Manteca Hospital | CA | 77829.47 | 89816 | 87% | 97.48% | 0 | 77829.47 |  | 79635.602 | -1806.132 | -2.268%

## Apr
CITI |  |  | PPA Modeled Output | Production VS Acual | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 2211322.04 | 2792828 | 0.79 | 2229750.719 | -18428.679 | -0.8265% | 2387855.809 | -176533.769 | -7.393%
Site | State | Actual |  |  | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA | 62502.25 | 65020 | 96% | 64700 | -2197.75 | -3.397% | 67484.096 | -4981.846 | -7.382% | 1. Inverter 5 offline from 04/19 till month end | 1. SR083643
CA: Antioch MC CUP - Citi | CA | 221879 | 220973 | 100% | 219865 | 2014 | 0.916% | 226738.631 | -4859.631 | -2.143%
CA: Clovis - Citi | CA | 91839.5 | 97023 | 95% | 94619 | -2779.5 | -2.938% | 96503.219 | -4663.719 | -4.833%
CA: Elk Grove MOB - Citi | CA | 145618 | 144992 | 100% | 144278 | 1340 | 0.9288% | 150577.356 | -4959.356 | -3.294%
CA: Elk Grove Promenade - Citi | CA | 75083 | 77224 | 97% | 76843.719 | -1760.719 | -2.291% | 79394.688 | -4311.688 | -5.431%
CA: Fresno Sequioa - Citi | CA | 153497 | 162121 | 95% | 161355 | -7858 | -4.87% | 159164.078 | -5667.078 | -3.561%
CA: Fresno MOB - Citi | CA | 60510.13 | 66110 | 92% | 66181 | -5670.87 | -8.569% | 60075.309 | 434.821 | 0.7238%
CA: Modesto Bangs - Citi | CA | 37677.38 | 45978 | 82% | 45983 | -8305.62 | -18.06% | 39150.418 | -1473.038 | -3.763%
CA: Napa Data Center - Citi | CA | 31030 | 45541 | 68% | 44146 | -13116 | -29.71% | 35666.853 | -4636.853 | -13% | 1. Site is tripped offline on 04/05 at 15:00 and technician reenergised the site on 04/12 at 09:30am. | 1. SR083144
CA: Petaluma MOB - Citi | CA | 95155.5 | 105601 | 90% | 102132 | -6976.5 | -6.831% | 105431.193 | -10275.693 | -9.746%
CA: Pleasanton Tec Ctr - Citi | CA | 123761.5 | 145619 | 85% | 144905 | -21143.5 | -14.59% | 146238.963 | -22477.463 | -15.37% | 1. Inverters 9 & 10 are offline throughtout the month | 1. SR079234
CA: Rancho Cordova - Citi | CA | 204774 | 200365 | 102% | 200167 | 4607 | 2.302% | 216950.073 | -12176.073 | -5.612% | 1. Inverter 4.4 offline since 04/23 | 1. SR083762
CA: S Sacramento Wyndham - Citi | CA | 122802 | 125049 | 98% | 121854 | 948 | 0.778% | 121199.493 | 1602.507 | 1.322%
CA: Sacramento Point West - Citi | CA | 218060 | 239197 | 91% | 238931 | -20871 | -8.735% | 250283.526 | -32223.526 | -12.87%
CA: San Jose FHC - Citi | CA | 45501.75 | 492327 | 9% | 50719 | -5217.25 | -10.29% | 49915.099 | -4413.349 | -8.842%
CA: San Jose MOB - Citi | CA | 70757.75 | 78444 | 90% | 79511 | -8753.25 | -11.01% | 82585.209 | -11827.459 | -14.32%
CA: Selma - Citi | CA | 46182.75 | 49331 | 94% | 49047 | -2864.25 | -5.84% | 48660.5 | -2477.75 | -5.092%
CA: Vacaville Hospital | CA | 307394 | 326133 | 94% | 324514 | -17120 | -5.276% | 357482.122 | -50088.122 | -14.01%
CA: Manteca - KP Manteca Hospital | CA | 97296.53 | 105781 | 92% | 0 | 97296.53 |  | 94354.983 | 2941.547 | 3.118%

## May
CITI |  |  | PPA Modeled Output | Production VS Acual | May Actual v. Expected |  |  | May Actual v. Forecasted |  |  |  | SR084272
Total |  | 2707257.21 | 2778689 | 0.97 | 2638371.5 | 68885.71 | 2.611% | 2970779.139 | -263521.929 | -8.87%
Site | State | Actual |  |  | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA | 77462.25 | 74449 | 104% | 74083 | 3379.25 | 4.561% | 84214.241 | -6751.991 | -8.018%
CA: Antioch MC CUP - Citi | CA | 272662.5 | 254349 | 107% | 253074 | 19588.5 | 7.74% | 284824.228 | -12161.728 | -4.27%
CA: Clovis - Citi | CA | 114407 | 108547 | 105% | 105858 | 8549 | 8.076% | 116144.681 | -1737.681 | -1.496% | 1. Inverter 2 tripped offline at 17:30 on 05/04 and back online at 07:00AM on 05/05 | 1. SR084272
CA: Elk Grove MOB - Citi | CA | 183481 | 181339 | 101% | 180446 | 3035 | 1.682% | 187871.616 | -4390.616 | -2.337%
CA: Elk Grove Promenade - Citi | CA | 92595 | 95545 | 97% | 95074.5 | -2479.5 | -2.608% | 98927.737 | -6332.737 | -6.401% | 1. Inverter 2.3 derating approximately 40kW during the peak hours on 05/08. | 1. SR084482
CA: Fresno Sequioa - Citi | CA | 190314 | 179936 | 106% | 179087 | 11227 | 6.269% | 194677.744 | -4363.744 | -2.242%
CA: Fresno MOB - Citi | CA | 74528.5 | 72873 | 102% | 73156 | 1372.5 | 1.876% | 74872.587 | -344.087 | -0.4596%
CA: Modesto Bangs - Citi | CA | 47610.62 | 52922 | 90% | 52928 | -5317.38 | -10.05% | 48752.074 | -1141.454 | -2.341% | 1. Inverter 1 has heavy evening shading based on previous history | 1. SR085819
CA: Napa Data Center - Citi | CA | 49680 | 53542 | 93% | 52066 | -2386 | -4.583% | 55682.618 | -6002.618 | -10.78%
CA: Petaluma MOB - Citi | CA | 116666 | 123235 | 95% | 119186 | -2520 | -2.114% | 128517.622 | -11851.622 | -9.222%
CA: Pleasanton Tec Ctr - Citi | CA | 133140.5 | 167398 | 80% | 166675 | -33534.5 | -20.12% | 179070.981 | -45930.481 | -25.65% | 1. Site is underperforming due damaged array1B, and site was taken offline since 05/29 for repair work. | 1. SR085283
CA: Rancho Cordova - Citi | CA | 239784 | 241188 | 99% | 240949 | -1165 | -0.4835% | 256798.966 | -17014.966 | -6.626%
CA: S Sacramento Wyndham - Citi | CA | 153563.75 | 157421 | 98% | 157119 | -3555.25 | -2.263% | 150885.588 | 2678.162 | 1.775%
CA: Sacramento Point West - Citi | CA | 275734.5 | 300484 | 92% | 299681 | -23946.5 | -7.991% | 314439.222 | -38704.722 | -12.31%
CA: San Jose FHC - Citi | CA | 55720.63 | 57716 | 97% | 59452 | -3731.37 | -6.276% | 60302.054 | -4581.424 | -7.597%
CA: San Jose MOB - Citi | CA | 87601.25 | 91386 | 96% | 92629 | -5027.75 | -5.428% | 100998.231 | -13396.981 | -13.26%
CA: Selma - Citi | CA | 56601.12 | 55270 | 102% | 55045 | 1556.12 | 2.827% | 60163.662 | -3562.542 | -5.921%
CA: Vacaville Hospital | CA | 364586 | 384708 | 95% | 381863 | -17277 | -4.524% | 460908.559 | -96322.559 | -20.9%
CA: Manteca - KP Manteca Hospital | CA | 121118.59 | 126381 | 96% | 0 | 121118.59 |  | 112726.728 | 8391.862 | 7.444%

## Jun
CITI |  |  | PPA Modeled Output | Production VS Acual | Q2 Production Vs PPA | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 2463183.5 | 2847462 | 87% | 89% | 2641284.516 | -178101.016 | -6.743% | 2773309.107 | -310125.607 | -11.18% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual |  |  |  | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA | 80694.75 | 76877 | 105% | 102% | 76499 | 4195.75 | 5.485% | 80283.123 | 411.627 | 0.5127%
CA: Antioch MC CUP - Citi | CA | 262899.5 | 262669 | 100% | 102.6% | 261352 | 1547.5 | 0.5921% | 275617.885 | -12718.385 | -4.614%
CA: Clovis - Citi | CA | 110568 | 114359 | 97% | 99.03% | 111525 | -957 | -0.8581% | 111243.93 | -675.93 | -0.6076%
CA: Elk Grove MOB - Citi | CA | 157485.5 | 182422 | 86% | 95.64% | 181524 | -24038.5 | -13.24% | 183908 | -26422.5 | -14.37% | 1. Inverters 5.1 & 5.2 tripped offline due to ground fault at 10:40 on 06/06. Inverters 5.1 & 5.2 again tripped offline at 12:15 on 06/30 and is still offline | 1. SR087140, SR085709, SR085708
CA: Elk Grove Promenade - Citi | CA | 88507.75 | 95644 | 93% | 95.44% | 95172.516 | -6664.766 | -7.003% | 95004.316 | -6496.566 | -6.838%
CA: Fresno Sequioa - Citi | CA | 180119.25 | 187953 | 96% | 98.85% | 187066 | -6946.75 | -3.714% | 189019.541 | -8900.291 | -4.709%
CA: Fresno MOB - Citi | CA | 68059.87 | 75912 | 90% | 94.51% | 76399 | -8339.13 | -10.92% | 71704.213 | -3644.343 | -5.082% | 1. Inverter 3 tripped offline on are fault at 17:30 on 06/19 and back online at 10:25 on 06/24 2. Inverter 1 & 4 tripped offline at 16:20 on 06/24 and back online the next day | 1. SR086466 2. SR086881
CA: Modesto Bangs - Citi | CA | 45253.38 | 54773 | 83% | 84.95% | 54780 | -9526.62 | -17.39% | 46359.14 | -1105.76 | -2.385% | 1. Inverter 1 having heavy evening shading based on previous history | 1. SR085819
CA: Napa Data Center - Citi | CA | 47603.87 | 54497 | 87% | 83.55% | 52986 | -5382.13 | -10.16% | 54599.736 | -6995.866 | -12.81% | 1. Site tripped offline at 16:50 on 06/29 due to utility outage and was reenergized at 14:10 on 07/03 | 1. SR087130
CA: Petaluma MOB - Citi | CA | 113623 | 124350 | 91% | 92.15% | 120264 | -6641 | -5.522% | 64628.465 | 48994.535 | 75.81% | 1. Weather station reporting errenous values from 06/08 due to vehicle strike. 2. Inverter 3 is offline from 06/19 | 1. SR086110 2. SR086446
CA: Pleasanton Tec Ctr - Citi | CA | 51641 | 176505 | 29% | 63.03% | 175737 | -124096 | -70.61% | 181415.657 | -129774.657 | -71.53% | 1. Site was offline from 05/28 and was renergized at 13:50 on 06/21 | 1. SR085283
CA: Rancho Cordova - Citi | CA | 232957.5 | 236948 | 98% | 99.85% | 236713 | -3755.5 | -1.587% | 246798.376 | -13840.876 | -5.608%
CA: S Sacramento Wyndham - Citi | CA | 148719.5 | 158605 | 94% | 96.37% | 158302 | -9582.5 | -6.053% | 149664.247 | -944.747 | -0.6312%
CA: Sacramento Point West - Citi | CA | 266046.5 | 302720 | 88% | 90.2% | 301798 | -35751.5 | -11.85% | 305914.578 | -39868.078 | -13.03% | 1. Inverter 5.5 is still offline | 1. SR081815
CA: San Jose FHC - Citi | CA |  | 60463 | 0% | 16.58% | -
CA: San Jose MOB - Citi | CA | 84360 | 95898 | 88% | 91.34% | 97202 | -12842 | -13.21% | 98563.369 | -14203.369 | -14.41%
CA: Selma - Citi | CA | 52894.25 | 58141 | 91% | 95.66% | 57976 | -5081.75 | -8.765% | 58119.135 | -5224.885 | -8.99%
CA: Vacaville Hospital | CA | 358022 | 398845 | 90% | 92.82% | 395989 | -37967 | -9.588% | 449936.477 | -91914.477 | -20.43%
CA: Manteca - KP Manteca Hospital | CA | 113727.88 | 129883 | 88% | 91.74% | 0 | 113727.88 |  | 110528.919 | 3198.961 | 2.894% | 1. Expected value is unavailable

## Jul
CITI |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA
CA: Antioch MC CUP - Citi | CA
CA: Clovis - Citi | CA
CA: Elk Grove MOB - Citi | CA
CA: Elk Grove Promenade - Citi | CA
CA: Fresno Sequioa - Citi | CA
CA: Fresno MOB - Citi | CA
CA: Modesto Bangs - Citi | CA
CA: Napa Data Center - Citi | CA
CA: Petaluma MOB - Citi | CA
CA: Pleasanton Tec Ctr - Citi | CA
CA: Rancho Cordova - Citi | CA
CA: S Sacramento Wyndham - Citi | CA
CA: Sacramento Point West - Citi | CA
CA: San Jose FHC - Citi | CA
CA: San Jose MOB - Citi | CA
CA: Selma - Citi | CA
CA: Vacaville Hospital | CA
CA: Manteca - KP Manteca Hospital | CA

## Aug
CITI |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA
CA: Antioch MC CUP - Citi | CA
CA: Clovis - Citi | CA
CA: Elk Grove MOB - Citi | CA
CA: Elk Grove Promenade - Citi | CA
CA: Fresno Sequioa - Citi | CA
CA: Fresno MOB - Citi | CA
CA: Modesto Bangs - Citi | CA
CA: Napa Data Center - Citi | CA
CA: Petaluma MOB - Citi | CA
CA: Pleasanton Tec Ctr - Citi | CA
CA: Rancho Cordova - Citi | CA
CA: S Sacramento Wyndham - Citi | CA
CA: Sacramento Point West - Citi | CA
CA: San Jose FHC - Citi | CA
CA: San Jose MOB - Citi | CA
CA: Selma - Citi | CA
CA: Vacaville Hospital | CA
CA: Manteca - KP Manteca Hospital | CA

## Sep
CITI |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA
CA: Antioch MC CUP - Citi | CA
CA: Clovis - Citi | CA
CA: Elk Grove MOB - Citi | CA
CA: Elk Grove Promenade - Citi | CA
CA: Fresno Sequioa - Citi | CA
CA: Fresno MOB - Citi | CA
CA: Modesto Bangs - Citi | CA
CA: Napa Data Center - Citi | CA
CA: Petaluma MOB - Citi | CA
CA: Pleasanton Tec Ctr - Citi | CA
CA: Rancho Cordova - Citi | CA
CA: S Sacramento Wyndham - Citi | CA
CA: Sacramento Point West - Citi | CA
CA: San Jose FHC - Citi | CA
CA: San Jose MOB - Citi | CA
CA: Selma - Citi | CA
CA: Vacaville Hospital | CA
CA: Manteca - KP Manteca Hospital | CA

## Oct
CITI |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA
CA: Antioch MC CUP - Citi | CA
CA: Clovis - Citi | CA
CA: Elk Grove MOB - Citi | CA
CA: Elk Grove Promenade - Citi | CA
CA: Fresno Sequioa - Citi | CA
CA: Fresno MOB - Citi | CA
CA: Modesto Bangs - Citi | CA
CA: Napa Data Center - Citi | CA
CA: Petaluma MOB - Citi | CA
CA: Pleasanton Tec Ctr - Citi | CA
CA: Rancho Cordova - Citi | CA
CA: S Sacramento Wyndham - Citi | CA
CA: Sacramento Point West - Citi | CA
CA: San Jose FHC - Citi | CA
CA: San Jose MOB - Citi | CA
CA: Selma - Citi | CA
CA: Vacaville Hospital | CA
CA: Manteca - KP Manteca Hospital | CA

## Nov
CITI |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA
CA: Antioch MC CUP - Citi | CA
CA: Clovis - Citi | CA
CA: Elk Grove MOB - Citi | CA
CA: Elk Grove Promenade - Citi | CA
CA: Fresno Sequioa - Citi | CA
CA: Fresno MOB - Citi | CA
CA: Modesto Bangs - Citi | CA
CA: Napa Data Center - Citi | CA
CA: Petaluma MOB - Citi | CA
CA: Pleasanton Tec Ctr - Citi | CA
CA: Rancho Cordova - Citi | CA
CA: S Sacramento Wyndham - Citi | CA
CA: Sacramento Point West - Citi | CA
CA: San Jose FHC - Citi | CA
CA: San Jose MOB - Citi | CA
CA: Selma - Citi | CA
CA: Vacaville Hospital | CA
CA: Manteca - KP Manteca Hospital | CA

## Dec
CITI |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CA: Antioch Deer Valley - Citi | CA
CA: Antioch MC CUP - Citi | CA
CA: Clovis - Citi | CA
CA: Elk Grove MOB - Citi | CA
CA: Elk Grove Promenade - Citi | CA
CA: Fresno Sequioa - Citi | CA
CA: Fresno MOB - Citi | CA
CA: Modesto Bangs - Citi | CA
CA: Napa Data Center - Citi | CA
CA: Petaluma MOB - Citi | CA
CA: Pleasanton Tec Ctr - Citi | CA
CA: Rancho Cordova - Citi | CA
CA: S Sacramento Wyndham - Citi | CA
CA: Sacramento Point West - Citi | CA
CA: San Jose FHC - Citi | CA
CA: San Jose MOB - Citi | CA
CA: Selma - Citi | CA
CA: Vacaville Hospital | CA
CA: Manteca - KP Manteca Hospital | CA

## Sites
Portfolio: | CITI
Site DAS Name | Site | State | Update | DAS
KP6 - Antioch Deer Valley - CN5701 | CA: Antioch Deer Valley - Citi | CA
KP6 - Antioch MC CUP - CN5701 | CA: Antioch MC CUP - Citi | CA
Clovis MOB | CA: Clovis - Citi | CA
Elk Grove MOB - CN73727 | CA: Elk Grove MOB - Citi | CA
Elk Grove Promenade - CN 6950 | CA: Elk Grove Promenade - Citi | CA
Fresno Sequioa Hospital | CA: Fresno Sequioa - Citi | CA
Fresno Medical Offices - CN7201 | CA: Fresno MOB - Citi | CA
Modesto Bangs MOB | CA: Modesto Bangs - Citi | CA
KP - Napa Data Center - CN2250 | CA: Napa Data Center - Citi | CA
Kaiser - Petaluma Medical Office - CN2001 | CA: Petaluma MOB - Citi | CA
Pleasanton PTC - Bldg B - CN470B | CA: Pleasanton Tec Ctr - Citi | CA
Rancho Cordova - Groundmount | CA: Rancho Cordova - Citi | CA
South Sacramento Wyndham CN6014 | CA: S Sacramento Wyndham - Citi | CA
Sacramento Point West MOB | CA: Sacramento Point West - Citi | CA
KP6 - San Jose FHC - CN6320 | CA: San Jose FHC - Citi | CA
KP6 - San Jose MOB - CN6310 | CA: San Jose MOB - Citi | CA
KP6 - Selma Medical Offices - CN8450 | CA: Selma - Citi | CA
Vacaville Hospital - CN6701 | CA: Vacaville Hospital | CA
Kaiser, KP6 - Manteca Hospital | CA: Manteca - KP Manteca Hospital | CA