## Year to Date
Pardee (ENCAP) |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 1077567.085 | 1047604.321 | 29962.764 | 2.86% | 1086830.607 | -9263.522 | -0.8523%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 52104.25 | 39687.526 | 12416.724 | 31.29% | 23861.518 | -7679.118 | -32.18%
AZ: ASU - Pardee - Farrington | AZ | 79124.25 | 82629.24 | -3504.99 | -4.242% | 88617.24 | -9492.99 | -10.71%
AZ: ASU - Pardee - Macro Tech. | AZ | 327405.46 | 316275.55 | 11129.91 | 3.519% | 320574.62 | 6830.84 | 2.131%
AZ: ASU - Pardee - McCord Hall | AZ | 28351.625 | 22846.845 | 5504.78 | 24.09% | 32212.949 | -3861.324 | -11.99%
AZ: NAU - SF Garage | AZ | 129718 | 165052.46 | -35334.46 | -21.41% | 169927.38 | -40209.38 | -23.66%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 53898.3125 | 55837.33 | -1939.0175 | -3.473% | 44156.45 | 9741.8625 | 22.06%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 90107.125 | 82892.33 | 7214.795 | 8.704% | 65384.51 | 24722.615 | 37.81%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 73359.875 | 68314.85 | 5045.025 | 7.385% | 79364.49 | -6004.615 | -7.566%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 73943 | 65451.34 | 8491.66 | 12.97% | 83298.18 | -9355.18 | -11.23%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 88325.1875 | 71483.51 | 16841.6775 | 23.56% | 91107.27 | -2782.0825 | -3.054%
AZ: ASU - Pardee - Sun Devil Complex | AZ | 81230 | 77133.34 | 4096.66 | 5.311% | 88326 | -7096 | -8.034%

## 1st Qtr
Pardee (ENCAP) |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 1046494.21 | 1025165.435 | 21328.775 | 2.081% | 1086830.607 | -40336.397 | -3.711%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 21031.375 | 17248.64 | 3782.735 | 21.93% | 23861.518 | -2830.143 | -11.86%
AZ: ASU - Pardee - Farrington | AZ | 79124.25 | 82629.24 | -3504.99 | -4.242% | 88617.24 | -9492.99 | -10.71%
AZ: ASU - Pardee - Macro Tech. | AZ | 327405.46 | 316275.55 | 11129.91 | 3.519% | 320574.62 | 6830.84 | 2.131%
AZ: ASU - Pardee - McCord Hall | AZ | 28351.625 | 22846.845 | 5504.78 | 24.09% | 32212.949 | -3861.324 | -11.99%
AZ: NAU - SF Garage | AZ | 129718 | 165052.46 | -35334.46 | -21.41% | 169927.38 | -40209.38 | -23.66%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 53898.3125 | 55837.33 | -1939.0175 | -3.473% | 44156.45 | 9741.8625 | 22.06%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 90107.125 | 82892.33 | 7214.795 | 8.704% | 65384.51 | 24722.615 | 37.81%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 73359.875 | 68314.85 | 5045.025 | 7.385% | 79364.49 | -6004.615 | -7.566%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 73943 | 65451.34 | 8491.66 | 12.97% | 83298.18 | -9355.18 | -11.23%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 88325.1875 | 71483.51 | 16841.6775 | 23.56% | 91107.27 | -2782.0825 | -3.054%
AZ: ASU - Pardee - Sun Devil Complex | AZ | 81230 | 77133.34 | 4096.66 | 5.311% | 88326 | -7096 | -8.034%

## 2nd Qtr
Pardee (ENCAP) |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 1586107.75 | 1518952.667 | 67155.083 | 4.421% | 0 | 1586107.75 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 31072.875 | 22438.886 | 8633.989 | 38.48% |  | -4848.975
AZ: ASU - Pardee - Farrington | AZ | 93292.25 | 121646.69 | -28354.44 | -23.31% |  | -43165.88
AZ: ASU - Pardee - Macro Tech. | AZ | 471176.75 | 457543.4 | 13633.35 | 2.98% |  | -28810.95
AZ: ASU - Pardee - McCord Hall | AZ | 41733.875 | 38280.25 | 3453.625 | 9.022% |  | -6760.825
AZ: NAU - SF Garage | AZ | 312344 | 291114.131 | 21229.869 | 7.293% |  | 17268.561
AZ: ASU - Pardee - Parking Lot 11 | AZ | 88645.875 | 88177.39 | 468.485 | 0.5313% |  | -1338.555
AZ: ASU - Pardee - Parking Lot 19 | AZ | 118986.75 | 108655.46 | 10331.29 | 9.508% |  | -14257.83
AZ: ASU - Pardee - Parking Lot 41 | AZ | 114045.25 | 99690.01 | 14355.24 | 14.4% |  | -8168.71
AZ: ASU - Pardee - Parking Lot 58 | AZ | 86248.125 | 84131.47 | 2116.655 | 2.516% |  | -39150.665
AZ: ASU - Pardee - Parking Lot 59S | AZ | 104839 | 91869.42 | 12969.58 | 14.12% |  | -32317.18
AZ: ASU - Pardee - Sun Devil Complex | AZ | 123723 | 115405.56 | 8317.44 | 7.207% |  | -7161

## 3rd Qtr
Pardee (ENCAP) |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Farrington | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Macro Tech. | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - McCord Hall | AZ | 0 | 0 | 0 |  |  | 0
AZ: NAU - SF Garage | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 11 | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 19 | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 41 | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 58 | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 59S | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Sun Devil Complex | AZ | 0 | 0 | 0 |  |  | 0

## 4th Qtr
Pardee (ENCAP) |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Farrington | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Macro Tech. | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - McCord Hall | AZ | 0 | 0 | 0 |  |  | 0
AZ: NAU - SF Garage | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 11 | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 19 | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 41 | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 58 | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Parking Lot 59S | AZ | 0 | 0 | 0 |  |  | 0
AZ: ASU - Pardee - Sun Devil Complex | AZ | 0 | 0 | 0 |  |  | 0

## Jan
Pardee (ENCAP) |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 286603.185 | 276538.334 | 10064.851 | 3.64% | 295333.301 | -8730.116 | -2.956%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ | 5658.375 | 4288.239 | 1370.136 | 31.95% | 6613.612 | -955.237 | -14.44%
AZ: ASU - Pardee - Farrington | AZ | 20942.75 | 22485.91 | -1543.16 | -6.863% | 24320.71 | -3377.96 | -13.89%
AZ: ASU - Pardee - Macro Tech. | AZ | 93471.06 | 84624.65 | 8846.41 | 10.45% | 90296.56 | 3174.5 | 3.516% | 1. Inverter 6 tripped offline on 01/08/2024 & back online on 01/17/2024 | 1. SR080052
AZ: ASU - Pardee - McCord Hall | AZ | 7336.125 | 5808.405 | 1527.72 | 26.3% | 8928.859 | -1592.734 | -17.84% | 1. Inverter tripped offline on 01/01/2024 at 14:15 & back online 01/03/2024 at 11:15 AM. | 1. SR079868
AZ: NAU - SF Garage | AZ | 37150 | 48177.46 | -11027.46 | -22.89% | 44269.38 | -7119.38 | -16.08%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 17337.5 | 14798.45 | 2539.05 | 17.16% | 10357.79 | 6979.71 | 67.39%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 24207.75 | 22732.63 | 1475.12 | 6.489% | 15337.79 | 8869.96 | 57.83%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 18216.6875 | 18371.14 | -154.4525 | -0.8407% | 21781.47 | -3564.7825 | -16.37%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 18853.625 | 16485.98 | 2367.645 | 14.36% | 23088.75 | -4235.125 | -18.34%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 23961.8125 | 18005.49 | 5956.3225 | 33.08% | 25253.38 | -1291.5675 | -5.114%
AZ: ASU - Pardee - Sun Devil Complex | AZ | 19467.5 | 20759.98 | -1292.48 | -6.226% | 25085 | -5617.5 | -22.39%

## Feb
Pardee (ENCAP) |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 309680 | 316895.792 | -7215.792 | -2.277% | 338232.721 | -28552.721 | -8.442%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ | 6617 | 5438.898 | 1178.102 | 21.66% | 7532.451 | -915.451 | -12.15%
AZ: ASU - Pardee - Farrington | AZ | 24988 | 25880.78 | -892.78 | -3.45% | 27910.12 | -2922.12 | -10.47%
AZ: ASU - Pardee - Macro Tech. | AZ | 98495.5 | 100242 | -1746.5 | -1.742% | 97496.26 | 999.24 | 1.025% | 1. Inverter 2 tripped offline on 02/05 and back online on 02/07 2. Inverter 5 tripped offline on 02/09 and back online on 02/13 3. Inverter 3 tripped offline on 02/17 and back online on 02/21 | 1. SR080747 2. SR080903 3. SR081078
AZ: ASU - Pardee - McCord Hall | AZ | 9062.25 | 7131.944 | 1930.306 | 27.07% | 10168.08 | -1105.83 | -10.88%
AZ: NAU - SF Garage | AZ | 29342 | 45707 | -16365 | -35.8% | 54628 | -25286 | -46.29%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 10468.9375 | 17416.29 | -6947.3525 | -39.89% | 13455.15 | -2986.2125 | -22.19% | 1. Inverter 2 is offline from 02/07 to 03/02. | 1. SR080834
AZ: ASU - Pardee - Parking Lot 19 | AZ | 28505.375 | 26099.84 | 2405.535 | 9.217% | 19923.12 | 8582.255 | 43.08%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 23220.6875 | 21480.82 | 1739.8675 | 8.1% | 24995.58 | -1774.8925 | -7.101%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 23236.5 | 20660.42 | 2576.08 | 12.47% | 26294.57 | -3058.07 | -11.63%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 27805.25 | 22564.69 | 5240.56 | 23.22% | 28759.39 | -954.14 | -3.318%
AZ: ASU - Pardee - Sun Devil Complex | AZ | 27938.5 | 24273.11 | 3665.39 | 15.1% | 27070 | 868.5 | 3.208% | 1. Inverter 2 tripped offline on 02/05 and back online on 02/07 | 1.SR080750

## Mar
Pardee (ENCAP) |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 450211.025 | 431731.309 | 18479.716 | 4.28% | 453264.585 | -3053.56 | -0.6737%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ | 8756 | 7521.503 | 1234.497 | 16.41% | 9715.455 | -959.455 | -9.876%
AZ: ASU - Pardee - Farrington | AZ | 33193.5 | 34262.55 | -1069.05 | -3.12% | 36386.41 | -3192.91 | -8.775%
AZ: ASU - Pardee - Macro Tech. | AZ | 135438.9 | 131408.9 | 4030 | 3.067% | 132781.8 | 2657.1 | 2.001%
AZ: ASU - Pardee - McCord Hall | AZ | 11953.25 | 9906.496 | 2046.754 | 20.66% | 13116.01 | -1162.76 | -8.865%
AZ: NAU - SF Garage | AZ | 63226 | 71168 | -7942 | -11.16% | 71030 | -7804 | -10.99%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 26091.875 | 23622.59 | 2469.285 | 10.45% | 20343.51 | 5748.365 | 28.26% | 1. Inverter 2 tripped offline on 03/31 and back online on 04/0 | 1.SR082951
AZ: ASU - Pardee - Parking Lot 19 | AZ | 37394 | 34059.86 | 3334.14 | 9.789% | 30123.6 | 7270.4 | 24.14%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 31922.5 | 28462.89 | 3459.61 | 12.15% | 32587.44 | -664.94 | -2.04%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 31852.875 | 28304.94 | 3547.935 | 12.53% | 33914.86 | -2061.985 | -6.08%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 36558.125 | 30913.33 | 5644.795 | 18.26% | 37094.5 | -536.375 | -1.446%
AZ: ASU - Pardee - Sun Devil Complex | AZ | 33824 | 32100.25 | 1723.75 | 5.37% | 36171 | -2347 | -6.489% | 1. Inverter 2 tripped offline on 03/05 and back online on 03/07 2. Inverter 1 tripped offline on 03/18 and back online 03/19 and again tripped offline on 03/30 and back online on 04/01 | 1. SR081586 2. SR082015

## Apr
Pardee (ENCAP) |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 553626.5 | 514831.284 | 38795.216 | 7.536% | 547175.267 | 6451.233 | 1.179%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ | 10336.375 | 8889.935 | 1446.44 | 16.27% | 11446.07 | -1109.695 | -9.695%
AZ: ASU - Pardee - Farrington | AZ | 38575.5 | 40498.67 | -1923.17 | -4.749% | 43228.93 | -4653.43 | -10.76%
AZ: ASU - Pardee - Macro Tech. | AZ | 159318.5 | 152391.5 | 6927 | 4.546% | 158586.5 | 732 | 0.4616%
AZ: ASU - Pardee - McCord Hall | AZ | 13983.625 | 12220.19 | 1763.435 | 14.43% | 15452.68 | -1469.055 | -9.507%
AZ: NAU - SF Garage | AZ | 95855 | 93292.369 | 2562.631 | 2.747% | 87917.557 | 7937.443 | 9.028%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 30431.0625 | 28336.31 | 2094.7525 | 7.392% | 26741.57 | 3689.4925 | 13.8%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 42655.875 | 37947.77 | 4708.105 | 12.41% | 39596.47 | 3059.405 | 7.726% | 1. Inverter 2 is underperforming 25kW compared to peer from 04/25 | 1. SR083890
AZ: ASU - Pardee - Parking Lot 41 | AZ | 37998.4375 | 33340.2 | 4658.2375 | 13.97% | 38716.08 | -717.6425 | -1.854%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 38145.875 | 33222.99 | 4922.885 | 14.82% | 39958.08 | -1812.205 | -4.535%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 42865.25 | 36282.89 | 6582.36 | 18.14% | 43704.33 | -839.08 | -1.92%
AZ: ASU - Pardee - Sun Devil Complex | AZ | 43461 | 38408.46 | 5052.54 | 13.15% | 41827 | 1634 | 3.907%

## May
Pardee (ENCAP) |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 584242 | 546539.435 | 37702.565 | 6.898% | 614447.549 | -30205.549 | -4.916%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ | 10966.125 | 9032.255 | 1933.87 | 21.41% | 12566.22 | -1600.095 | -12.73%
AZ: ASU - Pardee - Farrington | AZ | 35131.75 | 43013.36 | -7881.61 | -18.32% | 47795.39 | -12663.64 | -26.5% | 1. Inverter 1 was tripping on and off throughout the month. Inverter 1 tripped offline at 14:45 on 05/23 and back online at 08:30 on 05/31 | 1. SR084986
AZ: ASU - Pardee - Macro Tech. | AZ | 167658.875 | 161980.4 | 5678.475 | 3.506% | 172647.9 | -4989.025 | -2.89% | 1. Inverters 5 and 6 are derating during peak hours from 05/28 possibly due to fan wassue | 1. SR085334
AZ: ASU - Pardee - McCord Hall | AZ | 14700.25 | 13602.63 | 1097.62 | 8.069% | 16964.45 | -2264.2 | -13.35%
AZ: NAU - SF Garage | AZ | 111753 | 102747.23 | 9005.77 | 8.765% | 105502.259 | 6250.741 | 5.925%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 31725.75 | 31574.55 | 151.2 | 0.4789% | 31935.57 | -209.82 | -0.657% | 1. Inverter 2 was derating during peak hours from 05/13 | 1. SR085328
AZ: ASU - Pardee - Parking Lot 19 | AZ | 40541.75 | 37630.74 | 2911.01 | 7.736% | 47289.36 | -6747.61 | -14.27% | 1. Inverter 2 was underperforming 25kW compared to peer from 04/25 | 1. SR083890
AZ: ASU - Pardee - Parking Lot 41 | AZ | 40387.75 | 35002.89 | 5384.86 | 15.38% | 42806.31 | -2418.56 | -5.65%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 39734.25 | 33905.28 | 5828.97 | 17.19% | 43866.59 | -4132.34 | -9.42% | 1. Inverter 1 was tripping on and off on 05/15,05/29,05/30. Inverter 1 tripped offline at 14:00 on 05/31 | 1. SR085389
AZ: ASU - Pardee - Parking Lot 59S | AZ | 45335 | 37022.39 | 8312.61 | 22.45% | 47979.5 | -2644.5 | -5.512%
AZ: ASU - Pardee - Sun Devil Complex | AZ | 46307.5 | 41027.71 | 5279.79 | 12.87% | 45094 | 1213.5 | 2.691%

## Jun
Pardee (ENCAP) |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 448239.25 | 457581.948 | -9342.698 | -2.042% | 593196.943 | -144957.693 | -24.44%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ | 9770.375 | 4516.696 | 5253.679 | 116.3% | 11909.56 | -2139.185 | -17.96% | 1. Weather station stopped reporting at 08:19 on 06/19 due to that expected value was low | 1. SR087515
AZ: ASU - Pardee - Farrington | AZ | 19585 | 38134.66 | -18549.66 | -48.64% | 45433.81 | -25848.81 | -56.89% | 1. Inverter 1 tripped offline at 11:30 on 06/03 and was offline throughout the month | 1. SR085515
AZ: ASU - Pardee - Macro Tech. | AZ | 144199.375 | 143171.5 | 1027.875 | 0.7179% | 168753.3 | -24553.925 | -14.55% | 1. Inverters 5 and 6 are derating during peak hours whole month possibly due to fan wassue | 1. SR085334
AZ: ASU - Pardee - McCord Hall | AZ | 13050 | 12457.43 | 592.57 | 4.757% | 16077.57 | -3027.57 | -18.83%
AZ: NAU - SF Garage | AZ | 104736 | 95074.532 | 9661.468 | 10.16% | 101655.623 | 3080.377 | 3.03%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 26489.0625 | 28266.53 | -1777.4675 | -6.288% | 31307.29 | -4818.2275 | -15.39%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 35789.125 | 33076.95 | 2712.175 | 8.2% | 46358.75 | -10569.625 | -22.8% | 1. Inverter 2 was underperforming 25kW compared to peer from 04/25 | 1. SR083890
AZ: ASU - Pardee - Parking Lot 41 | AZ | 35659.0625 | 31346.92 | 4312.1425 | 13.76% | 40691.57 | -5032.5075 | -12.37%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 8368 | 17003.2 | -8635.2 | -50.79% | 41574.12 | -33206.12 | -79.87% | 1. Site stopped communicating from 06/19 at 05:00, possibly offline 2. Inverter 1 was offline from 05/30 and came back online on 06/14. Inverter again offline from 06/16 and was still offline | 1. SR086425 2. SR085389
AZ: ASU - Pardee - Parking Lot 59S | AZ | 16638.75 | 18564.14 | -1925.39 | -10.37% | 45472.35 | -28833.6 | -63.41% | 1. Site stopped communicating from 06/19 at 05:00, possibly offline | 1. SR086426
AZ: ASU - Pardee - Sun Devil Complex | AZ | 33954.5 | 35969.39 | -2014.89 | -5.602% | 43963 | -10008.5 | -22.77% | 1. Inverter 2 tripped offline at 08:00 on 06/12 and back online at 11:00 on 06/21 | 1. SR086086

## Jul
Pardee (ENCAP) |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Aug
Pardee (ENCAP) |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Sep
Pardee (ENCAP) |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Oct
Pardee (ENCAP) |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Nov
Pardee (ENCAP) |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Dec
Pardee (ENCAP) |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Sites
Portfolio: | Pardee (ENCAP)
Site DAS Name | Site | State | Update | DAS
AZ: ASU - Pardee - Discovery Hall | AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ: ASU - Pardee - Sun Devil Complex | AZ