## Quarterly
Frederick NMWDA
Actual vs. Expected |  |  |  |  | Actual vs. Forecasted
Quarter | Actual | Expected | Delta Expected | % Expected | Forecasted | Delta Forecasted | % Forecasted
1st Quarter | 265710 | 0 | 265710 | 0% | 0 | 265710 | 0%
2nd Quarter | 0 | 0 | 0 | 0% | 0 | 0 | 0%
3rd Quarter | 0 | 0 | 0 | 0% | 0 | 0 | 0%
4th Quarter | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Year to Date | 265710 | 0 | 265710 | 0% | 0 | 265710 | 0%

## Monthly
Frederick NMWDA
Actual vs. Expected |  |  |  |  | Actual vs. Forecasted |  |  | Notes
Month | Actual | Expected | Delta Expected | % Expected | Forecasted | Delta Forecasted | % Forecasted | Notes | Service Request
Jan | 46371 | 0 | 46371 | 0% | 0 | 46371 | 0% | 1. Inverter 5 was offline on 01/13 and back online at 15:00 on 01/13 2. Inverter 14 was offline from 01/24 to 01/31 3. Site was offline from 01/22 to 01/24 | 1. SR078692 2. SR080505 3. SR080380
Feb | 108403 |  | 108403 | 0% |  | 108403 | 0% | 1. Inverter 14 is offline and reporting Ground Fault Isolation Resistance Low on 02/22 and back online on 02/23 2. Inverter 5, 8, 16, 13 are being RMA'd. | 1. SR081194 2. SR081343
Mar | 110936 | 0 | 110936 | 0% | 0 | 110936 | 0% | 2. Inverter 5, 8, 16, 13 are RMA'd. | 2. SR081343
Apr |  |  | 0 | 0% |  | 0 | 0%
May |  |  | 0 | 0% |  | 0 | 0%
Jun |  |  | 0 | 0% |  | 0 | 0%
Jul |  |  | 0 | 0% |  | 0 | 0%
Aug |  |  | 0 | 0% |  | 0 | 0%
Sep |  |  | 0 | 0% |  | 0 | 0%
Oct |  |  | 0 | 0% |  | 0 | 0%
Nov |  |  | 0 | 0% |  | 0 | 0%
Dec |  |  | 0 | 0% |  | 0 | 0%
Totals | 265710 | 0 | 265710 | 0% | 0 | 265710 | 0%