## Year to Date
MN8 KEF |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 5061899.0399 | 5742936.91 | -681037.8701 | -11.86% | 6132609.53 | -1070710.4901 | -17.46%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Williamsburg A | MA | 299514.0943 | 343331.74 | -43817.6457 | -12.76% | 358213.49 | -58699.3957 | -16.39%
Orange A KB | MA | 247279.6957 | 258904.45 | -11624.7543 | -4.49% | 298151.89 | -50872.1943 | -17.06%
Goshen A | MA | 261845 | 308555.5 | -46710.5 | -15.14% | 191088.16 | 70756.84 | 37.03%
Phillipston A KB | MA | 282267 | 395445.18 | -113178.18 | -28.62% | 218309.68 | 63957.32 | 29.3%
Uxbridge D | MA | 312227 | 356457.4 | -44230.4 | -12.41% | 390177.4 | -77950.4 | -19.98%
West Bridgewater A&B | MA | 493322 | 566022.2 | -72700.2 | -12.84% | 639439.2 | -146117.2 | -22.85%
Sutton A | MA | 251473 | 302395.95 | -50922.95 | -16.84% | 361333.32 | -109860.32 | -30.4%
North Adams A | MA | 258785 | 294516.74 | -35731.74 | -12.13% | 363705.86 | -104920.86 | -28.85%
North Adams B | MA | 241080 | 254351.53 | -13271.53 | -5.218% | 363705.86 | -122625.86 | -33.72%
Clarksburg A | MA | 253576 | 280640.43 | -27064.43 | -9.644% | 362052.99 | -108476.99 | -29.96%
Swansea B | MA | 318674 | 361411.34 | -42737.34 | -11.83% | 218954.31 | 99719.69 | 45.54%
Wareham 2 | MA | 271754.25 | 287011.73 | -15257.48 | -5.316% | 395554.7 | -123800.45 | -31.3%
Kingston 1 KB | MA | 246362 | 280103.39 | -33741.39 | -12.05% | 297310.99 | -50948.99 | -17.14%
Kingston 2 KB | MA | 205192 | 180108.57 | 25083.43 | 13.93% | 238641.77 | -33449.77 | -14.02%
Holliston B | MA | 281743 | 324177.82 | -42434.82 | -13.09% | 379539.77 | -97796.77 | -25.77%
Fairhaven C | MA | 542636 | 619098.5 | -76462.5 | -12.35% | 678228.9 | -135592.9 | -19.99%
Plympton A-2 | MA | 294169 | 330404.44 | -36235.44 | -10.97% | 378201.24 | -84032.24 | -22.22%

## 1st Qtr
MN8 KEF |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 5061899.0399 | 5742936.91 | -681037.8701 | -11.86% | 6132609.53 | -1070710.4901 | -17.46%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Williamsburg A | MA | 299514.0943 | 343331.74 | -43817.6457 | -12.76% | 358213.49 | -58699.3957 | -16.39%
Orange A KB | MA | 247279.6957 | 258904.45 | -11624.7543 | -4.49% | 298151.89 | -50872.1943 | -17.06%
Goshen A | MA | 261845 | 308555.5 | -46710.5 | -15.14% | 191088.16 | 70756.84 | 37.03%
Phillipston A KB | MA | 282267 | 395445.18 | -113178.18 | -28.62% | 218309.68 | 63957.32 | 29.3%
Uxbridge D | MA | 312227 | 356457.4 | -44230.4 | -12.41% | 390177.4 | -77950.4 | -19.98%
West Bridgewater A&B | MA | 493322 | 566022.2 | -72700.2 | -12.84% | 639439.2 | -146117.2 | -22.85%
Sutton A | MA | 251473 | 302395.95 | -50922.95 | -16.84% | 361333.32 | -109860.32 | -30.4%
North Adams A | MA | 258785 | 294516.74 | -35731.74 | -12.13% | 363705.86 | -104920.86 | -28.85%
North Adams B | MA | 241080 | 254351.53 | -13271.53 | -5.218% | 363705.86 | -122625.86 | -33.72%
Clarksburg A | MA | 253576 | 280640.43 | -27064.43 | -9.644% | 362052.99 | -108476.99 | -29.96%
Swansea B | MA | 318674 | 361411.34 | -42737.34 | -11.83% | 218954.31 | 99719.69 | 45.54%
Wareham 2 | MA | 271754.25 | 287011.73 | -15257.48 | -5.316% | 395554.7 | -123800.45 | -31.3%
Kingston 1 KB | MA | 246362 | 280103.39 | -33741.39 | -12.05% | 297310.99 | -50948.99 | -17.14%
Kingston 2 KB | MA | 205192 | 180108.57 | 25083.43 | 13.93% | 238641.77 | -33449.77 | -14.02%
Holliston B | MA | 281743 | 324177.82 | -42434.82 | -13.09% | 379539.77 | -97796.77 | -25.77%
Fairhaven C | MA | 542636 | 619098.5 | -76462.5 | -12.35% | 678228.9 | -135592.9 | -19.99%
Plympton A-2 | MA | 294169 | 330404.44 | -36235.44 | -10.97% | 378201.24 | -84032.24 | -22.22%

## 2nd Qtr
MN8 KEF |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Williamsburg A | MA | 0 | 0 | 0 |  |  | 0
Orange A KB | MA | 0 | 0 | 0 |  |  | 0
Goshen A | MA | 0 | 0 | 0 |  |  | 0
Phillipston A KB | MA | 0 | 0 | 0 |  |  | 0
Uxbridge D | MA | 0 | 0 | 0 |  |  | 0
West Bridgewater A&B | MA | 0 | 0 | 0 |  |  | 0
Sutton A | MA | 0 | 0 | 0 |  |  | 0
North Adams A | MA | 0 | 0 | 0 |  |  | 0
North Adams B | MA | 0 | 0 | 0 |  |  | 0
Clarksburg A | MA | 0 | 0 | 0 |  |  | 0
Swansea B | MA | 0 | 0 | 0 |  |  | 0
Wareham 2 | MA | 0 | 0 | 0 |  |  | 0
Kingston 1 KB | MA | 0 | 0 | 0 |  |  | 0
Kingston 2 KB | MA | 0 | 0 | 0 |  |  | 0
Holliston B | MA | 0 | 0 | 0 |  |  | 0
Fairhaven C | MA | 0 | 0 | 0 |  |  | 0
Plympton A-2 | MA | 0 | 0 | 0 |  |  | 0

## 3rd Qtr
MN8 KEF |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Williamsburg A | MA | 0 | 0 | 0 |  |  | 0
Orange A KB | MA | 0 | 0 | 0 |  |  | 0
Goshen A | MA | 0 | 0 | 0 |  |  | 0
Phillipston A KB | MA | 0 | 0 | 0 |  |  | 0
Uxbridge D | MA | 0 | 0 | 0 |  |  | 0
West Bridgewater A&B | MA | 0 | 0 | 0 |  |  | 0
Sutton A | MA | 0 | 0 | 0 |  |  | 0
North Adams A | MA | 0 | 0 | 0 |  |  | 0
North Adams B | MA | 0 | 0 | 0 |  |  | 0
Clarksburg A | MA | 0 | 0 | 0 |  |  | 0
Swansea B | MA | 0 | 0 | 0 |  |  | 0
Wareham 2 | MA | 0 | 0 | 0 |  |  | 0
Kingston 1 KB | MA | 0 | 0 | 0 |  |  | 0
Kingston 2 KB | MA | 0 | 0 | 0 |  |  | 0
Holliston B | MA | 0 | 0 | 0 |  |  | 0
Fairhaven C | MA | 0 | 0 | 0 |  |  | 0
Plympton A-2 | MA | 0 | 0 | 0 |  |  | 0

## 4th Qtr
MN8 KEF |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Williamsburg A | MA | 0 | 0 | 0 |  |  | 0
Orange A KB | MA | 0 | 0 | 0 |  |  | 0
Goshen A | MA | 0 | 0 | 0 |  |  | 0
Phillipston A KB | MA | 0 | 0 | 0 |  |  | 0
Uxbridge D | MA | 0 | 0 | 0 |  |  | 0
West Bridgewater A&B | MA | 0 | 0 | 0 |  |  | 0
Sutton A | MA | 0 | 0 | 0 |  |  | 0
North Adams A | MA | 0 | 0 | 0 |  |  | 0
North Adams B | MA | 0 | 0 | 0 |  |  | 0
Clarksburg A | MA | 0 | 0 | 0 |  |  | 0
Swansea B | MA | 0 | 0 | 0 |  |  | 0
Wareham 2 | MA | 0 | 0 | 0 |  |  | 0
Kingston 1 KB | MA | 0 | 0 | 0 |  |  | 0
Kingston 2 KB | MA | 0 | 0 | 0 |  |  | 0
Holliston B | MA | 0 | 0 | 0 |  |  | 0
Fairhaven C | MA | 0 | 0 | 0 |  |  | 0
Plympton A-2 | MA | 0 | 0 | 0 |  |  | 0

## Jan
MN8 KEF |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 779580.4318 | 1198899.99 | -419319.5582 | -34.98% | 1598697.06 | -819116.6282 | -51.24%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA | 34976.7405 | 63711.84 | -28735.0995 | -45.1% | 96254.79 | -61278.0495 | -63.66%
Orange A KB | MA | 36812.4413 | 50249.95 | -13437.5087 | -26.74% | 78902.03 | -42089.5887 | -53.34% | 1. Site tripped offline on 01/13 multiple times early in the morningand auto-closed shortly after | 1. SR080185
Goshen A | MA | 25506 | 57487.3 | -31981.3 | -55.63% | 45574.37 | -20068.37 | -44.03% | 1. Site tripped on 01/14 at 14:30 and later back online on 01/15 at 10:00AM 2. Site tripped offline on 01/25 at 11:06AM and later back online 01/25 at 11:27AM. | 1. SR080209 2. SR080465
Phillipston A KB | MA | 28771 | 81174.38 | -52403.38 | -64.56% | 48828.99 | -20057.99 | -41.08%
Uxbridge D | MA | 42944 | 75174.5 | -32230.5 | -42.87% | 103260 | -60316 | -58.41%
West Bridgewater A&B | MA | 84322 | 126671.7 | -42349.7 | -33.43% | 169067.9 | -84745.9 | -50.13%
Sutton A | MA | 30226 | 57946.25 | -27720.25 | -47.84% | 93432.82 | -63206.82 | -67.65%
North Adams A | MA | 33659 | 55008.74 | -21349.74 | -38.81% | 98462.86 | -64803.86 | -65.82% | 1. Inverter 3.3 is offline on 01/13 at 07:00AM, later back online on 01/13 at 12:45PM and tripping on and off multiple days on and off. | 1. SR080193
North Adams B | MA | 25714 | 47004.33 | -21290.33 | -45.29% | 98462.86 | -72748.86 | -73.88%
Clarksburg A | MA | 25169 | 48116.73 | -22947.73 | -47.69% | 98015.59 | -72846.59 | -74.32%
Swansea B | MA | 54645 | 81330.64 | -26685.64 | -32.81% | 50080.16 | 4564.84 | 9.115% | 1. Site tripped offline on 01/29 at 16:00 and later back online on 01/30 at 11:15AM. | 1. SR080590
Wareham 2 | MA | 59387.25 | 65302.43 | -5915.18 | -9.058% | 103231.1 | -43843.85 | -42.47%
Kingston 1 KB | MA | 46172 | 64095.79 | -17923.79 | -27.96% | 78554.16 | -32382.16 | -41.22% | 1. Site tripped on 01/14 at 16:45 and later back online on 01/15 at 14:30. 2. Site tripped offline due to utility outage on 01/16 at 11:30AM and utility cleared outage on 01/18 at 07:45AM. | 1. SR080216 2. SR080258
Kingston 2 KB | MA | 38326 | 38638.25 | -312.25 | -0.8081% | 63052.82 | -24726.82 | -39.22% | 1. Site tripped on 01/14 at 16:45 and later back online on 01/15 at 14:30. 2. Site tripped offline due to utility outage on 01/16 at 11:30AM and utility cleared outage on 01/18 at 07:45AM. | 1. SR080217 2. SR080259
Holliston B | MA | 32229 | 61034.62 | -28805.62 | -47.2% | 98146.17 | -65917.17 | -67.16%
Fairhaven C | MA | 120080 | 148303.4 | -28223.4 | -19.03% | 176726.2 | -56646.2 | -32.05% | 1. Site tripped offline on 01/11 at 07:00AM and later back online on 01/12 at 07:45AM. 2. Inverter 47 was offline after site re-energize the site on 01/12 and back online on 14:15. | 1. SR080149 2. SR080171
Plympton A-2 | MA | 60641 | 77649.14 | -17008.14 | -21.9% | 98644.24 | -38003.24 | -38.53% | 1. Site tripped offline on 01/10 at 03:26AM and later back online on 01/10 at 06:24AM. | 1. SR080115

## Feb
MN8 KEF |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 1996105.2105 | 2188725.08 | -192619.8695 | -8.801% | 1959995.17 | 36110.0405 | 1.842%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA | 129427.3233 | 137302.4 | -7875.0767 | -5.736% | 113866 | 15561.3233 | 13.67%
Orange A KB | MA | 103151.8872 | 104286.4 | -1134.5128 | -1.088% | 95699.56 | 7452.3272 | 7.787% | 1. Inverters 1.01 & 1.02 tripped offline on 02/28 at 10:00 AM and resolved at 11:30AM | 1. SR081451
Goshen A | MA | 115740 | 124956.1 | -9216.1 | -7.375% | 59464.02 | 56275.98 | 94.64% | 1. Site offline on 02/16 at 04:45AM and back online at 10:15 2. Site offline on 02/20 at 18:30 and back online on 02/21 at 08:15AM | 1. SR081034 2. SR081141
Phillipston A KB | MA | 119297 | 156008.8 | -36711.8 | -23.53% | 69074.69 | 50222.31 | 72.71%
Uxbridge D | MA | 130995 | 137973 | -6978 | -5.058% | 125233.8 | 5761.2 | 4.6%
West Bridgewater A&B | MA | 191715 | 209729.7 | -18014.7 | -8.589% | 203452.8 | -11737.8 | -5.769%
Sutton A | MA | 95646 | 114772 | -19126 | -16.66% | 115682.6 | -20036.6 | -17.32%
North Adams A | MA | 112525 | 120744.9 | -8219.9 | -6.808% | 119388.7 | -6863.7 | -5.749% | 1. Inverter 3.3 is offline on 02/02 and back online on 02/03 at 07:00AM and tripping on and off multiple days on and off. | 1. SR080193
North Adams B | MA | 107095 | 104225.4 | 2869.6 | 2.753% | 119388.7 | -12293.7 | -10.3%
Clarksburg A | MA | 116505 | 117091.1 | -586.1 | -0.5006% | 118846.2 | -2341.2 | -1.97%
Swansea B | MA | 117946 | 130137.5 | -12191.5 | -9.368% | 66792.55 | 51153.45 | 76.59%
Wareham 2 | MA | 88759 | 98078.5 | -9319.5 | -9.502% | 123998.2 | -35239.2 | -28.42% | 1. Site is offline due to utility outage On 02/13 at 14:30PM and back online on 02/14 at 09:00AM | 1. SR080991
Kingston 1 KB | MA | 90493 | 102655.2 | -12162.2 | -11.85% | 97249.23 | -6756.23 | -6.947% | 1. Inverter 3.3 is offline on 02/16 at 12:45 and back online on 02/20 at 06:15AM. 2. Inverter 3.3 tripped offline on 02/24 at 14:00PM and back online on 02/25 3. Inverter 3.3 tripped offline on 02/28 at 10:45AM and back online at EOD and again tripped offline at 10:15 on 02/29 | 1. SR081063 2. SR081294 3. SR081405
Kingston 2 KB | MA | 76899 | 66380.18 | 10518.82 | 15.85% | 78058.62 | -1159.62 | -1.486% | 1. Inverter 5.1 tripped offline from 02/28 at 11:15 | 1. SR081422
Holliston B | MA | 111207 | 124683.7 | -13476.7 | -10.81% | 121518 | -10311 | -8.485%
Fairhaven C | MA | 187036 | 219891.7 | -32855.7 | -14.94% | 212087.3 | -25051.3 | -11.81% | 1. Inverter 47 derating after 10 am on sunny days. Possible fan issue. | 1. SR081128
Plympton A-2 | MA | 101668 | 119808.5 | -18140.5 | -15.14% | 120194.2 | -18526.2 | -15.41%

## Mar
MN8 KEF |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 2286213.3977 | 2355311.84 | -69098.4423 | -2.934% | 2573917.3 | -287703.9023 | -11.18%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA | 135110.0305 | 142317.5 | -7207.4695 | -5.064% | 148092.7 | -12982.6695 | -8.767%
Orange A KB | MA | 107315.3672 | 104368.1 | 2947.2672 | 2.824% | 123550.3 | -16234.9328 | -13.14%
Goshen A | MA | 120599 | 126112.1 | -5513.1 | -4.372% | 86049.77 | 34549.23 | 40.15% | 1. Relay tripped offline but voltages are available on 03/23 at 17:00 and back online at 13:00 on 03/24 | 1. SR082602
Phillipston A KB | MA | 134199 | 158262 | -24063 | -15.2% | 100406 | 33793 | 33.66% | 1. The relay tripped at 6:08PM and auto-closed within five minutes. | 1. SR082604
Uxbridge D | MA | 138288 | 143309.9 | -5021.9 | -3.504% | 161683.6 | -23395.6 | -14.47%
West Bridgewater A&B | MA | 217285 | 229620.8 | -12335.8 | -5.372% | 266918.5 | -49633.5 | -18.6%
Sutton A | MA | 125601 | 129677.7 | -4076.7 | -3.144% | 152217.9 | -26616.9 | -17.49%
North Adams A | MA | 112601 | 118763.1 | -6162.1 | -5.189% | 145854.3 | -33253.3 | -22.8% | 1. Inverter 3.3 is offline on 03/04 and back online at 14:00 on 03/04 and again offline on 03/05 and back online on 03/06 at 10:30am. | 1. SR080193
North Adams B | MA | 108271 | 103121.8 | 5149.2 | 4.993% | 145854.3 | -37583.3 | -25.77%
Clarksburg A | MA | 111902 | 115432.6 | -3530.6 | -3.059% | 145191.2 | -33289.2 | -22.93%
Swansea B | MA | 146083 | 149943.2 | -3860.2 | -2.574% | 102081.6 | 44001.4 | 43.1%
Wareham 2 | MA | 123608 | 123630.8 | -22.8 | -0.01844% | 168325.4 | -44717.4 | -26.57%
Kingston 1 KB | MA | 109697 | 113352.4 | -3655.4 | -3.225% | 121507.6 | -11810.6 | -9.72%
Kingston 2 KB | MA | 89967 | 75090.14 | 14876.86 | 19.81% | 97530.33 | -7563.33 | -7.755%
Holliston B | MA | 138307 | 138459.5 | -152.5 | -0.1101% | 159875.6 | -21568.6 | -13.49%
Fairhaven C | MA | 235520 | 250903.4 | -15383.4 | -6.131% | 289415.4 | -53895.4 | -18.62%
Plympton A-2 | MA | 131860 | 132946.8 | -1086.8 | -0.8175% | 159362.8 | -27502.8 | -17.26%

## May
MN8 KEF |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA
Orange A KB | MA
Goshen A | MA
Phillipston A KB | MA
Uxbridge D | MA
West Bridgewater A&B | MA
Sutton A | MA
North Adams A | MA
North Adams B | MA
Clarksburg A | MA
Swansea B | MA
Wareham 2 | MA
Kingston 1 KB | MA
Kingston 2 KB | MA
Holliston B | MA
Fairhaven C | MA
Plympton A-2 | MA

## Apr
MN8 KEF |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA
Orange A KB | MA
Goshen A | MA
Phillipston A KB | MA
Uxbridge D | MA
West Bridgewater A&B | MA
Sutton A | MA
North Adams A | MA
North Adams B | MA
Clarksburg A | MA
Swansea B | MA
Wareham 2 | MA
Kingston 1 KB | MA
Kingston 2 KB | MA
Holliston B | MA
Fairhaven C | MA
Plympton A-2 | MA

## Jun
MN8 KEF |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA
Orange A KB | MA
Goshen A | MA
Phillipston A KB | MA
Uxbridge D | MA
West Bridgewater A&B | MA
Sutton A | MA
North Adams A | MA
North Adams B | MA
Clarksburg A | MA
Swansea B | MA
Wareham 2 | MA
Kingston 1 KB | MA
Kingston 2 KB | MA
Holliston B | MA
Fairhaven C | MA
Plympton A-2 | MA

## Jul
MN8 KEF |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA
Orange A KB | MA
Goshen A | MA
Phillipston A KB | MA
Uxbridge D | MA
West Bridgewater A&B | MA
Sutton A | MA
North Adams A | MA
North Adams B | MA
Clarksburg A | MA
Swansea B | MA
Wareham 2 | MA
Kingston 1 KB | MA
Kingston 2 KB | MA
Holliston B | MA
Fairhaven C | MA
Plympton A-2 | MA

## Aug
MN8 KEF |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA
Orange A KB | MA
Goshen A | MA
Phillipston A KB | MA
Uxbridge D | MA
West Bridgewater A&B | MA
Sutton A | MA
North Adams A | MA
North Adams B | MA
Clarksburg A | MA
Swansea B | MA
Wareham 2 | MA
Kingston 1 KB | MA
Kingston 2 KB | MA
Holliston B | MA
Fairhaven C | MA
Plympton A-2 | MA

## Sep
MN8 KEF |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA
Orange A KB | MA
Goshen A | MA
Phillipston A KB | MA
Uxbridge D | MA
West Bridgewater A&B | MA
Sutton A | MA
North Adams A | MA
North Adams B | MA
Clarksburg A | MA
Swansea B | MA
Wareham 2 | MA
Kingston 1 KB | MA
Kingston 2 KB | MA
Holliston B | MA
Fairhaven C | MA
Plympton A-2 | MA

## Oct
MN8 KEF |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA
Orange A KB | MA
Goshen A | MA
Phillipston A KB | MA
Uxbridge D | MA
West Bridgewater A&B | MA
Sutton A | MA
North Adams A | MA
North Adams B | MA
Clarksburg A | MA
Swansea B | MA
Wareham 2 | MA
Kingston 1 KB | MA
Kingston 2 KB | MA
Holliston B | MA
Fairhaven C | MA
Plympton A-2 | MA

## Nov
MN8 KEF |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA
Orange A KB | MA
Goshen A | MA
Phillipston A KB | MA
Uxbridge D | MA
West Bridgewater A&B | MA
Sutton A | MA
North Adams A | MA
North Adams B | MA
Clarksburg A | MA
Swansea B | MA
Wareham 2 | MA
Kingston 1 KB | MA
Kingston 2 KB | MA
Holliston B | MA
Fairhaven C | MA
Plympton A-2 | MA

## Dec
MN8 KEF |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Williamsburg A | MA
Orange A KB | MA
Goshen A | MA
Phillipston A KB | MA
Uxbridge D | MA
West Bridgewater A&B | MA
Sutton A | MA
North Adams A | MA
North Adams B | MA
Clarksburg A | MA
Swansea B | MA
Wareham 2 | MA
Kingston 1 KB | MA
Kingston 2 KB | MA
Holliston B | MA
Fairhaven C | MA
Plympton A-2 | MA

## Sites
Portfolio: | MN8 KEF
Site DAS Name | Site | State | Update | DAS
MA-11-001 - Williamsburg A #1058 | Williamsburg A | MA | AEF | PowerTrack
MA-11-002 - Orange A KB | Orange A KB | MA | AEF | PowerTrack
MA-11-003 - Goshen A #1052 | Goshen A | MA | AEF | PowerTrack
MA-11-004 - Phillipston A KB | Phillipston A KB | MA | AEF | PowerTrack
MA-11-005 - Uxbridge D | Uxbridge D | MA | AEF | PowerTrack
MA-11-006 - West Bridgewater A&B #1063 | West Bridgewater A&B | MA | AEF | PowerTrack
MA-11-007 - Sutton A #1054 | Sutton A | MA | AEF | PowerTrack
MA-11-008 - North Adams A #1079 | North Adams A | MA | AEF | PowerTrack
MA-11-009 - North Adams B #1080 | North Adams B | MA | AEF | PowerTrack
MA-11-010 - Clarksburg A #1081 | Clarksburg A | MA | AEF | PowerTrack
MA-11-011 - Swansea B #1098 | Swansea B | MA | AEF | PowerTrack
MA-11-012 - Wareham 2 | Wareham 2 | MA | AEF | PowerTrack
MA-11-013 - Kingston 1 KB | Kingston 1 KB | MA | AEF | PowerTrack
MA-11-014 - Kingston 2 KB | Kingston 2 KB | MA | AEF | PowerTrack
MA-11-015 - Holliston B | Holliston B | MA | AEF | PowerTrack
MA-11-016 - Fairhaven C | Fairhaven C | MA | AEF | PowerTrack
MA-11-017 - Plympton A | Plympton A-2 | MA | AEF | PowerTrack