## Year to Date
MN8 NY8 |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 11520955.9415 | 10438513.4 | 1082442.5415 | 10.37% | 11714693 | -193737.0585 | -1.654%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Janis | NY | 5634708.9415 | 5879750 | -245041.0585 | -4.168% | 6151248 | -516539.0585 | -8.397%
Puckett Solar | NY | 5886247 | 4558763.4 | 1327483.6 | 29.12% | 5563445 | 322802 | 5.802%

## 1st Qtr
MN8 NY8 |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 11520955.9415 | 10438513.4 | 1082442.5415 | 10.37% | 11714693 | -193737.0585 | -1.654%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Janis | NY | 5634708.9415 | 5879750 | -245041.0585 | -4.168% | 6151248 | -516539.0585 | -8.397%
Puckett Solar | NY | 5886247 | 4558763.4 | 1327483.6 | 29.12% | 5563445 | 322802 | 5.802%

## 2nd Qtr
MN8 NY8 |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Janis | NY | 0 | 0 | 0 |  |  | 0
Puckett Solar | NY | 0 | 0 | 0 |  |  | 0

## 3rd Qtr
MN8 NY8 |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Janis | NY | 0 | 0 | 0 |  |  | 0
Puckett Solar | NY | 0 | 0 | 0 |  |  | 0

## 4th Qtr
MN8 NY8 |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Janis | NY | 0 | 0 | 0 |  |  | 0
Puckett Solar | NY | 0 | 0 | 0 |  |  | 0

## Jan
MN8 NY8 |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 1386024.184 | 1687476.4 | -301452.216 | -17.86% | 2753954 | -1367929.816 | -49.67%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY | 641158.184 | 1056577 | -415418.816 | -39.32% | 1516236 | -875077.816 | -57.71% | 1. Inverter 3.1,4.1 Module 1 and 5.1 module 2 has not started production on 01/09, 01/16, 01/18, 01/19 and 01/31 2.Inverter module 1.1 offline on 01/19 to 01/22 and started on 01/23 at 12:15 | 1.SR080623, SR080624 2.SR080390
Puckett Solar | NY | 744866 | 630899.4 | 113966.6 | 18.06% | 1237718 | -492852 | -39.82% | 1.Production meter was damaged they had to by pass the meter. 2.Inverter 5.1 module 2 is offfline on 01/17 and started on 01/18 at 10:45 3.Site tripped offlinedue to Utility planned outage on 01/25 at 12:00 and back online 02/01. Actual energy data is taken from Inverters data since production meter data is not available*** | 1.SR073174 2.SR080283 3.SR080466

## Feb
MN8 NY8 |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 5046188.7575 | 4124450 | 921738.7575 | 22.35% | 3585377 | 1460811.7575 | 40.74%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY | 2476319.7575 | 2363767 | 112552.7575 | 4.762% | 1923083 | 553236.7575 | 28.77% | 1. Inverter 5.1 module 1 did not start for production and back online at 14:00 on 02/29 | 1. SR081450
Puckett Solar | NY | 2569869 | 1760683 | 809186 | 45.96% | 1662294 | 907575 | 54.6% | 1. Inverters 6.1 Combiner boxes 1,2,3, 12,18,19,20 were barely producing on 02/09 and and issue resolved due to inverter being powercycled at 14:00. Issue reoccurred on 02/13 and resolved due to inverter being powercycled at 09:00 on 02/14 | 1. SR080883, SR080968

## Mar
MN8 NY8 |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 5088743 | 4626587 | 462156 | 9.989% | 5375362 | -286619 | -5.332%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY | 2517231 | 2459406 | 57825 | 2.351% | 2711929 | -194698 | -7.179%
Puckett Solar | NY | 2571512 | 2167181 | 404331 | 18.66% | 2663433 | -91921 | -3.451%

## May
MN8 NY8 |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY
Puckett Solar | NY

## Apr
MN8 NY8 |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY
Puckett Solar | NY

## Jun
MN8 NY8 |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY
Puckett Solar | NY

## Jul
MN8 NY8 |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY
Puckett Solar | NY

## Aug
MN8 NY8 |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY
Puckett Solar | NY

## Sep
MN8 NY8 |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY
Puckett Solar | NY

## Oct
MN8 NY8 |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY
Puckett Solar | NY

## Nov
MN8 NY8 |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY
Puckett Solar | NY

## Dec
MN8 NY8 |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Janis | NY
Puckett Solar | NY

## Sites
Portfolio: | MN8 NY8
Site DAS Name | Site | State | Update | DAS
Janis | Janis | NY | AEF | PowerTrack
Puckett Solar | Puckett Solar | NY | AEF | PowerTrack