## Year to Date
Ecofin |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 2278945 | 2704398.965 | -425453.965 | -15.73% | 0 | 2278945 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Alamosa School District | CO | 460134 | 513735.8303 | -53601.8303 | -10.43% |  | -125201.65
San Luis Valley | CO | 0 | 0 | 0 |  |  | 0
Golden NREL 2 | CO | 22181 | 22245.2058 | -64.2058 | -0.2886% |  | -6550.96
Golden NREL Wind 3 | CO | 0 | 0 | 0 |  |  | 0
Pratt Solar Farm | KS | 1796630 | 2168417.929 | -371787.929 | -17.15% |  | -83098.04
Rochester - 5516 Valleyhigh NW | MN | 0 | 0 | 0 |  |  | 0
Warsaw - 2201 Richmond | VA | 0 | 0 | 0 |  |  | 0

## 1st Qtr
Ecofin |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 2107421 | 2460365.2047 | -352944.2047 | -14.35% | 2220161.3 | -112740.3 | -5.078%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Alamosa School District | CO | 288610 | 269702.0699 | 18907.9301 | 7.011% | 311701.3 | -23091.3 | -7.408%
San Luis Valley | CO | 0 | 0 | 0 |  | 0 | 0
Golden NREL 2 | CO | 22181 | 22245.2058 | -64.2058 | -0.2886% | 28731.96 | -6550.96 | -22.8%
Golden NREL Wind 3 | CO | 0 | 0 | 0 |  | 0 | 0
Pratt Solar Farm | KS | 1796630 | 2168417.929 | -371787.929 | -17.15% | 1879728.04 | -83098.04 | -4.421%
Rochester - 5516 Valleyhigh NW | MN | 0 | 0 | 0 |  | 0 | 0
Warsaw - 2201 Richmond | VA | 0 | 0 | 0 |  | 0 | 0

## 2nd Qtr
Ecofin |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 4744605.427 | 6215839.9219 | -1471234.4949 | -23.67% | 6202445.66 | -1457840.233 | -23.5%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Alamosa School District | CO | 171524 | 244033.7604 | -72509.7604 | -29.71% | 273634.35 | -102110.35 | -37.32%
San Luis Valley | CO | 222774.727 | 0 | 222774.727 |  | 0 | 222774.727
Golden NREL 2 | CO | 26536 | 23267.9035 | 3268.0965 | 14.05% | 26565.72 | -29.72 | -0.1119%
Golden NREL Wind 3 | CO | 0 | 0 | 0 |  | 0 | 0
Pratt Solar Farm | KS | 1779130 | 2287094.73 | -507964.73 | -22.21% | 2268519.5 | -489389.5 | -21.57%
Rochester - 5516 Valleyhigh NW | MN | 1472046 | 2533439.71 | -1061393.71 | -0.41895 | 2459554.67 | -987508.67 | -0.4015
Warsaw - 2201 Richmond | VA | 1072594.7 | 1128003.818 | -55409.118 | -0.049121 | 1174171.42 | -101576.72 | -0.086509

## 3rd Qtr
Ecofin |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Alamosa School District | CO | 0 | 0 | 0 |  |  | 0
San Luis Valley | CO | 0 | 0 | 0 |  |  | 0
Golden NREL 2 | CO | 0 | 0 | 0 |  |  | 0
Golden NREL Wind 3 | CO | 0 | 0 | 0 |  |  | 0
Pratt Solar Farm | KS | 0 | 0 | 0 |  |  | 0
Rochester - 5516 Valleyhigh NW | MN | 0 | 0 | 0 |  |  | 0
Warsaw - 2201 Richmond | VA | 0 | 0 | 0 |  |  | 0

## 4th Qtr
Ecofin |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Alamosa School District | CO | 0 | 0 | 0 |  |  | 0
San Luis Valley | CO | 0 | 0 | 0 |  |  | 0
Golden NREL 2 | CO | 0 | 0 | 0 |  |  | 0
Golden NREL Wind 3 | CO | 0 | 0 | 0 |  |  | 0
Pratt Solar Farm | KS | 0 | 0 | 0 |  |  | 0
Rochester - 5516 Valleyhigh NW | MN | 0 | 0 | 0 |  |  | 0
Warsaw - 2201 Richmond | VA | 0 | 0 | 0 |  |  | 0

## Jan
Ecofin |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 78991 | 79673 | -682 | -0.856% | 100783 | -21792 | -21.62% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO | 72896 | 73786 | -890 | -1.206% | 93005 | -20109 | -21.62% | 1. Inverter 1 is offline on 01/09, 01/10, 01/12, 01/17. | 1. SR080094
San Luis Valley | CO | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site was not communicating from 04/22 | 1. SR077495
Golden NREL 2 | CO | 6095 | 5887 | 208 | 3.533% | 7778 | -1683 | -21.64% | 1. Inverter was barely produced on 1/13, 1/14 and 1/15 | 1. SR080235
Golden NREL Wind 3 | CO | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site was not communicating from 05/23/2022 | 1. SR079089
Pratt Solar Farm | KS
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Feb
Ecofin |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 911881 | 1076640.553 | -164759.553 | -15.3% | 944891.36 | -33010.36 | -3.494% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO | 100394 | 90505.5 | 9888.5 | 10.93% | 97813.3 | 2580.7 | 2.638%
San Luis Valley | CO | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site stopped communicating from 04/22 | 1. SR077494
Golden NREL 2 | CO | 6597 | 7237.8 | -640.8 | -8.854% | 8862.2 | -2265.2 | -25.56%
Golden NREL Wind 3 | CO | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site was not communicating from 05/23/2022 | 1. SR079089
Pratt Solar Farm | KS | 804890 | 978897.253 | -174007.253 | -17.78% | 838215.86 | -33325.86 | -3.976% | 1.(A) Inverter 2 was taken offline by technician on 02/26/2024 at 13:30 to 15:00 & inverter 1 at 15:00 - 16:15. 1.(B) Inverter 2 tripped offline on 02/27/2024 at 15:48 & back online at 12:00 on 02/28/2024. | 1. SR081345
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Mar
Ecofin |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 1116549 | 1304051.6517 | -187502.6517 | -14.38% | 1174486.94 | -57937.94 | -4.933% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO | 115320 | 105410.5699 | 9909.4301 | 9.401% | 120883 | -5563 | -4.602%
San Luis Valley | CO | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site stopped communicating from 04/22/20223 and communication regained on 04/03 | 1. SR077494
Golden NREL 2 | CO | 9489 | 9120.4058 | 368.5942 | 4.041% | 12091.76 | -2602.76 | -21.53%
Golden NREL Wind 3 | CO | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site was not communicating from 05/23/2022 | 1. SR079089
Pratt Solar Farm | KS | 991740 | 1189520.676 | -197780.676 | -16.63% | 1041512.18 | -49772.18 | -4.779% | 1. Inverter 2 is derating, due to overheating 2 modules are offline | 1. SR081345
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Apr
Ecofin |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 1126136.837 | 1267971.9095 | -141835.0725 | -11.19% | 1237372.96 | -111236.123 | -8.99% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO | 129640 | 120725.5538 | 8914.4462 | 7.384% | 129601.73 | 38.27 | 0.02953%
San Luis Valley | CO | 100708.837 | 0 | 100708.837 |  | 0 | 100708.837
Golden NREL 2 | CO | 12208 | 10993.1857 | 1214.8143 | 11.05% | 12899.28 | -691.28 | -5.359%
Golden NREL Wind 3 | CO | 0 | 0 |  | 0% | 0 | 0 |  | 1. Site was not communicating from 05/23/2022 | 1. SR079089
Pratt Solar Farm | KS | 883580 | 1136253.17 | -252673.17 | -22.24% | 1094871.95 | -211291.95 | -19.3% | 1. Inverter 2 is derating, due to overheating 2 modules are offline 2. Site is offline from 04/17 to 04/19. | 1. SR081345 2. SR083483
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## May
Ecofin |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 3618468.59 | 4947868.0124 | -1329399.4224 | -26.87% | 4965072.7 | -1346604.11 | -27.12%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO | 41884 | 123308.2066 | -81424.2066 | -66.03% | 144032.62 | -102148.62 | -70.92% | 1. Inverter 2 is offline since 05/03. 2. Inverter 1 didn't start for producton on 05/21 and back online at 01:15 on 05/21 and again offline since 05/22 | 1. SR084239 2. SR084949
San Luis Valley | CO | 122065.89 | 0 | 122065.89 |  | 0 | 122065.89 |  | 1. Site was offline from 05/10 at 07:00am to 11:00am on 05/10. | 1. SR084536
Golden NREL 2 | CO | 14328 | 12274.7178 | 2053.2822 | 16.73% | 13666.44 | 661.56 | 4.841%
Golden NREL Wind 3 | CO | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site was not communicating from 05/23/2022 | 1. SR079089
Pratt Solar Farm | KS | 895550 | 1150841.56 | -255291.56 | -22.18% | 1173647.55 | -278097.55 | -23.7% | 1. Inverter 2 is derating, due to overheating 2 modules are offline 2. Inverter 1 is derating since 05/28. | 1. SR081345 2. SR085401
Rochester - 5516 Valleyhigh NW | MN | 1472046 | 2533439.71 | -1061393.71 | -41.9% | 2459554.67 | -987508.67 | -40.15% | 1. Inverter 1 is offline due to a permanent fault of the power module. Fault0010 at 14:00 from 05/21. 2. Inverter 27 tripped offline due to bus imbalance. Protect0070 at 12:30PM on 05/23. 3. Inverter 35 tripped offline due to AC SPD Fault. Warn0070 at 11:30 on 05/18. 4. Inverter 49 tripped offline due to bus imbalance. Protect0070 at 15:45 on 05/25. 5. Inverter 71 tripped offline due to a permanent fault of the power module. Fault0010 at 15:15 on 05/05. 6. Inverter 40 tripped offline and reporting Grid Phase Voltage Out of Range at 18:15 on 05/29. | 1. SR085262 2. SR085263 3. SR085264 4. SR085265 5. SR085266 6. SR085294
Warsaw - 2201 Richmond | VA | 1072594.7 | 1128003.818 | -55409.118 | -4.912% | 1174171.42 | -101576.72 | -8.651% | 1. Inverter 12 is derating due to external fan fault since 05/28 | 1. SR085335

## Jun
Ecofin |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO
San Luis Valley | CO
Golden NREL 2 | CO
Golden NREL Wind 3 | CO
Pratt Solar Farm | KS
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Jul
Ecofin |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO
San Luis Valley | CO
Golden NREL 2 | CO
Golden NREL Wind 3 | CO
Pratt Solar Farm | KS
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Aug
Ecofin |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO
San Luis Valley | CO
Golden NREL 2 | CO
Golden NREL Wind 3 | CO
Pratt Solar Farm | KS
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Sep
Ecofin |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO
San Luis Valley | CO
Golden NREL 2 | CO
Golden NREL Wind 3 | CO
Pratt Solar Farm | KS
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Oct
Ecofin |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO
San Luis Valley | CO
Golden NREL 2 | CO
Golden NREL Wind 3 | CO
Pratt Solar Farm | KS
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Nov
Ecofin |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO
San Luis Valley | CO
Golden NREL 2 | CO
Golden NREL Wind 3 | CO
Pratt Solar Farm | KS
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Dec
Ecofin |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Alamosa School District | CO
San Luis Valley | CO
Golden NREL 2 | CO
Golden NREL Wind 3 | CO
Pratt Solar Farm | KS
Rochester - 5516 Valleyhigh NW | MN
Warsaw - 2201 Richmond | VA

## Sites
Portfolio: | Ecofin
Site DAS Name | Site | State | Update | DAS
003 - Alamosa School District | Alamosa School District | CO
002 - San Luis Valley Regional MC | San Luis Valley | CO
002 - NREL 2 | Golden NREL 2 | CO
004 - NREL Wind 3 | Golden NREL Wind 3 | CO
Kenyon Energy KS Solar | Pratt Solar Farm | KS
MN WestSide Solar | Rochester - 5516 Valleyhigh NW | MN
Hemings (VA) - ODEC | Warsaw - 2201 Richmond | VA