## Sites
Monthly Site Performance Summary
Account: | Ameresco
Report's period: | 10/01/2024 - 10/31/2024
Sites: | Manually selected sites
# of sites: | 11
Generated on: | 11/08/2024 01:36
Site Information | [6 empty] | Open Alerts | Current Month |  |  | Previous Month |  |  | Same month last year |  |  | Previous twelve months
# | Site Name | Country | State | City | Installation Date | Peak Power (kWp) | Highest Alert Impact | kWh | kWh/kWp | Revenue | kWh | kWh/kWp | Revenue | kWh | kWh/kWp | Revenue | kWh | kWh/kWp | Revenue
1 | NBHA Adams st | United States | Massachusetts | New Bedford | 12/01/2020 | 69.255 | 2 | 4056.2 | 58.6 |  | 4660.1 | 67.3 |  | 4071.7 | 58.8 |  | 52913.4 | 764
2 | NBHA Ben Rose | United States | Massachusetts | New Bedford | 03/03/2022 | 152.425 | 2 | 14053.3 | 92.2 |  | 15391.5 | 101 |  | 11904.9 | 78.1 |  | 169239 | 1110.3
3 | NBHA Brickenwood | United States | Massachusetts | New Bedford | 03/01/2022 | 572.325 | 6 | 49427.7 | 86.4 |  | 53710 | 93.8 |  | 48969.4 | 85.6 |  | 640326.5 | 1118.8
4 | NBHA Chaffee Fairfield | United States | Massachusetts | New Bedford | 07/29/2020 | 49.4 | 0 | 4926.8 | 99.7 |  | 5152.2 | 104.3 |  | 4417.2 | 89.4 |  | 58427.2 | 1182.7
5 | NBHA DeMedeiros | United States | Massachusetts | New Bedford | 01/10/2022 | 64.35 | 0 | 5920.5 | 92 |  | 6624.2 | 102.9 |  | 4201 | 65.3 |  | 58728.6 | 912.6
6 | NBHA Dottin Place 1 | United States | Massachusetts | New Bedford | 07/29/2020 | 88.4 | 0 | 7640.2 | 86.4 |  | 8232 | 93.1 |  | 6910.6 | 78.2 |  | 92975.9 | 1051.8
7 | NBHA Hillside | United States | Massachusetts | New Bedford | 06/28/2021 | 117 | 0 | 11494.8 | 98.2 |  | 12022.4 | 102.8 |  | 10342.4 | 88.4 |  | 135806.5 | 1160.7
8 | NBHA Presidential | United States | Massachusetts | New Bedford | 09/12/2021 | 468.65 | 2 | 36237.9 | 77.3 |  | 38389.4 | 81.9 |  | 34025.6 | 72.6 |  | 439970.9 | 938.8
9 | NBHA Satellite | United States | Massachusetts | New Bedford | 11/18/2021 | 169 | 2 | 10484.1 | 62 |  | 9363.7 | 55.4 |  | 14483.6 | 85.7 |  | 155477.4 | 920
10 | NBHA Shawmut Village | United States | Massachusetts | New Bedford | 10/21/2020 | 443.625 | 5 | 29335 | 66.1 |  | 25630.8 | 57.8 |  | 34465 | 77.7 |  | 396753 | 894.3
11 | NBHA Westlawn | United States | Massachusetts | New Bedford | 03/03/2022 | 267.8 | 2 | 19716.6 | 73.6 |  | 22979.8 | 85.8 |  | 20736.2 | 77.4 |  | 268043.1 | 1000.9
Total | [5 empty] | 2462.23 |  | 193293.1 |  |  | 202156.1 |  |  | 194527.6 |  |  | 2468661.5

## Service Request
Owner | Asset | Site Equipment | kW Down | Date | Description | Account Manager | Status | Pending | Priority | Summary | Request | D365 Project
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 113 Mashpee CT - Inverter 45 | Inv comms | 2024-10-29 13:34 | 10/29/24 Inv 45 stopped communicating 10/22. Production not confirmed. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR092738
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 28 Monroe Dr Bldg 16 - Inverter 17 | 9 | 2024-10-16 13:04 | 10/16/24 Inverter 17 tripped offline at 4pm on 10/8. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR092211
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 150 Hathaway - Inverter 5 | Inv comms | 2024-10-15 13:09 | 10/15/24 Inverter 5 stopped communicating 10/7. Production not confirmed | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR092164
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 209 Harvard - Inverter 31 | 7.5 | 2024-10-03 15:28 | 10/3/24 Inverter 31 tripped offline 9/27 | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR091736
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 18 Yale - Inverter 37 | Inv comms | 2024-09-22 12:37 | 9/22/24 Inverter 37 stopped communicating 9/15. Possibly offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR091041
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 37 Cherokee CT - Inverter 10 | 7.5 | 2024-09-18 15:01 | 9/18/24 Inverter 10 tripped offline on 9/10/24 | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR090723
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 133 Dakota CT - Inverter 36 | Inv comms | 2024-09-09 14:59 | 9/9/24 Inverter 36 stopped communicating 9/1. Production not confirmed. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR090138
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 109 Navaho CT - Inverter 40 | Inv comms | 2024-07-26 15:15 | 7/26/24 Inverter 40 stopped communicating on 7/19. Production not confirmed. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR088285
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 20 Malden - Inverter 20 | 7.5 | 2024-07-22 14:41 | 7/22/24 Inverter 20 tripped offline on 7/14, SolarEdge reporting inverter production issue. detected | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR087996
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 22 - Inverter 12 | Inv comms | 2024-07-16 13:22 | 7/16/24 Inverter 12 stopped communicating on 7/6/24. Production is not confirmed. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087778
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 131 Dakota CT - Inverter 38 | Inv comms | 2024-07-15 15:29 | 7/15/24 Inverter 38 stopped communicating on 7/6/24, production not confirmed. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087728
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 155 Gay Head CT - Inverter 33 | Inv comms | 2024-07-15 15:27 | 7/15/24 Inverter 33 stopped communicating on 7/6/24, production not confirmed. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087727
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 7 - Inverter 4 | Inv comms | 2024-07-02 13:00 | 7/2/24: Inverter 4 stopped communicating on 5/2, cannot confirm production. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087282
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 9 Shawnee CT - Inverter 3 | 6 | 2024-06-17 13:38 | 6/17/24 inverter 3 tripped offline on 6/15 at 3pm. Reporting production issue detected. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR086321 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 58 Yale - Inverter 49 | Inv comms | 2024-06-03 12:37 | 6/3/24 - inverter 49 stopped communicating on 5/25/24; possibly offline. | Diana Balayan | Pending | Pending Return Visit | PV Monitoring - Minor | Ameresco UM - Inverter Troubleshooting | SR085484 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring |  | Inv comms | 2024-05-17 12:41 | 5/17/24 - Presidential inverters 18, 27 have stopped communicating, possibly offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR084807 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring |  | Inv comms | 2024-05-11 13:39 | 6/3/24 - invs 15 and 16 regained comms, invs 4 and 6 still have no comms. 5/11 - Westlawn inverters 4, 6, 15, 16 stopped communicating, possibly offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure | SR084580 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 105 Navaho CT - Inverter 46 | Inv comms | 2024-04-19 12:51 | 4/19 - Inverter 46 is not communicating, possibly offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR083627 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 88 Malden - Inverter 27 | Inv comms | 2024-03-21 12:45 | 11/7 - Inverter 27 stopped communicating, possibly offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR082331 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 310 Mt-Pleasant St Bldg 2 - Inverter 1 | 14.4 | 2024-03-04 12:57 | 3/4 - Inverter 1 is offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR081556 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 240 Harvard - Inverter 46 | 6 | 2024-03-04 12:55 | 3/4 - Inverter 46 at Brickenwood is offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR081555 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 135 Dakota CT - Inverter 12 | Inv comms | 2024-03-01 14:56 | 3/1 - Inverter 12 lost communications; production cannot be confirmed. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR081505 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 33 - Inverter 26 | Inv comms | 2024-03-01 14:54 | 3/1 - Inverter 26 is not communicating. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR081504 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 45 - Inverter 23 | Inv comms | 2024-02-20 14:04 | 2/20/24 - Inverter 23 stopped communicating; cannot confirm production. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR081129 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 21 Mohawk CT - Inverter 8 | Inv comms | 2023-11-07 12:49 | 11/7 - Inverter 8 stopped communicating, possibly offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR078119 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 111 Mashpee CT - Inverter 49 | Inv comms | 2023-10-17 03:39 | 10/17/23 - Inverter 49 is not communicating from 07/09, possibly offline | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR077517 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Satellite - 90 Libra Dr - Inverter 11 | Inv comms | 2023-10-05 14:16 | 10/5/23 - Inverter 11 stopped communicating, possibly offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure | SR077287 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 161 Gay Head CT - Inverter 54 | Inv comms | 2023-09-08 12:40 | 7/3/2024 - Inverter stopped communicating 6/26/24 10/17/2023 - Inverter is communicating from 10/03 9/8 - Inverter stopped communicating, possibly offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR075876 | 1006999.001
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Adams St - 14 Adams St - Inverter 4 | 14.4 | 2023-08-31 14:53 | 10/16/23 - Inverter is still offline. 08/31/23 - Inverter 4 tripped offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR075642 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 121 Mashpee CT - Inverter 25 | 7.6 | 2023-08-09 12:46 | 10/17/2023 - Inverter is still not reporting, possibly offline 8/9 - Inverter 25 stopped communicating. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR074887 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 45 Cherokee CT - Inverter 37 | Inv comms | 2023-07-13 12:37 | 10/17/2023 - Inverter is still not communicating from 07/10, possibly offline 7/13 - Inverter 37 stopped communicating, possibly offline. S/N: 73086310-EE | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure | SR073825 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 190 Harvard - Inverter 35 | 10 | 2023-07-11 13:59 | 10/17/23 - Inverter 35 is still offline 07/11/23 - Inverter 35 tripped offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR073743 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Dottin Place 1 - Amanda Ave Bldg 5 (61) - Inverter 4 | 6 | 2023-07-07 04:52 | 07/07/2023 - Inverter 4 tripped offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR073621 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 240 Harvard - Inverter 46 | 7.6 | 2023-05-22 14:23 | 05/22/23 - Inverter 46 tripped offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR071782 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 63 Apache CT - Inverter 42 | Inv comms | 2023-05-09 14:11 | 10/17/2023 - Inverter is still not communicating from 05/07, possibly offline 5/9 - Inverter 42 stopped communicating, possibly offline. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR071467 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 157 Gay Head CT - Inverter 51 | Inv comms | 2023-04-25 14:19 | 4/25 - Shawmut Village inverter 51 no comms today. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR071089
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 67 Apache CT - Inverter 48 | Inv comms | 2023-04-21 12:34 | 10/17/2023 - Inverter is still not communicating from 04/11, possibly offline 4/21 - Inverter 48 stopped communicating. | Diana Balayan | Pending |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR070992 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 119 Fillmore St Bldg 9 - Inverter 21 | Inv comms | 2023-01-03 12:33 | 10/17/2023 - Issue still exists 4/3/23 - Issue still exists. 1/3/23 - Inverter 21 lost communications on 8/23/22. | Diana Balayan | New |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR068143 | 1006999
Total