## Year to Date
Creed Monarch - Roof |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 749491.3112 | 0 | 749491.3112 | 0% | 1066634.713 | -317143.4018 | -29.73%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: New Britain - Creed Monarch | CT | 749491.3112 | 0 | 749491.3112 |  | 1066634.713 | -317143.4018 | -29.73%

## 1st Qtr
Creed Monarch - Roof |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 159443.5202 | 0 | 159443.5202 | 0% | 236807.813 | -77364.2928 | -32.67%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: New Britain - Creed Monarch | CT | 159443.5202 | 0 | 159443.5202 |  | 236807.813 | -77364.2928 | -32.67%

## 2nd Qtr
Creed Monarch - Roof |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 268687.541 | 0 | 268687.541 | 0% | 432176.3 | -163488.759 | -37.83%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: New Britain - Creed Monarch | CT | 268687.541 | 0 | 268687.541 |  | 432176.3 | -163488.759 | -37.83%

## 3rd Qtr
Creed Monarch - Roof |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 321360.25 | 0 | 321360.25 | 0% | 397650.6 | -76290.35 | -19.19%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: New Britain - Creed Monarch | CT | 321360.25 | 0 | 321360.25 |  | 397650.6 | -76290.35 | -19.19%

## 4th Qtr
Creed Monarch - Roof |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: New Britain - Creed Monarch | CT | 0 | 0 | 0 |  |  | 0

## Jan
Creed Monarch - Roof |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 22388.4702 | 0 | 22388.4702 | 0% | 57340 | -34951.5298 | -60.95%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT | 22388.4702 | 0 | 22388.4702 |  | 57340 | -34951.5298 | -60.95%

## Feb
Creed Monarch - Roof |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 43907.63 | 0 | 43907.63 | 0% | 73689.025 | -29781.395 | -40.41%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT | 43907.63 | 0 | 43907.63 |  | 73689.025 | -29781.395 | -40.41%

## Mar
Creed Monarch - Roof |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 93147.42 | 0 | 93147.42 | 0% | 105778.788 | -12631.368 | -11.94%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT | 93147.42 | 0 | 93147.42 |  | 105778.788 | -12631.368 | -11.94%

## Apr
Creed Monarch - Roof |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 3262.181 | 0 | 3262.181 | 0% | 129887.5 | -126625.319 | -97.49%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT | 3262.181 | 0 | 3262.181 |  | 129887.5 | -126625.319 | -97.49% | 1. Site was taken offline due to removal of feeders on 04/03 at 13:15 throughout the month. | 1. SR083003

## May
Creed Monarch - Roof |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 126239.34 | 0 | 126239.34 | 0% | 146109.4 | -19870.06 | -13.6%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT | 126239.34 | 0 | 126239.34 |  | 146109.4 | -19870.06 | -13.6% | 1. Site back online on 05/01 at 11:30 | 1. SR083003

## Jun
Creed Monarch - Roof |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 139186.02 | 0 | 139186.02 | 0% | 156179.4 | -16993.38 | -10.88%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT | 139186.02 | 0 | 139186.02 |  | 156179.4 | -16993.38 | -10.88% | 1. Inverter 4 left unit tripped offline on 06/25 at 11:30 throughout the month | 1. SR086956

## Jul
Creed Monarch - Roof |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 124851.1196 | 0 | 124851.1196 | 0% | 153133.6 | -28282.4804 | -18.47%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT | 124851.1196 | 0 | 124851.1196 |  | 153133.6 | -28282.4804 | -18.47% | 1. Inverter 4 left unit tripped offline at 11:52 on 06/25 and back online at 11 on 07/03/2024. 2. Inverter 6 left unit tripped offline at 17:00 on 07/02 and back online at 9:52 on 07/16/2024. 3. Inverter 7 right unit tripped offline at 11:47 on 07/11 and back online at 11:52 on 07/18. 4. Inverter 5 left unit tripped offline at 14:52 on 07/11 and offline throughout the month. | 1. SR086956. 2. SR087368. 3. SR087605. 4. SR087606.

## Aug
Creed Monarch - Roof |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 105762.2403 | 0 | 105762.2403 | 0% | 137358.2 | -31595.9597 | -23%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT | 105762.2403 | 0 | 105762.2403 |  | 137358.2 | -31595.9597 | -23% | 1. Inverter 5 left unit tripped offline since 07/11. | 1. SR089217.

## Sep
Creed Monarch - Roof |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 90746.8901 | 0 | 90746.8901 | 0% | 107158.8 | -16411.9099 | -15.32%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT | 90746.8901 | 0 | 90746.8901 |  | 107158.8 | -16411.9099 | -15.32% | 1. Inverter 5 left unit tripped offline since 07/11. | 1. SR089217.

## Oct
Creed Monarch - Roof |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT

## Nov
Creed Monarch - Roof |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT

## Dec
Creed Monarch - Roof |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: New Britain - Creed Monarch | CT

## Sites
Portfolio: | Creed Monarch - Roof
Site DAS Name | Site | State | Update | DAS
Creed Monarch - Roof | CT: New Britain - Creed Monarch | CT | AF | PowerTrack