## Year to Date
Mira corp |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 975378 | 1017642.287 | -42264.287 | -4.153% | 964395.73 | 10982.27 | 1.139%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hartford Landfill - MIRA | CT | 975378 | 1017642.287 | -42264.287 | -4.153% | 964395.73 | 10982.27 | 1.139%

## 1st Qtr
Mira corp |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 297920 | 343589.248 | -45669.248 | -13.29% | 211861.36 | 86058.64 | 40.62%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hartford Landfill - MIRA | CT | 297920 | 343589.248 | -45669.248 | -13.29% | 211861.36 | 86058.64 | 40.62%

## 2nd Qtr
Mira corp |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 446150 | 427927.409 | 18222.591 | 4.258% | 391942 | 54208 | 13.83%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hartford Landfill - MIRA | CT | 446150 | 427927.409 | 18222.591 | 4.258% | 391942 | 54208 | 13.83%

## 3rd Qtr
Mira corp |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 231308 | 246125.63 | -14817.63 | -6.02% | 360592.37 | -129284.37 | -35.85%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hartford Landfill - MIRA | CT | 231308 | 246125.63 | -14817.63 | -6.02% | 360592.37 | -129284.37 | -35.85%

## 4th Qtr
Mira corp |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hartford Landfill - MIRA | CT | 0 | 0 | 0 |  |  | 0

## Jan
Mira corp |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 41663 | 74856.53 | -33193.53 | -44.34% | 50532.47 | -8869.47 | -17.55%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT | 41663 | 74856.53 | -33193.53 | -44.34% | 50532.47 | -8869.47 | -17.55%

## Feb
Mira corp |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 119806 | 131605.5 | -11799.5 | -8.966% | 65926.89 | 53879.11 | 81.73%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT | 119806 | 131605.5 | -11799.5 | -8.966% | 65926.89 | 53879.11 | 81.73%

## Mar
Mira corp |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 136451 | 137127.218 | -676.218 | -0.4931% | 95402 | 41049 | 43.03%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT | 136451 | 137127.218 | -676.218 | -0.4931% | 95402 | 41049 | 43.03%

## Apr
Mira corp |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 134516 | 131059.989 | 3456.011 | 2.637% | 117814 | 16702 | 14.18%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT | 134516 | 131059.989 | 3456.011 | 2.637% | 117814 | 16702 | 14.18%

## May
Mira corp |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 152521 | 144951.06 | 7569.94 | 5.222% | 132517 | 20004 | 15.1%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT | 152521 | 144951.06 | 7569.94 | 5.222% | 132517 | 20004 | 15.1%

## Jun
Mira corp |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 159113 | 151916.36 | 7196.64 | 4.737% | 141611 | 17502 | 12.36%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT | 159113 | 151916.36 | 7196.64 | 4.737% | 141611 | 17502 | 12.36% | 1. The site was offline from 06/03 at 14:00 to 06/04 at 16:45 due to utility planned outage | 1. SR085463

## Jul
Mira corp |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 144798 | 143057.8 | 1740.2 | 1.216% | 138883.9 | 5914.1 | 4.258%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT | 144798 | 143057.8 | 1740.2 | 1.216% | 138883.9 | 5914.1 | 4.258% | 1. Inverter 1 derating approximately from 120kW from 07/02 to 07/25. 2. Site tripped offline at 11:00AM on 07/13 and back online at 12:15PM on 07/14. | 1. SR087284, SR087331 2. SR087562

## Aug
Mira corp |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 79114 | 84536.48 | -5422.48 | -6.414% | 124538.6 | -45424.6 | -36.47%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT | 79114 | 84536.48 | -5422.48 | -6.414% | 124538.6 | -45424.6 | -36.47% | 1. Site is offline from 19:30 to 22:15 on 08/05. 2. Site is offline from 10:15AM to 12:15PM on 08/17. 3. Site is offline from 08/19. | 1. SR088663 2. SR089043 3. SR089989

## Sep
Mira corp |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 7396 | 18531.35 | -11135.35 | -60.09% | 97169.87 | -89773.87 | -92.39%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT | 7396 | 18531.35 | -11135.35 | -60.09% | 97169.87 | -89773.87 | -92.39% | 1. Site is offline from 08/19 and back online on 09/23 and inverter 1 is offline from 09/23. 2. Site had a brief outage from 11:00AM to 13:00 on 09/26. | 1. SR089989 2. SR091299

## Oct
Mira corp |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT

## Nov
Mira corp |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT

## Dec
Mira corp |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hartford Landfill - MIRA | CT

## Sites
Portfolio: | Mira corp
Site DAS Name | Site | State | Update | DAS
Hartford Landfill | CT: Hartford Landfill - MIRA | CT | AEF | PowerTrack