## Year to Date
Northbridge Companies |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 271416.766 | 101776.67 | 169640.096 | 166.7% | 226893.647 | 44523.119 | 19.62%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 220457.641 | 0 | 220457.641 |  | 0 | 220457.641 | 0%
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 50959.125 | 101776.67 | -50817.545 | -49.93% | 226893.647 | -800.245 | -0.3527%

## 1st Qtr
Northbridge Companies |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 103813.125 | 101776.67 | 2036.455 | 2.001% | 51759.37 | 52053.755 | 100.6%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 52854 | 0 | 52854 |  | 0 | 52854 | 0%
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 50959.125 | 101776.67 | -50817.545 | -49.93% | 51759.37 | -800.245 | -1.546%

## 2nd Qtr
Northbridge Companies |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 179147.875 | 39400.597 | 139747.278 | 354.7% | 90253.421 | 88894.454 | 98.49%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 86836 | 0 | 86836 |  | 0 | 86836
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 92311.875 | 39400.597 | 52911.278 | 134.3% | 90253.421 | 2058.454 | 2.281%

## 3rd Qtr
Northbridge Companies |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 166061.891 | 41443.071 | 124618.82 | 300.7% | 84880.856 | 81181.035 | 95.64%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 80767.641 | 0 | 80767.641 |  | 0 | 80767.641
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 85294.25 | 41443.071 | 43851.179 | 105.8% | 84880.856 | 413.394 | 0.487%

## 4th Qtr
Northbridge Companies |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 0 | 0 | 0 |  |  | 0
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 0 | 0 | 0 |  |  | 0

## Jan
Northbridge Companies |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 21075.625 | 38443.42 | -17367.795 | -45.18% | 13191.29 | 7884.335 | 59.77%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 11182 | 0 | 11182 |  | 0 | 11182
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 9893.625 | 38443.42 | -28549.795 | -74.26% | 13191.29 | -3297.665 | -25% | 1. Known for bad WMS readings due to that expected data values are high. | 1. SR061954

## Feb
Northbridge Companies |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 35551.5 | 35585.25 | -33.75 | -0.09484% | 16281.08 | 19270.42 | 118.4%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 18304 | 0 | 18304 |  | 0 | 18304
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 17247.5 | 35585.25 | -18337.75 | -51.53% | 16281.08 | 966.42 | 5.936% | 1. Inverter 2.3 is offline on 02/23/2024 and back online on 02/24 2. Known for bad WMS readings due to that expected data values are high. | 1. SR081278 2. SR061954

## Mar
Northbridge Companies |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 47186 | 27748 | 19438 | 70.05% | 22287 | 24899 | 111.7%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 23368 | 0 | 23368 |  | 0 | 23368
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 23818 | 27748 | -3930 | -14.16% | 22287 | 1531 | 6.869% | 1. Known for bad WMS readings due to that expected data values are high. | 1. SR061954

## Apr
Northbridge Companies |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 52168.075 | 16380.983 | 35787.092 | 218.5% | 26573.546 | 25594.529 | 96.32%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 25670.2 | 0 | 25670.2 |  | 0 | 25670.2
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 26497.875 | 16380.983 | 10116.892 | 61.76% | 26573.546 | -75.671 | -0.2848% | 1. Known for bad weather station readings due to that expected data values are low. | 1. SR061954

## May
Northbridge Companies |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 59284.8 | 14530.614 | 44754.186 | 308% | 31133.875 | 28150.925 | 90.42%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 28622.8 | 0 | 28622.8 |  | 0 | 28622.8
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 30662 | 14530.614 | 16131.386 | 111% | 31133.875 | -471.875 | -1.516% | 1. Known for bad weather station readings due to that expected data values are low. | 1. SR061954

## Jun
Northbridge Companies |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 67695 | 8489 | 59206 | 697.4% | 32546 | 35149 | 108%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 32543 | 0 | 32543 |  | 0 | 32543
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 35152 | 8489 | 26663 | 314.1% | 32546 | 2606 | 8.007% | 1. Known for bad weather station readings due to that expected data values are low. | 1. SR061954

## Jul
Northbridge Companies |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 56183.125 | 13963.361 | 42219.764 | 302.4% | 31018.196 | 25164.929 | 81.13%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 26973 | 0 | 26973 |  | 0 | 26973
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 29210.125 | 13963.361 | 15246.764 | 109.2% | 31018.196 | -1808.071 | -5.829% | 1. Known for bad weather station readings due to that expected data values are low. | 1.SR061954

## Aug
Northbridge Companies |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 60854 | 17409 | 43445 | 249.6% | 28301 | 32553 | 115%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 29632 | 0 | 29632 |  | 0 | 29632
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 31222 | 17409 | 13813 | 79.34% | 28301 | 2921 | 10.32% | 1.Known for bad weather station readings due to that expected data values are low. | 1. SR061954

## Sep
Northbridge Companies |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 49024.766 | 10070.71 | 38954.056 | 386.8% | 25561.66 | 23463.106 | 91.79%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA | 24162.641 | 0 | 24162.641 |  | 0 | 24162.641
MA: North Dartmouth - 293 Cross St (Array 2) | MA | 24862.125 | 10070.71 | 14791.415 | 146.9% | 25561.66 | -699.535 | -2.737% | 1.Known for bad weather station readings due to that expected data values are low. | 1. SR061954

## Oct
Northbridge Companies |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA
MA: North Dartmouth - 293 Cross St (Array 2) | MA

## Nov
Northbridge Companies |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA
MA: North Dartmouth - 293 Cross St (Array 2) | MA

## Dec
Northbridge Companies |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: North Dartmouth - 293 Cross St (Array 1) | MA
MA: North Dartmouth - 293 Cross St (Array 2) | MA

## Sites
Portfolio: | Northbridge Companies
Site DAS Name | Site | State | Update | DAS
MA - Northbridge Array 1 | MA: North Dartmouth - 293 Cross St (Array 1) | MA |  | Inaccess
Northbridge Array 2 | MA: North Dartmouth - 293 Cross St (Array 2) | MA |  | PowerTrack