## Year to Date
MRWSSD - Park City UT |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 141126.5426 | 291286.137 | -150159.5944 | -51.55% | 229851.957 | -88725.4144 | -38.6%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
UT: Park City - Signal Hill Floating | UT | 141126.5426 | 291286.137 | -150159.5944 | -51.55% | 229851.957 | -88725.4144 | -38.6%

## 1st Qtr
MRWSSD - Park City UT |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 48618.7926 | 193662.907 | -145044.1144 | -74.9% | 144124.173 | -95505.3804 | -66.27%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
UT: Park City - Signal Hill Floating | UT | 48618.7926 | 193662.907 | -145044.1144 | -74.9% | 144124.173 | -95505.3804 | -66.27%

## 2nd Qtr
MRWSSD - Park City UT |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 92507.75 | 97623.23 | -5115.48 | -5.24% | 85727.784 | 6779.966 | 7.909%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
UT: Park City - Signal Hill Floating | UT | 92507.75 | 97623.23 | -5115.48 | -5.24% | 85727.784 | 6779.966 | 7.909%

## 3rd Qtr
MRWSSD - Park City UT |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
UT: Park City - Signal Hill Floating | UT | 0 | 0 | 0 |  | 0 | 0

## 4th Qtr
MRWSSD - Park City UT |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
UT: Park City - Signal Hill Floating | UT | 0 | 0 | 0 |  | 0 | 0

## Jan
MRWSSD - Park City UT |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 43.9766 | 56044.05 | -56000.0734 | -99.92% | 29841.08 | -29797.1034 | -99.85%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT | 43.9766 | 56044.05 | -56000.0734 | -99.92% | 29841.08 | -29797.1034 | -99.85% | 1. Inverters dropping in and out of production regularly from 12/03. Inverters were reset on 01/23 but the production is still down as the site is covered in snow | 1. SR093826

## Feb
MRWSSD - Park City UT |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 7566.488 | 56459.036 | -48892.548 | -86.6% | 45282.364 | -37715.876 | -83.29%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT | 7566.488 | 56459.036 | -48892.548 | -86.6% | 45282.364 | -37715.876 | -83.29% | 1. Inverters have been dropping in and out of production since 12/03. They were reset on 01/23, but production remained down due to snow coverage. On 02/25/25, the site returned to expected production after the weather event. | 1. SR093826

## Mar
MRWSSD - Park City UT |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 41008.328 | 81159.821 | -40151.493 | -49.47% | 69000.729 | -27992.401 | -40.57%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT | 41008.328 | 81159.821 | -40151.493 | -49.47% | 69000.729 | -27992.401 | -40.57% | 1. Inverter 3 tripped offline from 8:30 AM to 9:30 AM on 04/20, reporting 'AC Low Voltage Detected.' After a remote reset, the inverter came back online. 2. Inverters 1, 2, and 3 tripped offline from 7:00 AM to 9:30 AM on 04/26, reporting 'High AC Voltage Detected.' After a remote reset, all inverters came back online. Additionally, Inverters 2 and 3 have been experiencing multiple tripping events during peak hours since 03/25/25 due to fan faults. Fan replacements are underway for all three inverters. 3. Site production was low due to snow on 03/06 to 03/09. | 1. SR093826, SR098814 2. SR098999 | SR098814 | SR098999

## Apr
MRWSSD - Park City UT |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 92507.75 | 97623.23 | -5115.48 | -5.24% | 85727.784 | 6779.966 | 7.909%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT | 92507.75 | 97623.23 | -5115.48 | -5.24% | 85727.784 | 6779.966 | 7.909% | 1.Inverters 1, 2, and 3 have been tripping off during midday high irradiance, reporting 'External Fan Damaged' on the Solectria portal. The fans are currently under replacement for all three inverters. | 1. SR099020

## May
MRWSSD - Park City UT |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT

## Jun
MRWSSD - Park City UT |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT

## Jul
MRWSSD - Park City UT |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT

## Aug
MRWSSD - Park City UT |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT

## Sep
MRWSSD - Park City UT |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT

## Oct
MRWSSD - Park City UT |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT

## Nov
MRWSSD - Park City UT |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT

## Dec
MRWSSD - Park City UT |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
UT: Park City - Signal Hill Floating | UT

## Sites
Portfolio: | MRWSSD - Park City UT
Site DAS Name | Site | State | Update | DAS
Signal Hill WTP | UT: Park City - Signal Hill Floating | UT | AEF | PowerTrack