## Service Request
Owner | Asset | Site Equipment | kW Down | Date | Description | Account Manager | Pending | Priority | Summary | Request | D365 Project
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 83 Pawnee CT - Inverter 26 | 5 | 2025-04-28 13:28 | 04/28/25 - Inverter 26 stopped communicating 4/22. Production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR100557
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 13 - Inverter 17 | 7 | 2025-04-28 13:15 | 04/28/25 - Inverter 17 stopped communicating 4/23. Production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR100543
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Satellite - 2 Gemini Dr - Inverter 24 | 5 | 2025-03-19 14:58 | 04/09/25-Issue still exists 03/19/25 Inverter 24 stopped communicating on 3/16. Production not confirmed. Reporting AC voltage surge. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR098772
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 185 Harvard - Inverter 28 | 6 | 2025-03-11 11:49 | 04/09/25- Issue still exists 03/11/25 - Inverter 28 stopped communicating 2/28. Production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR098386
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 235 Harvard - Inverter 56 | 7 | 2025-02-25 13:06 | 04/09/25- Issue still exists. 03/05/25 - Issue still exists. 02/25/25 - Inverter 56 stopped communicating 2/19. Production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR097766
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Dottin Place 1 - Amanda Ave Bldg 12 (92) - Inverter 6 | 5 | 2025-02-18 14:46 | 04/09/25 -Issue still exists. 03/05/25 -Issue still exists. 02/18/25 Inverter 6 stopped communicating 2/10/25, production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR097346
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 21 - Inverter 11 | 7 | 2025-01-02 14:55 | 04/09/25- Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/02/25 Inverter 11 stopped communicating 12/24. Production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR095246 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 23 - Inverter 10 | 7 | 2025-01-02 14:53 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/02/25 Inverter 10 stopped communicating 12/24. Production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR095244 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 29 - Inverter 5 | 7 - approximately | 2024-11-18 12:33 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists. 11/18/24 Inverter 5 stopped communicating on 10/31. Possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR093379
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Adams St - 14 Adams St - Inverter 2 | 14.4 | 2024-11-17 12:32 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists 12/02/24 - Issue still exists 11/17/24 Inverter 2 tripped offline 11/5 | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR093350
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Adams St - 14 Adams St - Inverter 1 | 14.4 | 2024-11-17 12:31 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists. 12/02/24 - Issue still exists. 11/17/24 Inverter 1 tripped offline 11/5 | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR093349
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 113 Mashpee CT - Inverter 45 | 7 | 2024-10-29 13:34 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists. 10/29/24 Inv 45 stopped communicating 10/22. Production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR092738
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 28 Monroe Dr Bldg 16 - Inverter 17 | 9 | 2024-10-16 13:04 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists. 10/16/24 Inverter 17 tripped offline at 4pm on 10/8. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR092211
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 150 Hathaway - Inverter 5 | 7 | 2024-10-15 13:09 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - issue still exists. 10/15/24 Inverter 5 stopped communicating 10/7. Production not confirmed | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR092164
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 22 - Inverter 12 | 7 | 2024-07-16 13:22 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 7/16/24 Inverter 12 stopped communicating on 7/6/24. Production is not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087778
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 131 Dakota CT - Inverter 38 | 7 | 2024-07-15 15:29 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 7/15/24 Inverter 38 stopped communicating on 7/6/24, production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087728
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 155 Gay Head CT - Inverter 33 | 7 | 2024-07-15 15:27 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 7/15/24 Inverter 33 stopped communicating on 7/6/24, production not confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087727
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 7 - Inverter 4 | 7 | 2024-07-02 13:00 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - issue still exists. 7/2/24: Inverter 4 stopped communicating on 5/2, cannot confirm production. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087282
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 138 Dakota CT (Now 149 Dakota CT) - Inverter 52 | 5 | 2024-06-28 14:51 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Still an issue. 01/08/25 - Still an issue. 6/28/24 Inverter 52 is not communicating since 4/21, possibly offline | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087105
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Satellite - 83 Libra Dr - Inverter 8 | 6 | 2024-06-27 14:37 | 04/09/25 - Issue still exists. 03/19/24 - Inv 8 has stopped communicating 3/15. Possibly offline. 06/27/24 - Inv 8 is not communicating, possibly offline. Last data 5/12. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087049
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 58 Yale - Inverter 49 | 5 | 2024-06-03 12:37 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 6/3/24 - inverter 49 stopped communicating on 5/25/24; possibly offline. | Amanda Harper | Pending Return Visit | PV Monitoring - Minor | Ameresco UM - Inverter Troubleshooting | SR085484 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring |  | 23.4 | 2024-05-17 12:41 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/09/25 - Issue still exists. 01/08/25 - Issue still exists. 5/17/24 - Presidential inverters 18, 27 have stopped communicating, possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR084807 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring |  | 21.8 | 2024-05-11 13:39 | 04/09/25 - Inverter 4,5 still an issue. 03/05/25 - Issue still exists. 02/09/25 - Inverter 4 still an issue. 01/08/25 - Inverters 6,15 and 16 resolved & Inverter 4 still an issue. 06/03/24 - invs 15 and 16 regained comms, invs 4 and 6 still have no comms. 05/11/24 - Westlawn inverters 4, 6, 15, 16 stopped communicating, possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure | SR084580 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 105 Navaho CT - Inverter 46 | 5 | 2024-04-19 12:51 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 4/19 - Inverter 46 is not communicating, possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR083627 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 88 Malden - Inverter 27 | 7 - inverter comms ? | 2024-03-21 12:45 | 04/09/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 12/02/24 - Issue still exists. 11/7/24 - Inverter 27 stopped communicating, possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR082331 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 310 Mt-Pleasant St Bldg 2 - Inverter 1 | 14.4 | 2024-03-04 12:57 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Still an issue. 01/08/25 - Inverter 1 is still in offline. 3/4 - Inverter 1 is offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR081556 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 240 Harvard - Inverter 46 | 6 | 2024-03-04 12:55 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 3/4 - Inverter 46 at Brickenwood is offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR081555 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Dottin Place 1 - Amanda Ave Bldg 7 (82) - Inverter 9 | - | 2024-03-01 15:01 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 12/1 - inverter 9 stopped communicating, possibly offline. 3/1 - Inverter 9 stopped communicating, possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR081508 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 135 Dakota CT - Inverter 12 | 7 - inverter comms ? | 2024-03-01 14:56 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 12/02/24 - 03/01/24 - Inverter 12 lost communications; production cannot be confirmed. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR081505 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 33 - Inverter 26 | 3 - Inverter comms ? | 2024-03-01 14:54 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 12/01/24 - Inverter last communicated 10/03/24. 03/01/24 - Inverter 26 is not communicating. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR081504 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 45 - Inverter 23 | 10 | 2024-02-20 14:04 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 2/20/24 - Inverter 23 stopped communicating; cannot confirm production. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR081129 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Adams St - 14 Adams St - Inverter 3 | 14.4 | 2023-12-31 04:44 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 12/02/24 - Inverter 3 is offline (re-occurring issue). 12/31/23 - Inverter 3 is offline and reporting "Isolation Fault". | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR079845 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 21 Mohawk CT - Inverter 8 | 7 - inverter comms ? | 2023-11-07 12:49 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 12/02/24 - Inverter 8 last communicated 7/6/24 11/07/23 - Inverter 8 stopped communicating, possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR078119 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 111 Mashpee CT - Inverter 49 | 6 | 2023-10-17 03:39 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 10/17/23 - Inverter 49 is not communicating from 07/09, possibly offline | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR077517 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Satellite - 90 Libra Dr - Inverter 11 | 6 | 2023-10-05 14:16 | 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 10/5/23 - Inverter 11 stopped communicating, possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure | SR077287 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 161 Gay Head CT - Inverter 54 | 6 - ? | 2023-09-08 12:40 | 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 7/3/2024 - Inverter stopped communicating 6/26/24 10/17/2023 - Inverter is communicating from 10/03 9/8 - Inverter stopped communicating, possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR075876 | 1006999.001
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Adams St - 14 Adams St - Inverter 4 | 14.4 | 2023-08-31 14:53 | 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 12/02/24 - Inverter is offline (re-occurring issue). 10/16/23 - Inverter is still offline. 08/31/23 - Inverter 4 tripped offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR075642 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 121 Mashpee CT - Inverter 25 | 7.6 | 2023-08-09 12:46 | 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 10/17/2023 - Inverter is still not reporting, possibly offline 8/9 - Inverter 25 stopped communicating. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR074887 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 45 Cherokee CT - Inverter 37 | 6 | 2023-07-13 12:37 | 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 10/17/2023 - Inverter is still not communicating from 07/10, possibly offline 7/13 - Inverter 37 stopped communicating, possibly offline. S/N: 73086310-EE | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Communications Failure | SR073825 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 190 Harvard - Inverter 35 | 10 | 2023-07-11 13:59 | 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 10/17/23 - Inverter 35 is still offline 07/11/23 - Inverter 35 tripped offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR073743 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Dottin Place 1 - Amanda Ave Bldg 5 (61) - Inverter 4 | 6 | 2023-07-07 04:52 | 04/09/25 -Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 07/07/2023 - Inverter 4 tripped offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR073621 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 240 Harvard - Inverter 46 | 7.6 | 2023-05-22 14:23 | 04/09/25 -Issue still exists 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 05/22/23 - Inverter 46 tripped offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR071782 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 63 Apache CT - Inverter 42 | 5 | 2023-05-09 14:11 | 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 10/17/2023 - Inverter is still not communicating from 05/07, possibly offline 5/9 - Inverter 42 stopped communicating, possibly offline. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR071467 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 157 Gay Head CT - Inverter 51 | 7 | 2023-04-25 14:19 | 04/09/25 -Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 4/25 - Shawmut Village inverter 51 no comms today. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR071089
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 67 Apache CT - Inverter 48 | 7.6 | 2023-04-21 12:34 | 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 10/17/2023 - Inverter is still not communicating from 04/11, possibly offline 4/21 - Inverter 48 stopped communicating. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR070992 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 119 Fillmore St Bldg 9 - Inverter 21 | 9 - approximately | 2023-01-03 12:33 | 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists 10/17/23 - Issue still exists 04/03/23 - Issue still exists. 01/03/23 - Inverter 21 lost communications on 8/23/22. | Amanda Harper |  | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR068143 | 1006999
Total

## Sites
Monthly Site Performance Summary
Account: | Ameresco
Report's period: | 04/01/2025 - 04/30/2025
Sites: | Manually selected sites
# of sites: | 11
Generated on: | 05/06/2025 02:42
Site Information | [6 empty] | Open Alerts | Current Month |  |  | Previous Month |  |  | Same month last year |  |  | Previous twelve months
# | Site Name | Country | State | City | Installation Date | Peak Power (kWp) | Highest Alert Impact | kWh | kWh/kWp | Revenue | kWh | kWh/kWp | Revenue | kWh | kWh/kWp | Revenue | kWh | kWh/kWp | Revenue
1 | NBHA Adams st | United States | Massachusetts | New Bedford | 12/01/2020 | 69.255 | 5 | 0 | 0 |  | 0 | 0 |  | 5418.3 | 78.2 |  | 40138.8 | 579.6
2 | NBHA Ben Rose | United States | Massachusetts | New Bedford | 03/03/2022 | 152.425 | 2 | 17641 | 115.7 |  | 16071.2 | 105.4 |  | 15742.3 | 103.3 |  | 179405.2 | 1177
3 | NBHA Brickenwood | United States | Massachusetts | New Bedford | 03/01/2022 | 572.325 | 6 | 60043 | 104.9 |  | 54751.4 | 95.7 |  | 60102.5 | 105 |  | 652183.7 | 1139.5
4 | NBHA Chaffee Fairfield | United States | Massachusetts | New Bedford | 07/29/2020 | 49.4 | 0 | 5879.1 | 119 |  | 5360.2 | 108.5 |  | 5734.4 | 116.1 |  | 60909.6 | 1233
5 | NBHA DeMedeiros | United States | Massachusetts | New Bedford | 01/10/2022 | 64.35 | 0 | 7548 | 117.3 |  | 6655.3 | 103.4 |  | 5548.6 | 86.2 |  | 67057 | 1042.1
6 | NBHA Dottin Place 1 | United States | Massachusetts | New Bedford | 07/29/2020 | 88.4 | 0 | 7116.8 | 80.5 |  | 6377.6 | 72.1 |  | 9177.8 | 103.8 |  | 92442.3 | 1045.7
7 | NBHA Hillside | United States | Massachusetts | New Bedford | 06/28/2021 | 117 | 0 | 13627.3 | 116.5 |  | 12324.7 | 105.3 |  | 13057.2 | 111.6 |  | 142072.7 | 1214.3
8 | NBHA Presidential | United States | Massachusetts | New Bedford | 09/12/2021 | 468.65 | 2 | 41626.8 | 88.8 |  | 39136.4 | 83.5 |  | 40129 | 85.6 |  | 456363.3 | 973.8
9 | NBHA Satellite | United States | Massachusetts | New Bedford | 11/18/2021 | 169 | 2 | 17724.4 | 104.9 |  | 17348 | 102.7 |  | 15831.6 | 93.7 |  | 164338.2 | 972.4
10 | NBHA Shawmut Village | United States | Massachusetts | New Bedford | 10/21/2020 | 443.625 | 5 | 35199.7 | 79.3 |  | 33206.5 | 74.9 |  | 41489.2 | 93.5 |  | 380651.5 | 858
11 | NBHA Westlawn | United States | Massachusetts | New Bedford | 03/03/2022 | 267.8 | 2 | 23067.3 | 86.1 |  | 20391.5 | 76.1 |  | 27096.5 | 101.2 |  | 261567.5 | 976.7
Total | [5 empty] | 2462.23 |  | 229473.4 |  |  | 211622.8 |  |  | 239327.4 |  |  | 2497129.8