## Year to Date
LX International America, Inc. |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 953174.84 | 91746.11 | 861428.73 | 938.9% | 0 | 953174.84 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu City - Police Station | AZ | 378453.75 | 0 | 378453.75 |  | 0 | 92331
AZ: Lake Havasu City - Aquatic Center | AZ | 365731.5 | 0 | 365731.5 |  | 0 | 104664
AZ: Lake Havasu City - City Hall | AZ | 131703.2 | 0 | 131703.2 |  | 0 | 36787.25
AZ: Lake Havasu City - Public Works | AZ | 77286.39 | 91746.11 | -14459.72 | -15.76% | 0 | 24017.23

## 1st Qtr
LX International America, Inc. |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 257799.48 | 27680.89 | 230118.59 | 831.3% | 0 | 257799.48 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu City - Police Station | AZ | 92331 | 0 | 92331 |  | 0 | 92331
AZ: Lake Havasu City - Aquatic Center | AZ | 104664 | 0 | 104664 |  | 0 | 104664
AZ: Lake Havasu City - City Hall | AZ | 36787.25 | 0 | 36787.25 |  | 0 | 36787.25
AZ: Lake Havasu City - Public Works | AZ | 24017.23 | 27680.89 | -3663.66 | -13.24% | 0 | 24017.23

## 2nd Qtr
LX International America, Inc. |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 420551.17 | 40339.22 | 380211.95 | 942.5% | 0 | 420551.17 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu City - Police Station | AZ | 166551.25 | 0 | 166551.25 |  | 0 | 0
AZ: Lake Havasu City - Aquatic Center | AZ | 161103 | 0 | 161103 |  | 0 | 0
AZ: Lake Havasu City - City Hall | AZ | 58469.25 | 0 | 58469.25 |  | 0 | 0
AZ: Lake Havasu City - Public Works | AZ | 34427.67 | 40339.22 | -5911.55 | -14.65% | 0 | 0

## 3rd Qtr
LX International America, Inc. |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 274824.19 | 23726 | 251098.19 | 1058% | 0 | 274824.19 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu City - Police Station | AZ | 119571.5 | 0 | 119571.5 |  | 0 | 0
AZ: Lake Havasu City - Aquatic Center | AZ | 99964.5 | 0 | 99964.5 |  | 0 | 0
AZ: Lake Havasu City - City Hall | AZ | 36446.7 | 0 | 36446.7 |  | 0 | 0
AZ: Lake Havasu City - Public Works | AZ | 18841.49 | 23726 | -4884.51 | -20.59% | 0 | 0

## 4th Qtr
LX International America, Inc. |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Lake Havasu City - Police Station | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: Lake Havasu City - Aquatic Center | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: Lake Havasu City - City Hall | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: Lake Havasu City - Public Works | AZ | 0 | 0 | 0 |  | 0 | 0

## Jan
LX International America, Inc. |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 69692 | 8421 | 61271 | 727.6% | 0 | 69692 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ | 23363 | 0 | 23363 |  | 0 | 23363 |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976, SR092908 | SR092908
AZ: Lake Havasu City - Aquatic Center | AZ | 29390 | 0 | 29390 |  | 0 | 29390 |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. 2. Site was taken offline from 10:00 AM to 2:00PM on 01/09/25 to replace the inverter 1 conductor and make the inverter 1 fully operational. 3. Site was taken offline from 9:00AM to 12:00PM on 01/15/25 to perform an Annual Preventative Maintenance Inspection. | 1. SR094976 2. SR086609 3. PM8296 | SR086609
AZ: Lake Havasu City - City Hall | AZ | 10074 | 0 | 10074 |  | 0 | 10074 |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. 2. Site was taken offline from 9:15AM to 11:15AM on 01/07/25 to perform an Annual Preventative Maintenance Inspection. | 1.SR094976 2. PM8361
AZ: Lake Havasu City - Public Works | AZ | 6865 | 8421 | -1556 | -18.48% | 0 | 6865 |  | 1. Site was taken offline from 09:00AM to 11:15AM on 01/06/25 to perform an Annual Preventative Maintenance Inspection. | 1. PM8441

## Feb
LX International America, Inc. |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 82790.47 | 8632.1 | 74158.37 | 859.1% | 0 | 82790.47 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ | 30567.75 | 0 | 30567.75 |  | 0 | 30567.75 |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976, SR092908 | SR092908
AZ: Lake Havasu City - Aquatic Center | AZ | 32984.5 | 0 | 32984.5 |  | 0 | 32984.5 |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1. SR094976
AZ: Lake Havasu City - City Hall | AZ | 11625.5 | 0 | 11625.5 |  | 0 | 11625.5 |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1. SR094976
AZ: Lake Havasu City - Public Works | AZ | 7612.72 | 8632.1 | -1019.38 | -11.81% | 0 | 7612.72 |  | 1. All Lake Havasu sites experienced a poor production day on 02/13/25, yet only the Public Works has a functioning Weather Station, therefore it kicked the difference.

## Mar
LX International America, Inc. |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 105317.01 | 10627.79 | 94689.22 | 891% | 0 | 105317.01 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ | 38400.25 | 0 | 38400.25 |  | 0 | 38400.25 |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976, SR092908 | SR092908
AZ: Lake Havasu City - Aquatic Center | AZ | 42289.5 | 0 | 42289.5 |  | 0 | 42289.5 |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - City Hall | AZ | 15087.75 | 0 | 15087.75 |  | 0 | 15087.75 |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - Public Works | AZ | 9539.51 | 10627.79 | -1088.28 | -10.24% | 0 | 9539.51 |  | 1.The weather station reported irradiance spikes of 5697 W/m² during non-production hours on 03/14 and 03/16 ,03/19 and after that did not reoccurred.

## Apr
LX International America, Inc. |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 128046.13 | 13026.05 | 115020.08 | 883% | 0 | 128046.13 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ | 46332 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976, SR092908 | SR092908
AZ: Lake Havasu City - Aquatic Center | AZ | 51606 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - City Hall | AZ | 18635 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - Public Works | AZ | 11473.13 | 13026.05 | -1552.92 | -11.92% | N/A |  |  | 1.The weather station reported irradiance spike of 5697 W/m² during non-production hours on 04/08 and a spike of 6611 W/m² on 04/17 during production hours. We are working with Asset planner team on this issue. | 1. SR100810

## May
LX International America, Inc. |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 140743.04 | 13586 | 127157.04 | 935.9% | 0 | 140743.04 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ | 54988.25 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1. SR094976, SR092908 | SR092908
AZ: Lake Havasu City - Aquatic Center | AZ | 54353 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1. SR094976
AZ: Lake Havasu City - City Hall | AZ | 19897.25 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1. SR094976
AZ: Lake Havasu City - Public Works | AZ | 11504.54 | 13586 | -2081.46 | -15.32% | N/A |  |  | 1.The weather station reported irradiance spike of 5697 W/m² during non-production hours and a spike of 6611 W/m² during production hours. The issue was resolved on 05/01 after Asset planner added a filter to block these erraneous readings. | 1. SR100810

## Jun
LX International America, Inc. |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 151762 | 13727.17 | 138034.83 | 1006% | 0 | 151762 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ | 65231 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976, SR092908 | SR092908
AZ: Lake Havasu City - Aquatic Center | AZ | 55144 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - City Hall | AZ | 19937 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - Public Works | AZ | 11450 | 13727.17 | -2277.17 | -16.59% | N/A |  |  | 1. We don’t have inverter communications or CB data; therefore, we’re unable to confirm the energy differential between actual and expected values.

## Jul
LX International America, Inc. |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 147170.19 | 13633 | 133537.19 | 979.5% | 0 | 147170.19 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ | 63511.5 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976, SR092908 | SR092908
AZ: Lake Havasu City - Aquatic Center | AZ | 53265.5 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - City Hall | AZ | 19439.7 | N/A |  |  | N/A |  |  | 1.Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - Public Works | AZ | 10953.49 | 13633 | -2679.51 | -19.65% | N/A |  |  | 1. We don’t have inverter communications or CB data; therefore, we’re unable to confirm the energy differential between actual and expected values.

## Aug
LX International America, Inc. |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 127654 | 10093 | 117561 | 1165% | 0 | 127654 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ | 56060 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976, SR092908 | SR092908
AZ: Lake Havasu City - Aquatic Center | AZ | 46699 | N/A |  |  | N/A |  |  | 1. Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - City Hall | AZ | 17007 | N/A |  |  | N/A |  |  | 1.Weather station has not been reporting since 10/29/2024 due to the replacement of the GHI sensor and POA sensor. | 1.SR094976
AZ: Lake Havasu City - Public Works | AZ | 7888 | 10093 | -2205 | -21.85% | N/A |  |  | 1.Site stopped communicating at 11:00 MST on 08/26 and production cannot be confirmed. Site modem is offline. 2.We don’t have inverter communications or CB data; therefore, we’re unable to confirm the energy differential between actual and expected values. | 1. SR106981

## Sep
LX International America, Inc. |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ
AZ: Lake Havasu City - Aquatic Center | AZ
AZ: Lake Havasu City - City Hall | AZ
AZ: Lake Havasu City - Public Works | AZ

## Oct
LX International America, Inc. |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ
AZ: Lake Havasu City - Aquatic Center | AZ
AZ: Lake Havasu City - City Hall | AZ
AZ: Lake Havasu City - Public Works | AZ

## Nov
LX International America, Inc. |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ
AZ: Lake Havasu City - Aquatic Center | AZ
AZ: Lake Havasu City - City Hall | AZ
AZ: Lake Havasu City - Public Works | AZ

## Dec
LX International America, Inc. |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Lake Havasu City - Police Station | AZ
AZ: Lake Havasu City - Aquatic Center | AZ
AZ: Lake Havasu City - City Hall | AZ
AZ: Lake Havasu City - Public Works | AZ

## Sites
Portfolio: | LX International America, Inc.
Site DAS Name | Site | State | Update | DAS
AZ: Lake Havasu City - Police Station | AZ: Lake Havasu City - Police Station | AZ
AZ: Lake Havasu City - Aquatic Center | AZ: Lake Havasu City - Aquatic Center | AZ
AZ: Lake Havasu City - City Hall | AZ: Lake Havasu City - City Hall | AZ
AZ: Lake Havasu City - Public Works | AZ: Lake Havasu City - Public Works | AZ