## Year to Date
RMR Group |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 165646.995 | 105890.6621 | 59756.3329 | 56.43% | 0 | 165646.995 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA - Newton RMR | MA | 165646.995 | 105890.6621 | 59756.3329 | 56.43% | 0 | 165646.995

## 1st Qtr
RMR Group |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 41253.093 | 40356.014 | 897.079 | 2.223% | 0 | 41253.093 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA - Newton RMR | MA | 41253.093 | 40356.014 | 897.079 | 2.223% | 0 | 41253.093

## 2nd Qtr
RMR Group |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 88768.423 | 37069.85 | 51698.573 | 139.5% | 0 | 88768.423 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA - Newton RMR | MA | 88768.423 | 37069.85 | 51698.573 | 139.5% | 0 | 88768.423

## 3rd Qtr
RMR Group |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 35625.479 | 28464.7981 | 7160.6809 | 25.16% | 0 | 35625.479 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA - Newton RMR | MA | 35625.479 | 28464.7981 | 7160.6809 | 25.16% | 0 | 35625.479

## 4th Qtr
RMR Group |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA - Newton RMR | MA | 0 | 0 | 0 |  | 0 | 0

## Jan
RMR Group |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 9261.793 | 15145.214 | -5883.421 | -38.85% | 0 | 9261.793 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA | 9261.793 | 15145.214 | -5883.421 | -38.85% | 0 | 9261.793 |  | 1.Low generation due to weather/snow.

## Feb
RMR Group |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 7778.7 | 15467.3 | -7688.6 | -49.71% | 0 | 7778.7 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA | 7778.7 | 15467.3 | -7688.6 | -49.71% | 0 | 7778.7 |  | 1. Low generation due to weather/snow

## Mar
RMR Group |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 24212.6 | 9743.5 | 14469.1 | 148.5% | 0 | 24212.6 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA | 24212.6 | 9743.5 | 14469.1 | 148.5% | 0 | 24212.6 |  | 1.The Site Expected Energy data reporting intermittently throughout the month due to site communication issues in the Unity portal. | 1. SR098457,SR092283 | SR092283

## Apr
RMR Group |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 28950.2 | 5305.19 | 23645.01 | 445.7% | 0 | 28950.2 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA | 28950.2 | 5305.19 | 23645.01 | 445.7% | 0 | 28950.2 |  | 1.Expected energy data reporting intermittently throughout the month due to site communication issue | 1.SR092283

## May
RMR Group |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 27649.523 | 8317.7 | 19331.823 | 232.4% | 0 | 27649.523 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA | 27649.523 | 8317.7 | 19331.823 | 232.4% | 0 | 27649.523 |  | 1.Expected energy data reporting intermittently throughout the month due to site communication issue | 1. SR092283

## Jun
RMR Group |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 32168.7 | 23446.96 | 8721.74 | 37.2% | 0 | 32168.7 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA | 32168.7 | 23446.96 | 8721.74 | 37.2% | 0 | 32168.7 |  | 1.Expected energy data reporting intermittently throughout the month due to site communication issue | 1. SR092283

## Jul
RMR Group |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 35625.479 | 28464.7981 | 7160.6809 | 25.16% | 0 | 35625.479 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA | 35625.479 | 28464.7981 | 7160.6809 | 25.16% | 0 | 35625.479 |  | 1.Expected energy data reporting intermittently throughout the month due to site communication issue | 1.SR092283

## Aug
RMR Group |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA

## Sep
RMR Group |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA

## Oct
RMR Group |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA

## Nov
RMR Group |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA

## Dec
RMR Group |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA - Newton RMR | MA

## Sites
Portfolio: | RMR Group
Site DAS Name | Site | State | Update | DAS
MA - Newton RMR | MA - Newton RMR | MA |  | InAccess