## Year to Date
Accel International |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 138287.24 | 0 | 138287.24 | 0% | 143182.347 | -4895.107 | -3.419%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Meriden - Accel International | CT | 138287.24 | 0 | 138287.24 |  | 143182.347 | 1883.348 | 1.315%

## 1st Qtr
Accel International |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 138287.24 | 0 | 138287.24 | 0% | 143182.347 | -4895.107 | -3.419%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Meriden - Accel International | CT | 138287.24 | 0 | 138287.24 |  | 143182.347 | 1883.348 | 1.315%

## 2nd Qtr
Accel International |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Meriden - Accel International | CT | 0 | 0 | 0 |  | 0 | 0

## 3rd Qtr
Accel International |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Meriden - Accel International | CT | 0 | 0 | 0 |  | 0 | 0

## 4th Qtr
Accel International |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Meriden - Accel International | CT | 0 | 0 | 0 |  | 0 | 0

## Jan
Accel International |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 32483.76 | 0 | 32483.76 | 0% | 34863.274 | -2379.514 | -6.825%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT | 32483.76 | 0 | 32483.76 |  | 34863.274 |  | 0% | 1.Inverter 14 was being RMA'D since 06/10/24. On 01/29/25 technician replaced dc relay board and fan the inverter back online at 11:15 and producing in line with its peers. 2.Inverter 9 was being RMA'D since 09/23/24. On 01/29/25 technician replaced dc relay board and fan the inverter back online at 11:15 and producing in line with its peers. | 1.SR085759 2.SR091076

## Feb
Accel International |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 39758.94 | 0 | 39758.94 | 0% | 44157.881 | -4398.941 | -9.962%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT | 39758.94 | 0 | 39758.94 |  | 44157.881 |  | 0% | 1.Inverter 1 tripped offline from 02/13 at 10AM due to 03x9B/Error in SolarEdge and offline through out the month. On 02/19 technician checked-in and RMA'D failed DC relay board. | 1.SR096986

## Mar
Accel International |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 66044.54 | 0 | 66044.54 | 0% | 64161.192 | 1883.348 | 2.935%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT | 66044.54 | 0 | 66044.54 |  | 64161.192 | 1883.348 | 2.935% | 1.Inverter 1 tripped offline from 02/13 at 10AM due to 03x9B/Error in SolarEdge and offline through out the month. On 03/14 technician checked in and RMA'D the inverter. | 1.SR096986

## Apr
Accel International |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT |  | 0

## May
Accel International |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT |  | 0

## Jun
Accel International |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT |  | 0

## Jul
Accel International |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT |  | 0

## Aug
Accel International |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT |  | 0

## Sep
Accel International |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT |  | 0

## Oct
Accel International |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT |  | 0

## Nov
Accel International |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT |  | 0

## Dec
Accel International |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Meriden - Accel International | CT |  | 0

## Sites
Portfolio: | Accel International
Site DAS Name | Site | State | Update | DAS
Accel International | CT: Meriden - Accel International | CT | AF | PowerTrack