## Year to Date
City of Flagstaff |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 303553 | 201520.79 | 102032.21 | 50.63% | 0 | 303553 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: COF Aquaplex | AZ | 98142 | 0 | 98142 | 0% | 0 | 0 | 0%
AZ: COF Sun Bear | AZ | 89479 | 85578.54 | 3900.46 | 4.558% | 0 | 0 | 0%
AZ: COF Rio de Flag | AZ | 115932 | 115942.25 | -10.25 | -0.008841% | 0 | 0 | 0%

## 1st Qtr
City of Flagstaff |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 303553 | 201520.79 | 102032.21 | 50.63% | 0 | 303553 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: COF Aquaplex | AZ | 98142 | 0 | 98142 |  | 0 | 0 | 0%
AZ: COF Sun Bear | AZ | 89479 | 85578.54 | 3900.46 | 4.558% | 0 | 0 | 0%
AZ: COF Rio de Flag | AZ | 115932 | 115942.25 | -10.25 | -0.008841% | 0 | 0 | 0%

## 2nd Qtr
City of Flagstaff |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: COF Aquaplex | AZ | 0 | 0 | 0 |  |  | 0
AZ: COF Sun Bear | AZ | 0 | 0 | 0 |  |  | 0
AZ: COF Rio de Flag | AZ | 0 | 0 | 0 |  |  | 0

## 3rd Qtr
City of Flagstaff |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: COF Aquaplex | AZ | 0 | 0 | 0 |  |  | 0
AZ: COF Sun Bear | AZ | 0 | 0 | 0 |  |  | 0
AZ: COF Rio de Flag | AZ | 0 | 0 | 0 |  |  | 0

## 4th Qtr
City of Flagstaff |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: COF Aquaplex | AZ | 0 | 0 | 0 |  |  | 0
AZ: COF Sun Bear | AZ | 0 | 0 | 0 |  |  | 0
AZ: COF Rio de Flag | AZ | 0 | 0 | 0 |  |  | 0

## Jan
City of Flagstaff |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 98127 | 63044 | 35083 | 55.65% | 0 | 98127 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ | 30434 | N/A |  | 0% | N/A
AZ: COF Sun Bear | AZ | 28362 | 27169 | 1193 | 4.391% | N/A |  |  | 1. Inverter 2 has been underproducing approximately 30 kW since 11/20 compared to Inverter 1. The fuse in Inverter 2 need to be replaced | 1. SR093473, SR093907 & SR094608
AZ: COF Rio de Flag | AZ | 39331 | 35875 | 3456 | 9.633% | N/A

## Feb
City of Flagstaff |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 105979 | 70189.06 | 35789.94 | 50.99% | 0 | 105979 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ | 33130 | N/A |  |  | N/A
AZ: COF Sun Bear | AZ | 29874 | 28804.46 | 1069.54 | 3.713% | N/A |  |  | 1. Inverter 2 has been underproducing approximately 30 kW since 11/20 compared to Inverter 1. The fuse in Inverter 2 needs to be replaced. | 1. SR093473, SR093907 | SR093907
AZ: COF Rio de Flag | AZ | 42975 | 41384.6 | 1590.4 | 3.843% | N/A

## Mar
City of Flagstaff |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 99447 | 68287.73 | 31159.27 | 45.63% | 0 | 99447 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ | 34578 | N/A |  |  | N/A
AZ: COF Sun Bear | AZ | 31243 | 29605.08 | 1637.92 | 5.533% | N/A |  |  | 1. Inverter 2 underperforming approximately 30kW since 11/20 compared to its Peer inverter 1 due to a faulty fuse.On 03/31 technician Replaced defective fuse and re-energized system and inverter 2 back to normal and producing with its peer. | 1.SR094608,SR094373 | SR094373
AZ: COF Rio de Flag | AZ | 33626 | 38682.65 | -5056.65 | -13.07% | N/A |  |  | 1.On 03/06, Inverter 3 was operating at approximately one-third of its normal output, possibly due to snow coverage. The issue self-resolved on 03/07. Other inverters remained unaffected. Inverter 3 offline from 03/17/25 and remained offline for the rest of month. Need to investigate. | 1.SR098227

## Apr
City of Flagstaff |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ

## May
City of Flagstaff |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ

## Jun
City of Flagstaff |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ

## Jul
City of Flagstaff |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ

## Aug
City of Flagstaff |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ

## Sep
City of Flagstaff |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ

## Oct
City of Flagstaff |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ

## Nov
City of Flagstaff |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ

## Dec
City of Flagstaff |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ

## Sites
Portfolio: | City of Flagstaff
Site DAS Name | Site | State | Update | DAS
AZ: COF Aquaplex | AZ: COF Aquaplex | AZ
AZ: COF Sun Bear | AZ: COF Sun Bear | AZ
AZ: COF Rio de Flag | AZ: COF Rio de Flag | AZ