## Year to Date
Pardee (ENCAP) |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 1004744.636 | 1086389.238 | -81644.602 | -7.515% | 1083575.165 | -78830.529 | -7.275%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 21298.125 | 18845.884 | 2452.241 | 13.01% | 23742.099 | -2443.974 | -10.29%
AZ: ASU - Pardee - Farrington | AZ | 90404.8235 | 87040.22 | 3364.6035 | 3.866% | 88173.74 | 2231.0835 | 2.53%
AZ: ASU - Pardee - Macro Tech. | AZ | 214085.875 | 326130.6 | -112044.725 | -34.36% | 318970.24 | -104884.365 | -32.88%
AZ: ASU - Pardee - McCord Hall | AZ | 29492.25 | 23630.756 | 5861.494 | 24.8% | 32051.733 | -2559.483 | -7.985%
AZ: NAU - SF Garage | AZ | 180392 | 194414.138 | -14022.138 | -7.213% | 170818.653 | 9573.347 | 5.604%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 64410.1875 | 60049.91 | 4360.2775 | 7.261% | 43935.49 | 20474.6975 | 46.6%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 92152.625 | 84699.63 | 7452.995 | 8.799% | 65057.32 | 27095.305 | 41.65%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 74533.5 | 72187.7 | 2345.8 | 3.25% | 78967.29 | -4433.79 | -5.615%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 91159.5 | 73363.57 | 17795.93 | 24.26% | 82881.3 | 8278.2 | 9.988%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 75749.75 | 67144.1 | 8605.65 | 12.82% | 90651.3 | -14901.55 | -16.44%
AZ: ASU - Pardee - Sun Devil Complex | AZ | 71066 | 78882.73 | -7816.73 | -9.909% | 88326 | -17260 | -19.54%

## 1st Qtr
Pardee (ENCAP) |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 1004744.636 | 1086389.238 | -81644.602 | -7.515% | 1083575.165 | -78830.529 | -7.275%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 21298.125 | 18845.884 | 2452.241 | 13.01% | 23742.099 | -2443.974 | -10.29%
AZ: ASU - Pardee - Farrington | AZ | 90404.8235 | 87040.22 | 3364.6035 | 3.866% | 88173.74 | 2231.0835 | 2.53%
AZ: ASU - Pardee - Macro Tech. | AZ | 214085.875 | 326130.6 | -112044.725 | -34.36% | 318970.24 | -104884.365 | -32.88%
AZ: ASU - Pardee - McCord Hall | AZ | 29492.25 | 23630.756 | 5861.494 | 24.8% | 32051.733 | -2559.483 | -7.985%
AZ: NAU - SF Garage | AZ | 180392 | 194414.138 | -14022.138 | -7.213% | 170818.653 | 9573.347 | 5.604%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 64410.1875 | 60049.91 | 4360.2775 | 7.261% | 43935.49 | 20474.6975 | 46.6%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 92152.625 | 84699.63 | 7452.995 | 8.799% | 65057.32 | 27095.305 | 41.65%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 74533.5 | 72187.7 | 2345.8 | 3.25% | 78967.29 | -4433.79 | -5.615%
AZ: ASU - Pardee - Parking Lot 58 | AZ | 91159.5 | 73363.57 | 17795.93 | 24.26% | 82881.3 | 8278.2 | 9.988%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 75749.75 | 67144.1 | 8605.65 | 12.82% | 90651.3 | -14901.55 | -16.44%
AZ: ASU - Pardee - Sun Devil Complex | AZ | 71066 | 78882.73 | -7816.73 | -9.909% | 88326 | -17260 | -19.54%

## 2nd Qtr
Pardee (ENCAP) |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Farrington | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Macro Tech. | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - McCord Hall | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: NAU - SF Garage | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 11 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 19 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 41 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 58 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 59S | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Sun Devil Complex | AZ | 0 | 0 | 0 |  | 0 | 0

## 3rd Qtr
Pardee (ENCAP) |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Farrington | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Macro Tech. | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - McCord Hall | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: NAU - SF Garage | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 11 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 19 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 41 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 58 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 59S | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Sun Devil Complex | AZ | 0 | 0 | 0 |  | 0 | 0

## 4th Qtr
Pardee (ENCAP) |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: ASU - Pardee - Discovery Hall | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Farrington | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Macro Tech. | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - McCord Hall | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: NAU - SF Garage | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 11 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 19 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 41 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 58 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Parking Lot 59S | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: ASU - Pardee - Sun Devil Complex | AZ | 0 | 0 | 0 |  | 0 | 0

## Jan
Pardee (ENCAP) |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 288814.3755 | 316487.484 | -27673.1085 | -8.744% | 295930.845 | -7116.4695 | -2.405%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ | 5916.75 | 5538.374 | 378.376 | 6.832% | 6580.477 | -663.727 | -10.09% | 1. Inverter is producing at maximum 40 kW throughout the month compared to its capacity 50kW due to seasonal underperformance | 1. SR099649
AZ: ASU - Pardee - Farrington | AZ | 17359.0005 | 25551.77 | -8192.7695 | -32.06% | 24198.86 | -6839.8595 | -28.27% | 1. Meter CT was replaced on 01/13 and AlsoEnergy was able to regain meter communication from 12:00 PM on 01/13 | 1. SR094972
AZ: ASU - Pardee - Macro Tech. | AZ | 76476.625 | 96023.1 | -19546.475 | -20.36% | 89844.16 | -13367.535 | -14.88% | 1.Inverter 4 was offline from 01/21 and came back online on 01/24 at 10:30 after the blown fuse was replaced. 2. Inverter 4 offline from 01/25 and came back online on 01/29 at 10:45 after the blown fuse was replaced. | 1. SR095814 2.SR096012 , SR096160
AZ: ASU - Pardee - McCord Hall | AZ | 8385.875 | 6453.786 | 1932.089 | 29.94% | 8884.123 | -498.248 | -5.608%
AZ: NAU - SF Garage | AZ | 52716 | 57354.054 | -4638.054 | -8.087% | 45999.135 | 6716.865 | 14.6%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 18327.75 | 17757.76 | 569.99 | 3.21% | 10305.89 | 8021.86 | 77.84%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 26035.5 | 25220.52 | 814.98 | 3.231% | 15260.94 | 10774.56 | 70.6%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 19602.125 | 21279.74 | -1677.615 | -7.884% | 21672.34 | -2070.215 | -9.552% | 1. Inverter 2 was underperforming 20kW down compared to inverter 1 due to L1 SP320 cartilage needs replacement and found active ground fault on CB 2-2 string 5. | 1. PM4031, SR086964, SR086966
AZ: ASU - Pardee - Parking Lot 58 | AZ | 25842.75 | 19977.46 | 5865.29 | 29.36% | 22973.07 | 2869.68 | 12.49%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 20102.5 | 18284.13 | 1818.37 | 9.945% | 25126.85 | -5024.35 | -20% | 1.Inverter 1 is underperforming by 12kW down from 08:00 AM to 12:30 PM due to seasonal shading | 1. SR099639
AZ: ASU - Pardee - Sun Devil Complex | AZ | 18049.5 | 23046.79 | -4997.29 | -21.68% | 25085 | -7035.5 | -28.05% | 1. Inverter 1 was offline from 07:00 on 01/06 to 12:00pm on 01/24 due to failed PWR DIST Card | 1. SR094724

## Feb
Pardee (ENCAP) |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 332166.0784 | 336249.9 | -4083.8216 | -1.215% | 336219.701 | -4053.6226 | -1.206%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ | 6598.875 | 5712.358 | 886.517 | 15.52% | 7494.711 | -895.836 | -11.95% | 1. Inverter is producing at maximum 40 kW throughout the month compared to its capacity 50kW due to seasonal underperformance | 1. SR099649
AZ: ASU - Pardee - Farrington | AZ | 31007.3284 | 26810.49 | 4196.8384 | 15.65% | 27770.28 | 3237.0484 | 11.66%
AZ: ASU - Pardee - Macro Tech. | AZ | 72327.375 | 99628.9 | -27301.525 | -27.4% | 97007.78 | -24680.405 | -25.44% | 1. Inverter 4 was tripped offline at 18:15 on 02/16 due to control card assembly plus backplane. 2. Inverter 2 and meter 2 stopped communication at 11:50AM on 02/20 tech suggested that replacing the Vlink MESR901 serial server. | 1. SR095814, SR096160, SR096012 2. SR097592 | SR096160 | SR096012 | SR097592
AZ: ASU - Pardee - McCord Hall | AZ | 9147.5 | 7200.132 | 1947.368 | 27.05% | 10117.14 | -969.64 | -9.584%
AZ: NAU - SF Garage | AZ | 60795 | 63728.1 | -2933.1 | -4.603% | 53900.3 | 6894.7 | 12.79%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 20052.5 | 18203.32 | 1849.18 | 10.16% | 13387.73 | 6664.77 | 49.78%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 28758 | 25680.77 | 3077.23 | 11.98% | 19823.29 | 8934.71 | 45.07%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 23110.25 | 22043 | 1067.25 | 4.842% | 24870.34 | -1760.09 | -7.077% | 1.Inverter 2 is underperforming by 20kW down due to shading related issue. | 1. SR096743
AZ: ASU - Pardee - Parking Lot 58 | AZ | 28384.25 | 22538.77 | 5845.48 | 25.94% | 26162.83 | 2221.42 | 8.491%
AZ: ASU - Pardee - Parking Lot 59S | AZ | 23550 | 20628.14 | 2921.86 | 14.16% | 28615.3 | -5065.3 | -17.7% | 1.Inverter 1 is underperforming by 12kW down from 08:00 AM to 12:30 PM due to seasonal shading | 1. SR099639
AZ: ASU - Pardee - Sun Devil Complex | AZ | 28435 | 24075.92 | 4359.08 | 18.11% | 27070 | 1365 | 5.042% | 1. Inverter 2 having multiple tripping events on 02/25 and 02/27. | 1. SR097804

## Mar
Pardee (ENCAP) |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 383764.1821 | 433651.854 | -49887.6719 | -11.5% | 451424.619 | -67660.4369 | -14.99%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ | 8782.5 | 7595.152 | 1187.348 | 15.63% | 9666.911 | -884.411 | -9.149%
AZ: ASU - Pardee - Farrington | AZ | 42038.4946 | 34677.96 | 7360.5346 | 21.23% | 36204.6 | 5833.8946 | 16.11%
AZ: ASU - Pardee - Macro Tech. | AZ | 65281.875 | 130478.6 | -65196.725 | -49.97% | 132118.3 | -66836.425 | -50.59% | 1.Inverter 4 was offline from 18:20 on 02/16 to 22:20 on 03/25. On 03/25, a Bold technician was onsite to replace the controller card and Upon arrival he found a worn DC shunt harness, which was requested for replacement. The inverter went offline again at 18:45 on 03/26 and requires additional components for full restoration. 2. Inverter 2 and meter 2 stopped communicating at 11:50AM on 02/20 and production can't be confirmed.On 02/24 upon troubleshooting ,technician recommends replacing the Vlink MESR901 serial server | 1.SR096012,SR096160 2.SR097592 | SR096160 | SR097592
AZ: ASU - Pardee - McCord Hall | AZ | 11958.875 | 9976.838 | 1982.037 | 19.87% | 13050.47 | -1091.595 | -8.364%
AZ: NAU - SF Garage | AZ | 66881 | 73331.984 | -6450.984 | -8.797% | 70919.218 | -4038.218 | -5.694%
AZ: ASU - Pardee - Parking Lot 11 | AZ | 26029.9375 | 24088.83 | 1941.1075 | 8.058% | 20241.87 | 5788.0675 | 28.59%
AZ: ASU - Pardee - Parking Lot 19 | AZ | 37359.125 | 33798.34 | 3560.785 | 10.54% | 29973.09 | 7386.035 | 24.64%
AZ: ASU - Pardee - Parking Lot 41 | AZ | 31821.125 | 28864.96 | 2956.165 | 10.24% | 32424.61 | -603.485 | -1.861% | 1.Inverter 2 is underperforming by approximately 20 kW, likely due to shading related issues | 1.SR096743
AZ: ASU - Pardee - Parking Lot 58 | AZ | 36932.5 | 30847.34 | 6085.16 | 19.73% | 33745.4 | 3187.1 | 9.445% | 1. A canopy strike was reported on 01/17, prompting immediate dispatch to secure the parking lot array and document the damages. Dispatch is scheduled to return on 04/10 to install five modules, reconnect homeruns, and re-energize the string. | 1.SR095815
AZ: ASU - Pardee - Parking Lot 59S | AZ | 32097.25 | 28231.83 | 3865.42 | 13.69% | 36909.15 | -4811.9 | -13.04% | 1.Inverter 1 is underperforming by 12kW down from 08:00 AM to 12:30 PM due to seasonal shading | 1. SR099639
AZ: ASU - Pardee - Sun Devil Complex | AZ | 24581.5 | 31760.02 | -7178.52 | -22.6% | 36171 | -11589.5 | -32.04% | 1. Inverter 2 tripped offline at 15:45 on 03/02 and was restored at 16:10 on 03/03 after a technician restart. It went offline again on 03/23 due to a "Watchdog Timer Fault." On 03/24, technicians confirmed the fault is related to internal monitoring and can be triggered by grid voltage fluctuations. The inverter was power cycled and back online at 09:10 AM on 03/24. 2. Inverter 1 tripped offline at 13:00 on 03/15/25 due to a ground fault. On 03/18, the technician observed heat marks on several Trina modules, likely impacted by recent heavy rain. A follow-up visit is required, along with replacement of 5A fuses. | 1.SR097804,SR098900 2.SR098620 | SR098900 | SR098620

## Apr
Pardee (ENCAP) |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## May
Pardee (ENCAP) |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Jun
Pardee (ENCAP) |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Jul
Pardee (ENCAP) |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Aug
Pardee (ENCAP) |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Sep
Pardee (ENCAP) |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ

## Oct
Pardee (ENCAP) |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actual data is taken from inverters data since meter lost communication from 08/22

## Sites
Portfolio: | Pardee (ENCAP)
Site DAS Name | Site | State | Update | DAS
AZ: ASU - Pardee - Discovery Hall | AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ: ASU - Pardee - Sun Devil Complex | AZ

## Nov
Pardee (ENCAP) |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actual data is taken from inverters data since meter lost communication from 08/22

## Dec
Pardee (ENCAP) |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: ASU - Pardee - Discovery Hall | AZ
AZ: ASU - Pardee - Farrington | AZ
AZ: ASU - Pardee - Macro Tech. | AZ
AZ: ASU - Pardee - McCord Hall | AZ
AZ: NAU - SF Garage | AZ
AZ: ASU - Pardee - Parking Lot 11 | AZ
AZ: ASU - Pardee - Parking Lot 19 | AZ
AZ: ASU - Pardee - Parking Lot 41 | AZ
AZ: ASU - Pardee - Parking Lot 58 | AZ
AZ: ASU - Pardee - Parking Lot 59S | AZ
AZ: ASU - Pardee - Sun Devil Complex | AZ
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actual data is taken from inverters data since meter lost communication from 08/22