## Year to Date
Greenbaker Capital |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 1356780.5239 | 2492033.6121 | -1135253.0882 | -45.56% | 1525093.9239 | -168313.4 | -11.04%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 1356780.5239 | 2492033.6121 | -1135253.0882 | -45.56% | 1525093.9239 | -986281.9361 | -64.67%

## 1st Qtr
Greenbaker Capital |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 0 | 0 | 0 |  | 0 | 0

## 2nd Qtr
Greenbaker Capital |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 0 | 0 | 0 |  | 0 | 0

## 3rd Qtr
Greenbaker Capital |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 986677.5239 | 1858006.6284 | -871329.1045 | -46.9% | 860568.1639 | 126109.36 | 14.65%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 986677.5239 | 1858006.6284 | -871329.1045 | -46.9% | 860568.1639 | -691859.1761 | -80.4%

## 4th Qtr
Greenbaker Capital |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 370103 | 634026.9837 | -263923.9837 | -41.63% | 664525.76 | -294422.76 | -44.31%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 370103 | 634026.9837 | -263923.9837 | -41.63% | 664525.76 | -294422.76 | -44.31%

## Jan
Greenbaker Capital |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ

## Feb
Greenbaker Capital |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ

## Mar
Greenbaker Capital |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ

## Apr
Greenbaker Capital |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ

## May
Greenbaker Capital |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ

## Jun
Greenbaker Capital |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ

## Jul
Greenbaker Capital |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 352821 | 731357.3616 | -378536.3616 | -51.76% | 641267.71 | -288446.71 | -44.98%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 352821 | 731357.3616 | -378536.3616 | -51.76% | 641267.71 | -288446.71 | -44.98% | 1. Numerous inverters lost communication on 03/03, possibly due to being offline. Many of these inverters appear to be duplicates. Additionally, the Block 4 inverters have been offline since 07/24 due to a datalogger fault, which requires further troubleshooting. Inverter 1 has been offline since 03/10, and its communication board is currently being RMA’d. 2. Site was offline at 10:10 0n 07/30 due to billing mix up with Verizon and remained offline. | 1. SR097964 2. SR105456 | SR105456

## Aug
Greenbaker Capital |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 350363.5239 | 633412.458 | -283048.9341 | -44.69% | 0 | 350363.5239 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 350363.5239 | 633412.458 | -283048.9341 | -44.69% | 584166.03 | -233802.5061 | -40.02% | 1. Numerous inverters lost communication on 03/03, possibly due to being offline. Many of these inverters appear to be duplicates. Additionally, the Block 4 inverters have been offline since 07/24 due to a datalogger fault, which requires further troubleshooting. Inverter 1 has been offline since 03/10, and its communication board is currently being RMA’d. 2. Inverters 4-03 and 6-09 are offline on 8/18 on 08/26 technician checked in and found that 3 inverters without production and restored 2. remaining inverter need further troubleshooting. | 1. SR097964 2. SR106854, SR105456 | SR106854 | SR105456

## Sep
Greenbaker Capital |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 283493 | 493236.8088 | -209743.8088 | -42.52% | 453102.96 | -169609.96 | -37.43%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 283493 | 493236.8088 | -209743.8088 | -42.52% | 453102.96 | -169609.96 | -37.43% | 1. Numerous inverters lost communication on 03/03, possibly due to being offline. Many of these inverters appear to be duplicates. Additionally, the Block 4 inverters have been offline since 07/24 due to a datalogger fault, which requires further troubleshooting. Inverter 1 has been offline since 03/10, and its communication board is currently being RMA’d. 2. Inverter S/N ending 1195 was offline for whole month. 3. Inverter 1.3 has tripped offline at 13:20 on 09/18 and was back online on 09/24 at 07:00 | 1. SR097964 2. SR106854, SR105456 3. SR108260 | SR106854 | SR105456 | SR108260

## Oct
Greenbaker Capital |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 231582 | 405866.1596 | -174284.1596 | -42.94% | 377886.4 | -146304.4 | -38.72%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 231582 | 405866.1596 | -174284.1596 | -42.94% | 377886.4 | -146304.4 | -38.72% | 1. Numerous inverters lost communication on 03/03, possibly due to being offline. Many of these inverters appear to be duplicates. Additionally, the Block 4 inverters have been offline since 07/24 due to a datalogger fault, which requires further troubleshooting. 2. Inverter S/N ending 1195 was back online at 10/16. 3. Inverters 1–21 and 22, Inverter 2–21 and 22, Inverter 3–15, Inverter 4–6, Inverter 5–3, and Inverter 6–3 have been offline since 10/22. | 1. SR097964 2. SR106854, SR105456 3. SR109924 | 1. Closed 2. Closed 3. Pending | SR106854 | SR105456 | SR109924

## Nov
Greenbaker Capital |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 138521 | 228160.8241 | -89639.8241 | -39.29% | 286639.36 | -148118.36 | -51.67%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
NJ: Camden - Cambell Soup (Roof Parkade) | NJ | 138521 | 228160.8241 | -89639.8241 | -39.29% | 286639.36 | -148118.36 | -51.67% | 1. Inverters 1–21 and 22, Inverters 2–21 and 22, Inverters 3–15, Inverters 4–6, Inverter 5–3, and Inverter 6–3 had been offline since 10/22. On 11/24, after the technician replaced the RMA’d communications board, all inverters came back online and are now producing as expected. | 1 SR109924 | 1. Pending

## Dec
Greenbaker Capital |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
NJ: Camden - Cambell Soup (Roof Parkade) | NJ

## Sites
Portfolio: | Greenbaker Capital
Site DAS Name | Site | State | Update | DAS
BNB Camden [0821] | NJ: Camden - Cambell Soup (Roof Parkade) | NJ | AEF | PF Drive