## Service requests
Customer | Asset | Site Equipment | kW Down | Date | Description | Account Manager | Pending | Priority | Summary | Request | D365 Project
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Satellite - 83 Libra Dr - Inverter 8 | 6 | 2025-09-30 12:26 | 09/30/25 - Inverter 8 stopped communicating. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR108769
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 16 Malden - Inverter 19 | 6 | 2025-09-30 12:19 | 09/30/25 - Inverter 19 stopped communicating. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR108767
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Ben Rose - 871 S Water St - Inverter 3 | 6 | 2025-09-24 13:06 | 09/24/25 - Inverter 3 stopped communicating. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR108469
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 164 Van-Buren St Bldg 8 - Inverter 32 | 9 | 2025-09-24 13:02 | 09/24/25 - Inverter 32 stopped communicating, production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR108468
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 164 Van-Buren St Bldg 8 - Inverter 18 | 9 | 2025-09-24 12:58 | 09/24/25 - Inverter 18 stopped communicating. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR108467
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 150 Hathaway - Inverter 5 | 6 | 2025-09-15 12:46 | 09/15/25 - Inverter 5 stopped communicating. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR107976
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 59 Malden - Inverter 24 | 6 | 2025-09-02 16:26 | 09/08/25 - Still an issue. 09/02/25 - Inverter 24 stopped communicating. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR107318
New Bedford Housing Authority | MA: New Bedford – HA Monitoring |  | 7.6 | 2025-09-02 16:24 | 09/08/25 - Issue still exists. Brickenwood inverter 16 stopped communicating. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR107316
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 79 Pawnee CT - Inverter 19 | 7.6 | 2025-09-02 16:05 | 09/08/25 - Issue still exists. 09/02/25 - Inverter 19 stopped communicating. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR107314
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 42 Yale - Inverter 39 | 7.6 | 2025-08-07 13:07 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 08/07/25 - Inverter 39 tripped offline at 11am on 7/28. Reporting internal error. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR105843
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Dottin Place 1 - Amanda Ave Bldg 7 (82) - Inverter 9 | 10 | 2025-07-30 14:08 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/30/25 - Inverter 9 stopped communicating 7/21. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR105365
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 132 Hathaway - Inverter 8 | 7.5 | 2025-07-30 13:51 | 09/08/25 - Still an issue. 07/30/25 - Inverter 8 stopped communicating 7/25 | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR105362
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 219 Harvard - Inverter 53 | 5 | 2025-06-16 12:31 | 09/08/25 - Issue still exists. 08/07/25 - Issue still exists. 07/07/25 - Issue still exists. 06/16/25 - Inverter 53 stopped communicating 6/8. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR103023
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 35 Yale - Inverter 58 | 8 | 2025-06-09 12:46 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/10/25 - Still an issue. 06/09/25 - Inverter 58 stopped communicating on 6/3. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR102700
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 61 Apache CT - Inverter 50 | 5 | 2025-06-03 12:48 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/04/25 - Still an issue. 06/03/25 - Inverter 50 stopped communicating 5/26. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR102390
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Chaffee/Fairfield - 975 Fairfield St 1E - Inverter 3 | 6 | 2025-05-19 14:54 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/19/25 - Inverter 3 tripped offline 5/12. Reporting internal error. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR101683
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 13 Yale - Inverter 48 | 5 | 2025-05-13 14:39 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/13/25 - Inverter 48 stopped communicating 5/10. Production not confirmed. Reporting Power Limitation. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco Production Not Confirmed - Site Outage | SR101400
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 83 Pawnee CT - Inverter 26 | 5 | 2025-04-28 13:28 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/04/25 - Issue still exists 05/09/25 - Issue still exists 04/28/25 - Inverter 26 stopped communicating 4/22. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR100557
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 235 Harvard - Inverter 56 | 7 | 2025-02-25 13:06 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25- Issue still exists. 04/09/25- Issue still exists. 03/05/25 - Issue still exists. 02/25/25 - Inverter 56 stopped communicating 2/19. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR097766
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Dottin Place 1 - Amanda Ave Bldg 12 (92) - Inverter 6 | 5 | 2025-02-18 14:46 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 -Issue still exists. 03/05/25 -Issue still exists. 02/18/25 Inverter 6 stopped communicating 2/10/25, production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco - Inverter Troubleshooting | SR097346
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Adams St - 14 Adams St - Inverter 2 | 14.4 | 2024-11-17 12:32 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/08/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists 12/02/24 - Issue still exists 11/17/24 Inverter 2 tripped offline 11/5 | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR093350
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Adams St - 14 Adams St - Inverter 1 | 14.4 | 2024-11-17 12:31 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/08/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists. 12/02/24 - Issue still exists. 11/17/24 Inverter 1 tripped offline 11/5 | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR093349
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 113 Mashpee CT - Inverter 45 | 7 | 2024-10-29 13:34 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/04/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists. 10/29/24 Inv 45 stopped communicating 10/22. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR092738
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 28 Monroe Dr Bldg 16 - Inverter 17 | 9 | 2024-10-16 13:04 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/08/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists. 10/16/24 Inverter 17 tripped offline at 4pm on 10/8. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR092211
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 99 Navaho CT - Inverter 24 | 6 | 2024-08-12 12:41 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/26/25 - Inverter 24 stopped communicating 06/18/25. Production not confirmed. 04/10/25 - Inverter 24 resumed communicating 04/05/25. 03/31/25 - Inverter 24 stopped communicating 03/23/25. Production not confirmed. 08/12/24 - Inverter 24 stopped communicating 08/05/24. Production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR088926
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 155 Gay Head CT - Inverter 33 | 7 | 2024-07-15 15:27 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/04/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 7/15/24 Inverter 33 stopped communicating on 7/6/24, production not confirmed. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087727
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 7 - Inverter 4 | 7 | 2024-07-02 13:00 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - issue still exists. 7/2/24: Inverter 4 stopped communicating on 5/2, cannot confirm production. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR087282
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 58 Yale - Inverter 49 | 5 | 2024-06-03 12:37 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 6/3/24 - inverter 49 stopped communicating on 5/25/24; possibly offline. | Amanda Harper | EPC Completion | PV Monitoring - Minor | Ameresco UM - Inverter Troubleshooting | SR085484 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring |  | 23.4 | 2024-05-17 12:41 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 08/06/25 - Inverter 18 resumed communicating on 8/1 at 8pm. Inverter 27 still not communicating. 07/08/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/09/25 - Issue still exists. 01/08/25 - Issue still exists. 5/17/24 - Presidential inverters 18, 27 have stopped communicating, possibly offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR084807 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring |  | 21.8 | 2024-05-11 13:39 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/08/25 - Issue still exists. 06/05/25 - Inverter 5 resolved & Inverter 4 still an issue. 05/09/25 - Issue still exists. 04/09/25 - Inverter 4,5 still an issue. 03/05/25 - Issue still exists. 02/09/25 - Inverter 4 still an issue. 01/08/25 - Inverters 6,15 and 16 resolved & Inverter 4 still an issue. 06/03/24 - invs 15 and 16 regained comms, invs 4 and 6 still have no comms. 05/11/24 - Westlawn inverters 4, 6, 15, 16 stopped communicating, possibly offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Communications Failure | SR084580 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 88 Malden - Inverter 27 | 7 - inverter comms ? | 2024-03-21 12:45 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 12/02/24 - Issue still exists. 11/7/24 - Inverter 27 stopped communicating, possibly offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR082331 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 310 Mt-Pleasant St Bldg 2 - Inverter 1 | 14.4 | 2024-03-04 12:57 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/08/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Still an issue. 01/08/25 - Inverter 1 is still in offline. 3/4 - Inverter 1 is offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR081556 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 240 Harvard - Inverter 46 | 6 | 2024-03-04 12:55 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 3/4 - Inverter 46 at Brickenwood is offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR081555 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 33 - Inverter 26 | 3 - Inverter comms ? | 2024-03-01 14:54 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 12/01/24 - Inverter last communicated 10/03/24. 03/01/24 - Inverter 26 is not communicating. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR081504 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Westlawn - 197 Liberty St Bldg 45 - Inverter 23 | 10 | 2024-02-20 14:04 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 2/20/24 - Inverter 23 stopped communicating; cannot confirm production. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Communications Failure / Production Not Confirmed | SR081129 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Adams St - 14 Adams St - Inverter 3 | 14.4 | 2023-12-31 04:44 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/08/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 12/02/24 - Inverter 3 is offline (re-occurring issue). 12/31/23 - Inverter 3 is offline and reporting "Isolation Fault". | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR079845 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 111 Mashpee CT - Inverter 49 | 6 | 2023-10-17 03:39 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/04/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 10/17/23 - Inverter 49 is not communicating from 07/09, possibly offline | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR077517 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Satellite - 90 Libra Dr - Inverter 11 | 6 | 2023-10-05 14:16 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists. 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 10/5/23 - Inverter 11 stopped communicating, possibly offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Communications Failure | SR077287 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Adams St - 14 Adams St - Inverter 4 | 14.4 | 2023-08-31 14:53 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/08/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 -Issue still exists 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 12/02/24 - Inverter is offline (re-occurring issue). 10/16/23 - Inverter is still offline. 08/31/23 - Inverter 4 tripped offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR075642 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 121 Mashpee CT - Inverter 25 | 7.6 | 2023-08-09 12:46 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/04/25 - Issue still exists. 05/09/25 - Issue still exists 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 10/17/2023 - Inverter is still not reporting, possibly offline 8/9 - Inverter 25 stopped communicating. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR074887 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 45 Cherokee CT - Inverter 37 | 6 | 2023-07-13 12:37 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/04/25 - Issue still exists. 05/09/25 - Issue still exists 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 10/17/2023 - Inverter is still not communicating from 07/10, possibly offline 7/13 - Inverter 37 stopped communicating, possibly offline. S/N: 73086310-EE | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Communications Failure | SR073825 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 190 Harvard - Inverter 35 | 10 | 2023-07-11 13:59 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 - Issue still exists 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 10/17/23 - Inverter 35 is still offline 07/11/23 - Inverter 35 tripped offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR073743 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Brickenwood - 240 Harvard - Inverter 46 | 7.6 | 2023-05-22 14:23 | 09/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 -Issue still exists 04/09/25 -Issue still exists 03/05/25 - Issue still exists. 02/08/25 - Issue still exists. 01/08/25 - Issue still exists. 05/22/23 - Inverter 46 tripped offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR071782 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 63 Apache CT - Inverter 42 | 5 | 2023-05-09 14:11 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/04/25 - Issue still exists. 05/09/25 - Issue still exists 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 10/17/2023 - Inverter is still not communicating from 05/07, possibly offline 5/9 - Inverter 42 stopped communicating, possibly offline. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR071467 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Shawmut Village - 67 Apache CT - Inverter 48 | 7.6 | 2023-04-21 12:34 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/07/25 - Issue still exists. 06/04/25 - Issue still exists. 05/09/25 -Issue still exists 04/09/25 - Issue still exists 03/05/25 - Issue still exists. 02/08/2025 - Issue still exists. 01/08/2025 - Issue still exists. 10/17/2023 - Inverter is still not communicating from 04/11, possibly offline 4/21 - Inverter 48 stopped communicating. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR070992 | 1006999
New Bedford Housing Authority | MA: New Bedford – HA Monitoring | Presidential - 119 Fillmore St Bldg 9 - Inverter 21 | 9 - approximately | 2023-01-03 12:33 | 09/08/25 - Issue still exists. 08/08/25 - Issue still exists. 07/08/25 - Issue still exists. 06/05/25 - Issue still exists. 05/09/25 -Issue still exists 04/09/25 - Issue still exists. 03/05/25 - Issue still exists. 02/08/25 - Issue still exists 01/08/25 - Issue still exists 10/17/23 - Issue still exists 04/03/23 - Issue still exists. 01/03/23 - Inverter 21 lost communications on 8/23/22. | Amanda Harper | Pending Subcontractor Completion | PV-Monitoring-ROC | Ameresco UM - Inverter Troubleshooting | SR068143 | 1006999
Total

## Sites
Monthly Site Performance Summary
Account: | Ameresco
Report Period: | From 9/1/25 to 9/30/25
Sites: | Manually selected sites
Number of Sites: | 11
Generated on: | 10/7/25, 1:20 AM
Site Information | [7 empty] | Open Alerts | Current Month |  | Previous Month |  | Same Month Last Year |  | Previous Twelve Months
| Site Name | Site ID | Country | State | City | Installation Date | Peak Power (kWp) | Highest Alert Impact | kWh | kWh/kWp | kWh | kWh/kWp | kWh | kWh/kWp | kWh | kWh/kWp
1 | NBHA Adams st | 2484387 | United States | Massachusetts | New Bedford | 12/1/20 | 69.26 | 5 | 0 | 0 | 0 | 0 | 4,660.14 | 67.29 | 9,101.19 | 131.42
2 | NBHA Ben Rose | 2752799 | United States | Massachusetts | New Bedford | 3/3/22 | 152.43 | 5 | 14,949.11 | 98.08 | 22,207.01 | 145.69 | 15,391.48 | 100.98 | 183,715.73 | 1,205.29
3 | NBHA Brickenwood | 2747637 | United States | Massachusetts | New Bedford | 3/1/22 | 572.33 | 6 | 50,762.29 | 88.69 | 66,619.74 | 116.4 | 53,710.02 | 93.85 | 630,647.8 | 1,101.91
4 | NBHA Chaffee Fairfield | 1735612 | United States | Massachusetts | New Bedford | 7/29/20 | 49.4 | 2 | 4,410.98 | 89.29 | 5,378.35 | 108.87 | 5,152.22 | 104.3 | 56,007.67 | 1,133.76
5 | NBHA DeMedeiros | 2660184 | United States | Massachusetts | New Bedford | 1/10/22 | 64.35 | 2 | 6,810.52 | 105.84 | 9,291.61 | 144.39 | 6,624.17 | 102.94 | 77,657.98 | 1,206.81
6 | NBHA Dottin Place 1 | 1735791 | United States | Massachusetts | New Bedford | 7/29/20 | 88.4 | 2 | 7,221.94 | 81.7 | 9,910.04 | 112.1 | 8,231.98 | 93.12 | 82,610.51 | 934.51
7 | NBHA Hillside | 2331864 | United States | Massachusetts | New Bedford | 6/28/21 | 117 | 2 | 12,494.97 | 106.79 | 16,642 | 142.24 | 12,022.44 | 102.76 | 143,364.36 | 1,225.34
8 | NBHA Presidential | 2457881 | United States | Massachusetts | New Bedford | 9/12/21 | 468.65 | 6 | 38,509.88 | 82.17 | 52,119.95 | 111.21 | 44,320.9 | 94.57 | 455,740.88 | 972.45
9 | NBHA Satellite | 2597872 | United States | Massachusetts | New Bedford | 11/18/21 | 169 | 2 | 17,677.12 | 104.6 | 18,600.73 | 110.06 | 9,363.74 | 55.41 | 177,058.97 | 1,047.69
10 | NBHA Shawmut Village | 2382372 | United States | Massachusetts | New Bedford | 10/21/20 | 443.63 | 6 | 36,626.7 | 82.56 | 38,782.83 | 87.42 | 25,630.79 | 57.78 | 354,988.4 | 800.2
11 | NBHA Westlawn | 2753485 | United States | Massachusetts | New Bedford | 3/3/22 | 267.8 | 2 | 24,181.96 | 90.3 | 28,213.06 | 105.35 | 22,979.82 | 85.81 | 239,655.14 | 894.9
Total | [6 empty] | 2,462.23 |  | 213,645.45 |  | 267,765.31 |  | 208,087.7 |  | 2,410,548.63