## Year to Date
38 DN |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 1965665.2752 | 3545725.09 | -1580059.8148 | -44.56% | 3232149.48 | -1266484.2048 | -39.18%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 128041 | 89763.77 | 38277.23 | 42.64% | 143798.9 | -15757.9 | -10.96%
Barton Acres | MA | 29694 | 107049.1 | -77355.1 | -72.26% | 68759.86 | -39065.86 | -56.81%
Bowden | MA | 69512 | 188771.7 | -119259.7 | -63.18% | 166003.7 | -96491.7 | -58.13%
Blair Wire Village | MA | 25710 | 117129.2 | -91419.2 | -78.05% | 82282.53 | -56572.53 | -68.75%
Boutilier | MA | 88425 | 276022.2 | -187597.2 | -67.96% | 188755.7 | -100330.7 | -53.15%
Cherry Valley | MA | 28918 | 126189 | -97271 | -77.08% | 75238.47 | -46320.47 | -61.56%
Cohasse | MA | 28561 | 122933.8 | -94372.8 | -76.77% | 113040.9 | -84479.9 | -74.73%
ISM Dighton Solar 2 | MA | 124498.0033 | 228179.9 | -103681.8967 | -45.44% | 193899 | -69400.9967 | -35.79%
Dudley River 1 | MA | 34973 | 98451.27 | -63478.27 | -64.48% | 82926.12 | -47953.12 | -57.83%
Dudley River 2 | MA | 37948 | 101210.3 | -63262.3 | -62.51% | 81101.73 | -43153.73 | -53.21%
Dudley River 3 | MA | 46815 | 101328.2 | -54513.2 | -53.8% | 83309.23 | -36494.23 | -43.81%
Flint Pond | MA | 13493 | 57616.02 | -44123.02 | -76.58% | 33208.85 | -19715.85 | -59.37%
Incom | MA | 58433 | 229168.4 | -170735.4 | -74.5% | 217959.3 | -159526.3 | -73.19%
JH | MA | 25125 | 125626.5 | -100501.5 | -80% | 105158.4 | -80033.4 | -76.11%
Ledeaux | MA | 24326 | 88562.29 | -64236.29 | -72.53% | 97784.09 | -73458.09 | -75.12%
Palombo A | MA | 89529 | 242420.3 | -152891.3 | -63.07% | 240167 | -150638 | -62.72%
Palombo B | MA | 41178 | 122740.4 | -81562.4 | -66.45% | 71052.02 | -29874.02 | -42.05%
St Josephs Church | MA | 30068.6 | 121421.5 | -91352.9 | -75.24% | 90617.38 | -60548.78 | -66.82%
Sunset A | MA | 13004.5 | 56404.29 | -43399.79 | -76.94% | 32370.49 | -19365.99 | -59.83%
Sunset B | MA | 10824.5 | 39293.98 | -28469.48 | -72.45% | 31984.83 | -21160.33 | -66.16%
Woodchuck | MA | 22531 | 90321.07 | -67790.07 | -75.05% | 95138.48 | -72607.48 | -76.32%
NY: Skaneateles - Spafford 1 - (PW) | NY | 240951 | 358531.6 | -117580.6 | -32.8% | 393718.7 | -152767.7 | -38.8%
NY: Skaneateles - Spafford 2 - (PW) | NY | 99727 | 133297.2 | -33570.2 | -25.18% | 163651.8 | -63924.8 | -39.06%
NY: New Hartford - 4001 NY-12 (IRA) | NY | 261323 | 323293.1 | -61970.1 | -19.17% | 380222 | -118899 | -31.27%
NY: Glenmont - Bethlehem (IRA) | NY | 392056.6719 | 0 | 392056.6719 |  | 0 | 0

## 1st Qtr
38 DN |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 1965665.2752 | 3545725.09 | -1580059.8148 | -44.56% | 3232149.48 | -1266484.2048 | -39.18%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 128041 | 89763.77 | 38277.23 | 42.64% | 143798.9 | -15757.9 | -10.96%
Barton Acres | MA | 29694 | 107049.1 | -77355.1 | -72.26% | 68759.86 | -39065.86 | -56.81%
Bowden | MA | 69512 | 188771.7 | -119259.7 | -63.18% | 166003.7 | -96491.7 | -58.13%
Blair Wire Village | MA | 25710 | 117129.2 | -91419.2 | -78.05% | 82282.53 | -56572.53 | -68.75%
Boutilier | MA | 88425 | 276022.2 | -187597.2 | -67.96% | 188755.7 | -100330.7 | -53.15%
Cherry Valley | MA | 28918 | 126189 | -97271 | -77.08% | 75238.47 | -46320.47 | -61.56%
Cohasse | MA | 28561 | 122933.8 | -94372.8 | -76.77% | 113040.9 | -84479.9 | -74.73%
ISM Dighton Solar 2 | MA | 124498.0033 | 228179.9 | -103681.8967 | -45.44% | 193899 | -69400.9967 | -35.79%
Dudley River 1 | MA | 34973 | 98451.27 | -63478.27 | -64.48% | 82926.12 | -47953.12 | -57.83%
Dudley River 2 | MA | 37948 | 101210.3 | -63262.3 | -62.51% | 81101.73 | -43153.73 | -53.21%
Dudley River 3 | MA | 46815 | 101328.2 | -54513.2 | -53.8% | 83309.23 | -36494.23 | -43.81%
Flint Pond | MA | 13493 | 57616.02 | -44123.02 | -76.58% | 33208.85 | -19715.85 | -59.37%
Incom | MA | 58433 | 229168.4 | -170735.4 | -74.5% | 217959.3 | -159526.3 | -73.19%
JH | MA | 25125 | 125626.5 | -100501.5 | -80% | 105158.4 | -80033.4 | -76.11%
Ledeaux | MA | 24326 | 88562.29 | -64236.29 | -72.53% | 97784.09 | -73458.09 | -75.12%
Palombo A | MA | 89529 | 242420.3 | -152891.3 | -63.07% | 240167 | -150638 | -62.72%
Palombo B | MA | 41178 | 122740.4 | -81562.4 | -66.45% | 71052.02 | -29874.02 | -42.05%
St Josephs Church | MA | 30068.6 | 121421.5 | -91352.9 | -75.24% | 90617.38 | -60548.78 | -66.82%
Sunset A | MA | 13004.5 | 56404.29 | -43399.79 | -76.94% | 32370.49 | -19365.99 | -59.83%
Sunset B | MA | 10824.5 | 39293.98 | -28469.48 | -72.45% | 31984.83 | -21160.33 | -66.16%
Woodchuck | MA | 22531 | 90321.07 | -67790.07 | -75.05% | 95138.48 | -72607.48 | -76.32%
NY: Skaneateles - Spafford 1 - (PW) | NY | 240951 | 358531.6 | -117580.6 | -32.8% | 393718.7 | -152767.7 | -38.8%
NY: Skaneateles - Spafford 2 - (PW) | NY | 99727 | 133297.2 | -33570.2 | -25.18% | 163651.8 | -63924.8 | -39.06%
NY: New Hartford - 4001 NY-12 (IRA) | NY | 261323 | 323293.1 | -61970.1 | -19.17% | 380222 | -118899 | -31.27%
NY: Glenmont - Bethlehem (IRA) | NY | 392056.6719 | 0 | 392056.6719 |  | 0 | 0

## 2nd Qtr
38 DN |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 0 | 0 | 0 |  | 0 | 0
Barton Acres | MA | 0 | 0 | 0 |  | 0 | 0
Bowden | MA | 0 | 0 | 0 |  | 0 | 0
Blair Wire Village | MA | 0 | 0 | 0 |  | 0 | 0
Boutilier | MA | 0 | 0 | 0 |  | 0 | 0
Cherry Valley | MA | 0 | 0 | 0 |  | 0 | 0
Cohasse | MA | 0 | 0 | 0 |  | 0 | 0
ISM Dighton Solar 2 | MA | 0 | 0 | 0 |  | 0 | 0
Dudley River 1 | MA | 0 | 0 | 0 |  | 0 | 0
Dudley River 2 | MA | 0 | 0 | 0 |  | 0 | 0
Dudley River 3 | MA | 0 | 0 | 0 |  | 0 | 0
Flint Pond | MA | 0 | 0 | 0 |  | 0 | 0
Incom | MA | 0 | 0 | 0 |  | 0 | 0
JH | MA | 0 | 0 | 0 |  | 0 | 0
Ledeaux | MA | 0 | 0 | 0 |  | 0 | 0
Palombo A | MA | 0 | 0 | 0 |  | 0 | 0
Palombo B | MA | 0 | 0 | 0 |  | 0 | 0
St Josephs Church | MA | 0 | 0 | 0 |  | 0 | 0
Sunset A | MA | 0 | 0 | 0 |  | 0 | 0
Sunset B | MA | 0 | 0 | 0 |  | 0 | 0
Woodchuck | MA | 0 | 0 | 0 |  | 0 | 0
NY: Skaneateles - Spafford 1 - (PW) | NY | 0 | 0 | 0 |  | 0 | 0
NY: Skaneateles - Spafford 2 - (PW) | NY | 0 | 0 | 0 |  | 0 | 0
NY: New Hartford - 4001 NY-12 (IRA) | NY | 0 | 0 | 0 |  | 0 | 0
NY: Glenmont - Bethlehem (IRA) | NY | 0 | 0 | 0 |  | 0 | 0

## 3rd Qtr
38 DN |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 0 | 0 | 0 |  | 0 | 0
Barton Acres | MA | 0 | 0 | 0 |  | 0 | 0
Bowden | MA | 0 | 0 | 0 |  | 0 | 0
Blair Wire Village | MA | 0 | 0 | 0 |  | 0 | 0
Boutilier | MA | 0 | 0 | 0 |  | 0 | 0
Cherry Valley | MA | 0 | 0 | 0 |  | 0 | 0
Cohasse | MA | 0 | 0 | 0 |  | 0 | 0
ISM Dighton Solar 2 | MA | 0 | 0 | 0 |  | 0 | 0
Dudley River 1 | MA | 0 | 0 | 0 |  | 0 | 0
Dudley River 2 | MA | 0 | 0 | 0 |  | 0 | 0
Dudley River 3 | MA | 0 | 0 | 0 |  | 0 | 0
Flint Pond | MA | 0 | 0 | 0 |  | 0 | 0
Incom | MA | 0 | 0 | 0 |  | 0 | 0
JH | MA | 0 | 0 | 0 |  | 0 | 0
Ledeaux | MA | 0 | 0 | 0 |  | 0 | 0
Palombo A | MA | 0 | 0 | 0 |  | 0 | 0
Palombo B | MA | 0 | 0 | 0 |  | 0 | 0
St Josephs Church | MA | 0 | 0 | 0 |  | 0 | 0
Sunset A | MA | 0 | 0 | 0 |  | 0 | 0
Sunset B | MA | 0 | 0 | 0 |  | 0 | 0
Woodchuck | MA | 0 | 0 | 0 |  | 0 | 0
NY: Skaneateles - Spafford 1 - (PW) | NY | 0 | 0 | 0 |  | 0 | 0
NY: Skaneateles - Spafford 2 - (PW) | NY | 0 | 0 | 0 |  | 0 | 0
NY: New Hartford - 4001 NY-12 (IRA) | NY | 0 | 0 | 0 |  | 0 | 0
NY: Glenmont - Bethlehem (IRA) | NY | 0 | 0 | 0 |  | 0 | 0

## 4th Qtr
38 DN |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
6th St. | CA | 0 | 0 | 0 |  | 0 | 0
Barton Acres | MA | 0 | 0 | 0 |  | 0 | 0
Bowden | MA | 0 | 0 | 0 |  | 0 | 0
Blair Wire Village | MA | 0 | 0 | 0 |  | 0 | 0
Boutilier | MA | 0 | 0 | 0 |  | 0 | 0
Cherry Valley | MA | 0 | 0 | 0 |  | 0 | 0
Cohasse | MA | 0 | 0 | 0 |  | 0 | 0
ISM Dighton Solar 2 | MA | 0 | 0 | 0 |  | 0 | 0
Dudley River 1 | MA | 0 | 0 | 0 |  | 0 | 0
Dudley River 2 | MA | 0 | 0 | 0 |  | 0 | 0
Dudley River 3 | MA | 0 | 0 | 0 |  | 0 | 0
Flint Pond | MA | 0 | 0 | 0 |  | 0 | 0
Incom | MA | 0 | 0 | 0 |  | 0 | 0
JH | MA | 0 | 0 | 0 |  | 0 | 0
Ledeaux | MA | 0 | 0 | 0 |  | 0 | 0
Palombo A | MA | 0 | 0 | 0 |  | 0 | 0
Palombo B | MA | 0 | 0 | 0 |  | 0 | 0
St Josephs Church | MA | 0 | 0 | 0 |  | 0 | 0
Sunset A | MA | 0 | 0 | 0 |  | 0 | 0
Sunset B | MA | 0 | 0 | 0 |  | 0 | 0
Woodchuck | MA | 0 | 0 | 0 |  | 0 | 0
NY: Skaneateles - Spafford 1 - (PW) | NY | 0 | 0 | 0 |  | 0 | 0
NY: Skaneateles - Spafford 2 - (PW) | NY | 0 | 0 | 0 |  | 0 | 0
NY: New Hartford - 4001 NY-12 (IRA) | NY | 0 | 0 | 0 |  | 0 | 0
NY: Glenmont - Bethlehem (IRA) | NY | 0 | 0 | 0 |  | 0 | 0

## Jan
38 DN |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 1965665.2752 | 3545725.09 | -1580059.8148 | -44.56% | 3232149.48 | -1266484.2048 | -39.18%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
6th St. | CA | 128041 | 89763.77 | 38277.23 | 42.64% | 143798.9 | -15757.9 | -10.96% | 1.Inverter 33 tripped offline from 10:30 to 15:15 on 01/13 | 1. SR114528 | 1.Closed
Barton Acres | MA | 29694 | 107049.1 | -77355.1 | -72.26% | 68759.86 | -39065.86 | -56.81% | 1.Site production was low on 01/07,01/17,01/18,01/19,01/20,01/21,01/25,01/26,01/27 due to snow
Bowden | MA | 69512 | 188771.7 | -119259.7 | -63.18% | 166003.7 | -96491.7 | -58.13% | 1.Site production was low on 01/17 and again from 01/25,01/26 due to snow
Blair Wire Village | MA | 25710 | 117129.2 | -91419.2 | -78.05% | 82282.53 | -56572.53 | -68.75% | 1.Site was offline at 06:00 on 01/08 at 07:30 on 01/09 2.Site production was low on 01/17,01/18 to 01/21 and from 01/25 due to snow | 1.SR113977 | 1.Closed
Boutilier | MA | 88425 | 276022.2 | -187597.2 | -67.96% | 188755.7 | -100330.7 | -53.15% | 1.Site production was low on 01/17,01/18 and again from 01/25 due to snow
Cherry Valley | MA | 28918 | 126189 | -97271 | -77.08% | 75238.47 | -46320.47 | -61.56% | 1.Site prodction was low on 01/17,01/18,01/19 and again from 01/25 due to snow
Cohasse | MA | 28561 | 122933.8 | -94372.8 | -76.77% | 113040.9 | -84479.9 | -74.73% | 1.Site production was low on 01/17,01/18,01/19 and again from 01/25 due to snow
ISM Dighton Solar 2 | MA | 124498.0033 | 228179.9 | -103681.8967 | -45.44% | 193899 | -69400.9967 | -35.79% | 1.Site was offline from 07:15 to 08:45 on 01/01 2.Site production was low on 01/07, 01/17,01/18 and again fron 01/25 due to snow | 1. SR113615 | 1.Closed
Dudley River 1 | MA | 34973 | 98451.27 | -63478.27 | -64.48% | 82926.12 | -47953.12 | -57.83% | 1.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
Dudley River 2 | MA | 37948 | 101210.3 | -63262.3 | -62.51% | 81101.73 | -43153.73 | -53.21% | 1.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
Dudley River 3 | MA | 46815 | 101328.2 | -54513.2 | -53.8% | 83309.23 | -36494.23 | -43.81% | 1.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
Flint Pond | MA | 13493 | 57616.02 | -44123.02 | -76.58% | 33208.85 | -19715.85 | -59.37% | 1.Inverter 1 CB 4 and CB5 have heavy seasonal shading in the afternoon 2.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
Incom | MA | 58433 | 229168.4 | -170735.4 | -74.5% | 217959.3 | -159526.3 | -73.19% | 1.Site production was low on 01/17,01/18 and again fron 01/25 due to snow 2.Inverter D CB 1, CB 2 and CB 5 have seasonal shading in the afternoon Inverter C CB 5 has heavy seasonal shading in the afternoon.
JH | MA | 25125 | 125626.5 | -100501.5 | -80% | 105158.4 | -80033.4 | -76.11% | 1. Inverter 2 has heavy shading in afternoon. 2. Inverter 1 has afternoon to evenig shading. 3.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
Ledeaux | MA | 24326 | 88562.29 | -64236.29 | -72.53% | 97784.09 | -73458.09 | -75.12% | 1. Inverter 2 CB 4 and CB 5 has heavy seasonal shading in the afternoon. 2.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
Palombo A | MA | 89529 | 242420.3 | -152891.3 | -63.07% | 240167 | -150638 | -62.72% | 1.Inverter D has evening shading and inverter B has morning shading. 2.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
Palombo B | MA | 41178 | 122740.4 | -81562.4 | -66.45% | 71052.02 | -29874.02 | -42.05% | 1.Inverter A has evening shading. 2.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
St Josephs Church | MA | 30068.6 | 121421.5 | -91352.9 | -75.24% | 90617.38 | -60548.78 | -66.82% | 1.Site production was low on 01/17,01/18 and again fron 01/25 due to snow 2.Meter lost communication at 10:30 on 01/17 and it came back online at 14:45 on 01/19 | 2.SR114718 | 1.Closed
Sunset A | MA | 13004.5 | 56404.29 | -43399.79 | -76.94% | 32370.49 | -19365.99 | -59.83% | 1. Inverter 1 CB 4 has aftertnoon to evening shading. and inverter has morning shading. 2.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
Sunset B | MA | 10824.5 | 39293.98 | -28469.48 | -72.45% | 31984.83 | -21160.33 | -66.16% | 1. Inverter 1 CB 3 has heavy aftertnoon to evening shading 2.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
Woodchuck | MA | 22531 | 90321.07 | -67790.07 | -75.05% | 95138.48 | -72607.48 | -76.32% | 1.Site was offline at 06:00 on 01/08 and it came back online at 07:45 on 01/09 2.Site production was low on 01/17,01/18 and again fron 01/25 due to snow
NY: Skaneateles - Spafford 1 - (PW) | NY | 240951 | 358531.6 | -117580.6 | -32.8% | 393718.7 | -152767.7 | -38.8% | 1.Inverters has evening shading. 2.Site tripped offline from 08:30 to 09:15 on 01/18 | 2.SR114712 | 1.Closed
NY: Skaneateles - Spafford 2 - (PW) | NY | 99727 | 133297.2 | -33570.2 | -25.18% | 163651.8 | -63924.8 | -39.06% | 1.Site tripped offline from 08:30 to 09:30 on 01/18 | 1.SR114713 | 1.Closed
NY: New Hartford - 4001 NY-12 (IRA) | NY | 261323 | 323293.1 | -61970.1 | -19.17% | 380222 | -118899 | -31.27% | 1.CBs 4,15 and 17 producing as expected since 01/08
NY: Glenmont - Bethlehem (IRA) | NY | 392056.6719 | N/A |  |  | N/A

## Feb
38 DN |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Mar
38 DN |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Apr
38 DN |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## May
38 DN |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Jun
38 DN |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Jul
` |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Aug
38 DN |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Sep
38 DN |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Oct
38 DN |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Nov
38 DN |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Dec
38 DN |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
6th St. | CA
Barton Acres | MA
Bowden | MA
Blair Wire Village | MA
Boutilier | MA
Cherry Valley | MA
Cohasse | MA
ISM Dighton Solar 2 | MA
Dudley River 1 | MA
Dudley River 2 | MA
Dudley River 3 | MA
Flint Pond | MA
Incom | MA
JH | MA
Ledeaux | MA
Palombo A | MA
Palombo B | MA
St Josephs Church | MA
Sunset A | MA
Sunset B | MA
Woodchuck | MA
NY: Skaneateles - Spafford 1 - (PW) | NY
NY: Skaneateles - Spafford 2 - (PW) | NY
NY: New Hartford - 4001 NY-12 (IRA) | NY
NY: Glenmont - Bethlehem (IRA) | NY

## Sites
Portfolio: | 38 DN
Site DAS Name | Site | State | Update | DAS
6th St. | 6th St. | CA | AEF | PowerTrack
Barton Acres | Barton Acres | MA | AEF | PowerTrack
Bowden | Bowden | MA | AEF | PowerTrack
Blair Wire Village | Blair Wire Village | MA | AEF | PowerTrack
Boutilier | Boutilier | MA | AEF | PowerTrack
Cherry Valley | Cherry Valley | MA | AEF | PowerTrack
Cohasse | Cohasse | MA | AEF | PowerTrack
ISM Dighton Solar 2 | ISM Dighton Solar 2 | MA | AEF | PowerTrack
Dudley River 1 | Dudley River 1 | MA | AEF | PowerTrack
Dudley River 2 | Dudley River 2 | MA | AEF | PowerTrack
Dudley River 3 | Dudley River 3 | MA | AEF | PowerTrack
Flint Pond | Flint Pond | MA | AEF | PowerTrack
Incom | Incom | MA | AEF | PowerTrack
JH | JH | MA | AEF | PowerTrack
Ledeaux | Ledeaux | MA | AEF | PowerTrack
Palombo A | Palombo A | MA | AEF | PowerTrack
Palombo B | Palombo B | MA | AEF | PowerTrack
St Josephs Church | St Josephs Church | MA |  | PowerTrack
Sunset A | Sunset A | MA | AEF | PowerTrack
Sunset B | Sunset B | MA | AEF | PowerTrack
Woodchuck | Woodchuck | MA | AEF | PowerTrack
Spafford 1 - Rose Hill Road Solar 1 LLC | NY: Skaneateles - Spafford 1 - (PW) | NY | AEF | PowerTrack
Spafford 2 - Rose Hill Road Solar 2 LLC | NY: Skaneateles - Spafford 2 - (PW) | NY | AEF | PowerTrack
38DN New Hartford - New Paris Road Solar 1, LLC, | NY: New Hartford - 4001 NY-12 (IRA) | NY | AEF | PowerTrack | ff
38DN Bethlehem - Route 9W Solar 1, LLC | NY: Glenmont - Bethlehem (IRA) | NY | AEF | PowerTrack