## Year to Date
Altus Power |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 1593356.893 | 1672057.18 | -78700.287 | -4.707% | 1602821.4 | -9464.507 | -0.5905%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Pratt Solar Farm | KS | 759988 | 968508.18 | -208520.18 | -21.53% | 859113.6 | -99125.6 | -11.54%
MA: Hamilton - 500 Chebacco Rd | MA | 26193 | 69671.8 | -43478.8 | -62.41% | 0 | 0
MA: Wellfleet - 370 Coles Neck Rd | MA | 37214.7 | 43954.6 | -6739.9 | -15.33% | 0 | 0
MD: West Friendship - 13300 Frederick Rd I | MD | 231590 | 238147.1 | -6557.1 | -2.753% | 254938.1 | -23348.1 | -9.158%
MD: West Friendship - 13300 Frederick Rd II | MD | 227755 | 251176.5 | -23421.5 | -9.325% | 254321 | -26566 | -10.45%
NJ: Kearny - 30-35 Hackensack Ave | NJ | 59251.193 | 100599 | -41347.807 | -41.1% | 129824.5 | -70573.307 | -54.36%
PA: Lewisburg - 93 Art Barn Dr | PA | 63449 | 0 | 63449 |  | 104624.2 | -41175.2 | -39.36%
IL: Tilton - North G St | IL | 187916 | 0 | 187916 |  | 0 | 0

## 1st Qtr
Altus Power |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 1593356.893 | 1672057.18 | -78700.287 | -4.707% | 1602821.4 | -9464.507 | -0.5905%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Pratt Solar Farm | KS | 759988 | 968508.18 | -208520.18 | -21.53% | 859113.6 | -99125.6 | -11.54%
MA: Hamilton - 500 Chebacco Rd | MA | 26193 | 69671.8 | -43478.8 | -62.41% | 0 | 0
MA: Wellfleet - 370 Coles Neck Rd | MA | 37214.7 | 43954.6 | -6739.9 | -15.33% | 0 | 0
MD: West Friendship - 13300 Frederick Rd I | MD | 231590 | 238147.1 | -6557.1 | -2.753% | 254938.1 | -23348.1 | -9.158%
MD: West Friendship - 13300 Frederick Rd II | MD | 227755 | 251176.5 | -23421.5 | -9.325% | 254321 | -26566 | -10.45%
NJ: Kearny - 30-35 Hackensack Ave | NJ | 59251.193 | 100599 | -41347.807 | -41.1% | 129824.5 | -70573.307 | -54.36%
PA: Lewisburg - 93 Art Barn Dr | PA | 63449 | 0 | 63449 |  | 104624.2 | -41175.2 | -39.36%
IL: Tilton - North G St | IL | 187916 | 0 | 187916 |  | 0 | 0

## 2nd Qtr
Altus Power |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Pratt Solar Farm | KS | 0 | 0 | 0 |  | 0 | 0
MA: Hamilton - 500 Chebacco Rd | MA | 0 | 0 | 0 |  | 0 | 0
MA: Wellfleet - 370 Coles Neck Rd | MA | 0 | 0 | 0 |  | 0 | 0
MD: West Friendship - 13300 Frederick Rd I | MD | 0 | 0 | 0 |  | 0 | 0
MD: West Friendship - 13300 Frederick Rd II | MD | 0 | 0 | 0 |  | 0 | 0
NJ: Kearny - 30-35 Hackensack Ave | NJ | 0 | 0 | 0 |  | 0 | 0
PA: Lewisburg - 93 Art Barn Dr | PA | 0 | 0 | 0 |  | 0 | 0
IL: Tilton - North G St | IL | 0 | 0 | 0 |  | 0 | 0

## 3rd Qtr
Altus Power |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Pratt Solar Farm | KS | 0 | 0 | 0 |  | 0 | 0
MA: Hamilton - 500 Chebacco Rd | MA | 0 | 0 | 0 |  | 0 | 0
MA: Wellfleet - 370 Coles Neck Rd | MA | 0 | 0 | 0 |  | 0 | 0
MD: West Friendship - 13300 Frederick Rd I | MD | 0 | 0 | 0 |  | 0 | 0
MD: West Friendship - 13300 Frederick Rd II | MD | 0 | 0 | 0 |  | 0 | 0
NJ: Kearny - 30-35 Hackensack Ave | NJ | 0 | 0 | 0 |  | 0 | 0
PA: Lewisburg - 93 Art Barn Dr | PA | 0 | 0 | 0 |  | 0 | 0
IL: Tilton - North G St | IL | 0 | 0 | 0 |  | 0 | 0

## 4th Qtr
Altus Power |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Pratt Solar Farm | KS | 0 | 0 | 0 |  | 0 | 0
MA: Hamilton - 500 Chebacco Rd | MA | 0 | 0 | 0 |  | 0 | 0
MA: Wellfleet - 370 Coles Neck Rd | MA | 0 | 0 | 0 |  | 0 | 0
MD: West Friendship - 13300 Frederick Rd I | MD | 0 | 0 | 0 |  | 0 | 0
MD: West Friendship - 13300 Frederick Rd II | MD | 0 | 0 | 0 |  | 0 | 0
NJ: Kearny - 30-35 Hackensack Ave | NJ | 0 | 0 | 0 |  | 0 | 0
PA: Lewisburg - 93 Art Barn Dr | PA | 0 | 0 | 0 |  | 0 | 0
IL: Tilton - North G St | IL | 0 | 0 | 0 |  | 0 | 0

## Jan
Altus Power |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 1593356.893 | 1672057.18 | -78700.287 | -4.707% | 1602821.4 | -9464.507 | -0.5905%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
Pratt Solar Farm | KS | 759988 | 968508.18 | -208520.18 | -21.53% | 859113.6 | -99125.6 | -11.54% | 1. Inverter 1 was offline from 01/01 to 10:00 on 01/05. 2. Inverter B was derating by about 600kw from 01/26 to end of the month. | 1. SR113602 2. SR115476 | 1. Closed 2. Pending | SR115476
MA: Hamilton - 500 Chebacco Rd | MA | 26193 | 69671.8 | -43478.8 | -62.41% | N/A |  |  | 1. Site was offline from 14:00 on 01/04 to 12:00 on 01/05. 2. Site production was low from 01/17 to 01/22, 01/24 to 01/31 due to snow | 1. SR114082 | 1. Closed
MA: Wellfleet - 370 Coles Neck Rd | MA | 37214.7 | 43954.6 | -6739.9 | -15.33% | N/A |  |  | 1. Inverter 3 down a string from 11/9/2025. 2. 1 Module need to be replaced. 3. Site production was low from 01/17 to 01/21, 01/25 to 01/31 due to snow | 1. SR111474 2. SR108893 | 1. Pending 2. Pending | SR108893
MD: West Friendship - 13300 Frederick Rd I | MD | 231590 | 238147.1 | -6557.1 | -2.753% | 254938.1 | -23348.1 | -9.158% | 1. Site production was lowon 01/18 and 01/25 due to snow.
MD: West Friendship - 13300 Frederick Rd II | MD | 227755 | 251176.5 | -23421.5 | -9.325% | 254321 | -26566 | -10.45% | 1. Site production was low on 01/09, 01/10, 01/14, 01/18 and 01/25 and few inverters production were low due to snow.
NJ: Kearny - 30-35 Hackensack Ave | NJ | 59251.193 | 100599 | -41347.807 | -41.1% | 129824.5 | -70573.307 | -54.36% | 1. Site production was low from 01/17 to 01/22, 01/24 to 01/31 due to snow 2. All inverters have seasonal shading.
PA: Lewisburg - 93 Art Barn Dr | PA | 63449 | 0 | 63449 |  | 104624.2 | -41175.2 | -39.36% | 1. Site production was low from 01/17 to 01/22, 01/24 to 01/31 due to snow 2. All inverters have seasonal shading. 3. 15 Modules need to be replaced. | 3. SR114901 | 3. Pending
IL: Tilton - North G St | IL | 187916 | N/A |  |  | N/A |  |  | 1. Site was offline from 23:45 on 01/08 to 11:15 on 01/09 and inverters 8, 10, 15 were offline from 07:00 to 14:00 on 01/09. 2.Site production was low on 01/10, 01/11, 01/13, 01/14, 01/24, 01/25, 01/26 due to snow. | 1. SR114342 | 1. Closed

## Feb
Altus Power |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Mar
Altus Power |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Apr
Altus Power |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## May
Altus Power |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Jun
Altus Power |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Jul
Altus Power |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Aug
Altus Power |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS |  | 0 |  |  | 0 |  |  |  | 2. SR089346
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Sep
Altus Power |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS |  |  |  |  | 0
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Oct
Altus Power |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS |  |  |  |  | 0
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Nov
Altus Power |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS |  |  |  |  | 0 |  |  | 1. Inverter 4 is underperforming by 6kW from 11/02 due to stuck tracker. 2. Site tripped offline at 05:15 AM and back online at 06:00 AM on 11/25 due to utility outage. 3. Forecasted data is not available.
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Dec
Altus Power |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Pratt Solar Farm | KS |  |  |  |  | 0
MA: Hamilton - 500 Chebacco Rd | MA
MA: Wellfleet - 370 Coles Neck Rd | MA
MD: West Friendship - 13300 Frederick Rd I | MD
MD: West Friendship - 13300 Frederick Rd II | MD
NJ: Kearny - 30-35 Hackensack Ave | NJ
PA: Lewisburg - 93 Art Barn Dr | PA
IL: Tilton - North G St | IL

## Sites
Portfolio: | Altus Power
Site DAS Name | Site | State | Update | DAS
Kenyon Energy KS Solar | Pratt Solar Farm | KS |  | PowerTrack
Hamilton | MA: Hamilton - 500 Chebacco Rd | MA |  | PF Unity
Wellfleet | MA: Wellfleet - 370 Coles Neck Rd | MA |  | PF Unity
West Friendship I | MD: West Friendship - 13300 Frederick Rd I | MD |  | Also Energy
West Friendship II | MD: West Friendship - 13300 Frederick Rd II | MD |  | Also Energy
Hudson | NJ: Kearny - 30-35 Hackensack Ave | NJ |  | Also Energy
ER Bison Solar | PA: Lewisburg - 93 Art Barn Dr | PA |  | Also Energy
Danville | IL: Tilton - North G St | IL |  | PF Unity