## Year to Date
Luminace |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 2812061.3004 | 3604268.213 | -792206.9126 | -21.98% | 2541902.62 | 270158.6804 | 10.63%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Raymond Ed Re-Development - DC-23-0001 | DC | 18272.7 | 36267.38 | -17994.68 | -49.62% | 24480.12 | -6207.42 | -25.36%
Berkeley - NJ-22-C893 Berkeley I | NJ | 469718 | 473292.9 | -3574.9 | -0.7553% | 402492.4 | 67225.6 | 16.7%
Berkeley - NJ-22-C894 Berkeley II | NJ | 453238 | 461332.9 | -8094.9 | -1.755% | 406892 | 46346 | 11.39%
BEMS Landfill East | NJ | 0 | 424307 | -424307 | -100% | 355358.6 | -355358.6 | -100%
Southampton - BEMS West NJ-22-C898 | NJ | 300960 | 455910.8 | -154950.8 | -33.99% | 362238 | -61278 | -16.92%
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ | 2065.8594 | 3424.203 | -1358.3436 | -39.67% | 2301 | -235.1406 | -10.22%
Lakewood Township - Public Works | NJ | 44532 | 73444.05 | -28912.05 | -39.37% | 26278 | 18254 | 69.46%
Canby - Dover - OR-23-C003 | OR | 151450.831 | 159215.1 | -7764.269 | -4.877% | 116555 | 34895.831 | 29.94%
Estacada - Clayfield - OR-23-C001 | OR | 141824.519 | 151135.4 | -9310.881 | -6.161% | 156810 | -14985.481 | -9.556%
Willamina - Waterford - OR-23-C006 | OR | 190623.791 | 204554.5 | -13930.709 | -6.81% | 154888 | 35735.791 | 23.07%
OR-23-C005 Solops SPI - Belvedere Solar | OR | 151622.808 | 154661.5 | -3038.692 | -1.965% | 147839 | 3783.808 | 2.559%
OR-23-C002 SPI - Cork Solar | OR | 151450.831 | 159215.1 | -7764.269 | -4.877% | 116555 | 34895.831 | 29.94%
OR: Oregon City - Buckner Creek - OR-23-C008 | OR | 134710.701 | 142033.1 | -7322.399 | -5.155% | 115785 | 18925.701 | 16.35%
OR: Dundee - Gun Club - OR-23-C009 | OR | 165736.96 | 154452.5 | 11284.46 | 7.306% | 153430.5 | 12306.46 | 8.021%
OR: Molalla - Marquam - OR-23-C010 | OR | 0 | 0 | 0 |  | 0 | 0
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA | 435854.3 | 551021.78 | -115167.48 | -20.9% | 0 | 0

## 1st Qtr
Luminace |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 2812061.3004 | 3604268.213 | -792206.9126 | -21.98% | 2541902.62 | 270158.6804 | 10.63%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Raymond Ed Re-Development - DC-23-0001 | DC | 18272.7 | 36267.38 | -17994.68 | -49.62% | 24480.12 | -6207.42 | -25.36%
Berkeley - NJ-22-C893 Berkeley I | NJ | 469718 | 473292.9 | -3574.9 | -0.7553% | 402492.4 | 67225.6 | 16.7%
Berkeley - NJ-22-C894 Berkeley II | NJ | 453238 | 461332.9 | -8094.9 | -1.755% | 406892 | 46346 | 11.39%
BEMS Landfill East | NJ | 0 | 424307 | -424307 | -100% | 355358.6 | -355358.6 | -100%
Southampton - BEMS West NJ-22-C898 | NJ | 300960 | 455910.8 | -154950.8 | -33.99% | 362238 | -61278 | -16.92%
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ | 2065.8594 | 3424.203 | -1358.3436 | -39.67% | 2301 | -235.1406 | -10.22%
Lakewood Township - Public Works | NJ | 44532 | 73444.05 | -28912.05 | -39.37% | 26278 | 18254 | 69.46%
Canby - Dover - OR-23-C003 | OR | 151450.831 | 159215.1 | -7764.269 | -4.877% | 116555 | 34895.831 | 29.94%
Estacada - Clayfield - OR-23-C001 | OR | 141824.519 | 151135.4 | -9310.881 | -6.161% | 156810 | -14985.481 | -9.556%
Willamina - Waterford - OR-23-C006 | OR | 190623.791 | 204554.5 | -13930.709 | -6.81% | 154888 | 35735.791 | 23.07%
OR-23-C005 Solops SPI - Belvedere Solar | OR | 151622.808 | 154661.5 | -3038.692 | -1.965% | 147839 | 3783.808 | 2.559%
OR-23-C002 SPI - Cork Solar | OR | 151450.831 | 159215.1 | -7764.269 | -4.877% | 116555 | 34895.831 | 29.94%
OR: Oregon City - Buckner Creek - OR-23-C008 | OR | 134710.701 | 142033.1 | -7322.399 | -5.155% | 115785 | 18925.701 | 16.35%
OR: Dundee - Gun Club - OR-23-C009 | OR | 165736.96 | 154452.5 | 11284.46 | 7.306% | 153430.5 | 12306.46 | 8.021%
OR: Molalla - Marquam - OR-23-C010 | OR | 0 | 0 | 0 |  | 0 | 0
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA | 435854.3 | 551021.78 | -115167.48 | -20.9% | 0 | 0

## 2nd Qtr
Luminace |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Raymond Ed Re-Development - DC-23-0001 | DC | 0 | 0 | 0 |  | 0 | 0
Berkeley - NJ-22-C893 Berkeley I | NJ | 0 | 0 | 0 |  | 0 | 0
Berkeley - NJ-22-C894 Berkeley II | NJ | 0 | 0 | 0 |  | 0 | 0
BEMS Landfill East | NJ | 0 | 0 | 0 |  | 0 | 0
Southampton - BEMS West NJ-22-C898 | NJ | 0 | 0 | 0 |  | 0 | 0
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ | 0 | 0 | 0 |  | 0 | 0
Lakewood Township - Public Works | NJ | 0 | 0 | 0 |  | 0 | 0
Canby - Dover - OR-23-C003 | OR | 0 | 0 | 0 |  | 0 | 0
Estacada - Clayfield - OR-23-C001 | OR | 0 | 0 | 0 |  | 0 | 0
Willamina - Waterford - OR-23-C006 | OR | 0 | 0 | 0 |  | 0 | 0
OR-23-C005 Solops SPI - Belvedere Solar | OR | 0 | 0 | 0 |  | 0 | 0
OR-23-C002 SPI - Cork Solar | OR | 0 | 0 | 0 |  | 0 | 0
OR: Oregon City - Buckner Creek - OR-23-C008 | OR | 0 | 0 | 0 |  | 0 | 0
OR: Dundee - Gun Club - OR-23-C009 | OR | 0 | 0 | 0 |  | 0 | 0
OR: Molalla - Marquam - OR-23-C010 | OR | 0 | 0 | 0 |  | 0 | 0
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## 3rd Qtr
Luminace |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Raymond Ed Re-Development - DC-23-0001 | DC | 0 | 0 | 0 |  | 0 | 0
Berkeley - NJ-22-C893 Berkeley I | NJ | 0 | 0 | 0 |  | 0 | 0
Berkeley - NJ-22-C894 Berkeley II | NJ | 0 | 0 | 0 |  | 0 | 0
BEMS Landfill East | NJ | 0 | 0 | 0 |  | 0 | 0
Southampton - BEMS West NJ-22-C898 | NJ | 0 | 0 | 0 |  | 0 | 0
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ | 0 | 0 | 0 |  | 0 | 0
Lakewood Township - Public Works | NJ | 0 | 0 | 0 |  | 0 | 0
Canby - Dover - OR-23-C003 | OR | 0 | 0 | 0 |  | 0 | 0
Estacada - Clayfield - OR-23-C001 | OR | 0 | 0 | 0 |  | 0 | 0
Willamina - Waterford - OR-23-C006 | OR | 0 | 0 | 0 |  | 0 | 0
OR-23-C005 Solops SPI - Belvedere Solar | OR | 0 | 0 | 0 |  | 0 | 0
OR-23-C002 SPI - Cork Solar | OR | 0 | 0 | 0 |  | 0 | 0
OR: Oregon City - Buckner Creek - OR-23-C008 | OR | 0 | 0 | 0 |  | 0 | 0
OR: Dundee - Gun Club - OR-23-C009 | OR | 0 | 0 | 0 |  | 0 | 0
OR: Molalla - Marquam - OR-23-C010 | OR | 0 | 0 | 0 |  | 0 | 0
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## 4th Qtr
Luminace |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
Raymond Ed Re-Development - DC-23-0001 | DC | 0 | 0 | 0 |  | 0 | 0
Berkeley - NJ-22-C893 Berkeley I | NJ | 0 | 0 | 0 |  | 0 | 0
Berkeley - NJ-22-C894 Berkeley II | NJ | 0 | 0 | 0 |  | 0 | 0
BEMS Landfill East | NJ | 0 | 0 | 0 |  | 0 | 0
Southampton - BEMS West NJ-22-C898 | NJ | 0 | 0 | 0 |  | 0 | 0
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ | 0 | 0 | 0 |  | 0 | 0
Lakewood Township - Public Works | NJ | 0 | 0 | 0 |  | 0 | 0
Canby - Dover - OR-23-C003 | OR | 0 | 0 | 0 |  | 0 | 0
Estacada - Clayfield - OR-23-C001 | OR | 0 | 0 | 0 |  | 0 | 0
Willamina - Waterford - OR-23-C006 | OR | 0 | 0 | 0 |  | 0 | 0
OR-23-C005 Solops SPI - Belvedere Solar | OR | 0 | 0 | 0 |  | 0 | 0
OR-23-C002 SPI - Cork Solar | OR | 0 | 0 | 0 |  | 0 | 0
OR: Oregon City - Buckner Creek - OR-23-C008 | OR | 0 | 0 | 0 |  | 0 | 0
OR: Dundee - Gun Club - OR-23-C009 | OR | 0 | 0 | 0 |  | 0 | 0
OR: Molalla - Marquam - OR-23-C010 | OR | 0 | 0 | 0 |  | 0 | 0
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Jan
Luminace |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 2812061.3004 | 3604268.213 | -792206.9126 | -21.98% | 2541902.62 | 270158.6804 | 10.63%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Raymond Ed Re-Development - DC-23-0001 | DC | 18272.7 | 36267.38 | -17994.68 | -49.62% | 24480.12 | -6207.42 | -25.36% | 1. Site was barely producing on 01/2, 01/09, 01/10, 01/14, 01/25 to 01/31 due to snow. 2. Inverter 8 was offline from 14:00 on 01/09 to 16:45 on 01/10. 3. All inverters have seasonal shading which impacting production. | 2. SR110376 | 2. Closed
Berkeley - NJ-22-C893 Berkeley I | NJ | 469718 | 473292.9 | -3574.9 | -0.7553% | 402492.4 | 67225.6 | 16.7%
Berkeley - NJ-22-C894 Berkeley II | NJ | 453238 | 461332.9 | -8094.9 | -1.755% | 406892 | 46346 | 11.39%
BEMS Landfill East | NJ | 0 | 424307 | -424307 | -100% | 355358.6 | -355358.6 | -100% | 1. Site was offline for whole month. | 1. SR112315 | 1. Pending
Southampton - BEMS West NJ-22-C898 | NJ | 300960 | 455910.8 | -154950.8 | -33.99% | 362238 | -61278 | -16.92% | 1. Site was barely producing on 01/2, 01/09, 01/10, 01/14, 01/25 to 01/28 due to snow.
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ | 2065.8594 | 3424.203 | -1358.3436 | -39.67% | 2301 | -235.1406 | -10.22% | 1. Site was barely producing on 01/2, 01/09, 01/10, 01/14, 01/17, 01/18, 01/19, 01/25 to 01/31 due to snow. 2. Inverter 2 was offline from 01/27 to 01/31 due to snow. | 2. SR115452 | 2. closed
Lakewood Township - Public Works | NJ | 44532 | 73444.05 | -28912.05 | -39.37% | 26278 | 18254 | 69.46% | 1. Site was barely producing on 01/2, 01/09, 01/10, 01/14, 01/17, 01/18, 01/19, 01/25 to 01/27 due to snow. 2. Site tripped offline on 01/27 at 09:00 and later back online at 11:15 on 01/29. | 2. SR115413
Canby - Dover - OR-23-C003 | OR | 151450.831 | 159215.1 | -7764.269 | -4.877% | 116555 | 34895.831 | 29.94%
Estacada - Clayfield - OR-23-C001 | OR | 141824.519 | 151135.4 | -9310.881 | -6.161% | 156810 | -14985.481 | -9.556% | 1. Site was offline from 13:45 to end of the day on 01/31. 2. Site was offline from 16:15 on 01/16 to 13:45 on 01/17. 3. Site was offline from 10:00 to 10:30 on 01/13. 4. Site was offline from 14:00 on 01/14 to 10:00 on 01/15. 5. Site was offline from 10:00 to 13:45 on 01/08. | 1. SR115526 2. SR114702 3. SR114521 4. SR114574 5. SR114311 | 1. Closed 2. Closed 3. Closed 4. Closed 5. Closed | SR114702 | SR114521 | SR114574 | SR114311
Willamina - Waterford - OR-23-C006 | OR | 190623.791 | 204554.5 | -13930.709 | -6.81% | 154888 | 35735.791 | 23.07%
OR-23-C005 Solops SPI - Belvedere Solar | OR | 151622.808 | 154661.5 | -3038.692 | -1.965% | 147839 | 3783.808 | 2.559% | 1. Site was offline from 13:15 on 01/21 to 12:00 on 01/23. 2. Inverter 22 has late starting issue. | 1. SR114841 2. SR114824 | 1. closed 2. closed | SR114824
OR-23-C002 SPI - Cork Solar | OR | 151450.831 | 159215.1 | -7764.269 | -4.877% | 116555 | 34895.831 | 29.94%
OR: Oregon City - Buckner Creek - OR-23-C008 | OR | 134710.701 | 142033.1 | -7322.399 | -5.155% | 115785 | 18925.701 | 16.35% | 1. Inverter 20 powerhead was being RMA'd. 2. Inverter 3 had intermittent tripping and 5kW derate during high irradiance | 1. SR115343 2. SR108253 | 1. Work in progress 2. Closed | SR108253
OR: Dundee - Gun Club - OR-23-C009 | OR | 165736.96 | 154452.5 | 11284.46 | 7.306% | 153430.5 | 12306.46 | 8.021% | 1. CPR Virtual weather station was reporting zero for whole month. | 1. SR114386 | 1. Closed
OR: Molalla - Marquam - OR-23-C010 | OR | 0 | 0 | 0 |  | 0 | 0 |  | 1. Site was not communicating for whole month. | 1. SR110001 | 1. Denied
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA | 435854.3 | 551021.78 | -115167.48 | -20.9% | N/A |  |  | 1. Inverter 8 offline from 12/17/25 and remained offline for rest of the month. | 1.SR114369 | 1.Pending

## Feb
Luminace |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Since meter M1 is reporting negative values from 01/03 we have consider M0 production as total site production.

## Mar
Luminace |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Apr
Luminace |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## May
Luminace |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Jun
Luminace |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ |  |  | 0
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Jul
Luminace |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Aug
Luminace |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Sep
Luminace |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Oct
Luminace |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Nov
Luminace |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Dec
Luminace |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
Raymond Ed Re-Development - DC-23-0001 | DC
Berkeley - NJ-22-C893 Berkeley I | NJ
Berkeley - NJ-22-C894 Berkeley II | NJ
BEMS Landfill East | NJ
Southampton - BEMS West NJ-22-C898 | NJ
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ
Lakewood Township - Public Works | NJ
Canby - Dover - OR-23-C003 | OR
Estacada - Clayfield - OR-23-C001 | OR
Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR
OR-23-C002 SPI - Cork Solar | OR
OR: Oregon City - Buckner Creek - OR-23-C008 | OR
OR: Dundee - Gun Club - OR-23-C009 | OR
OR: Molalla - Marquam - OR-23-C010 | OR
VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA

## Sites
Portfolio: | Luminace
Site DAS Name | Site | State | Update | DAS
DC-23-0001 - Raymond Elementary Redev | Raymond Ed Re-Development - DC-23-0001 | DC | AEF | PowerTrack
NJ-22-C893 - CS Energy - Berkeley I | Berkeley - NJ-22-C893 Berkeley I | NJ | AEF | PowerTrack
NJ-22-C894 - CS Energy - Berkeley II | Berkeley - NJ-22-C894 Berkeley II | NJ | AEF | PowerTrack
Southampton - BEMS East NJ-22-C897 | BEMS Landfill East | NJ |  | PowerTrack
NJ-22-C898 - BEMS Landfill West | Southampton - BEMS West NJ-22-C898 | NJ | AEF | PowerTrack
Lakewood Twp - Emergency Services Dev - NJ-23-0008 | Lakewood Twp - Emergency Services Dev - NJ-23-0008 | NJ |  | PowerTrack
Lakewood Township - Public Works | Lakewood Township - Public Works | NJ |  | PowerTrack
OR-23-C003 Dover - SPI | Canby - Dover - OR-23-C003 | OR | AEF | PowerTrack
OR-23-C001 SPI - Clayfield Solar | Estacada - Clayfield - OR-23-C001 | OR | AEF | PowerTrack
SPI - Waterford Solar | Willamina - Waterford - OR-23-C006 | OR
OR-23-C005 Solops SPI - Belvedere Solar | OR-23-C005 Solops SPI - Belvedere Solar | OR | AEF
Molalla - Cork - OR-23-C002 | OR-23-C002 SPI - Cork Solar | OR
OR-23-C008 Buckner Solar | OR: Oregon City - Buckner Creek - OR-23-C008 | OR |  | PowerTrack
OR-23-C009 Green Key Gun Club Solar | OR: Dundee - Gun Club - OR-23-C009 | OR |  | PowerTrack
OR-23-C010 Marquam Creek Solar | OR: Molalla - Marquam - OR-23-C010 | OR |  | PowerTrack
VA - Mechanicsville | VA: Mechanicsville - Peppertown Rd - VA-24-C002 (IRA) | VA |  | PF Unity