## Year to Date
REC Solar |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 2233531.538 | 351433.54 | 1882097.998 | 535.5% | 373875.89 | 1859655.648 | 497.4%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Goodyear - Amazon GYR2 | AZ | 301975.2 | 302200.09 | -224.89 | -0.07442% | 298527.2 | 3448 | 1.155%
AZ: Tucson - Amazon - TUS2 | AZ | 300385 | 0 | 300385 |  | 0 | 0
CO: Denver - TruStile Doors | CO | 91741 | 0 | 91741 |  | 0 | 0
CO: Thornton - Amazon - DEN3 | CO | 388827 | 0 | 388827 |  | 0 | 0
CO: Greenwood Village - REC H5 Data Center | CO | 30729 | 0 | 30729 |  | 0 | 0
HI: Ewa Beach - Salvation Army Kroc Center | HI | 3029 | 0 | 3029 |  | 0 | 0
HI: Honolulu - Hawaii Foodbank | HI | 20685.95 | 28454.35 | -7768.4 | -27.3% | 29676.64 | -8990.69 | -30.3%
HI: Kailua-Kona - Home Depot #1704 | HI | 61869 | 0 | 61869 |  | 0 | 0
HI: Kapolei - Home Depot #1706 | HI | 46759 | 0 | 46759 |  | 0 | 0
HI: Laie - Polynesian Cultural Center | HI | 9 | 0 | 9 |  | 0 | 0
HI: Laie- BYU Hawaii (PW) | HI | 258088 | 0 | 258088 |  | 0 | 0
HI: Waianae - Makaha Surfside | HI | 21962.7 | 20779.1 | 1183.6 | 5.696% | 22747.2 | -784.5 | -3.449%
HI: Kahului - Home Depot #1703 | HI | 59924 | 0 | 59924 |  | 0 | 0
MA: Andover - Boston One Campus | MA | 6801.688 | 0 | 6801.688 |  | 22924.85 | -16123.162 | -70.33%
MA: Foxboro - Schneider Cocasset | MA | 5651 | 0 | 5651 |  | 0 | 0
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD | 84770 | 0 | 84770 |  | 0 | 0
MD: Sparrows Point - Amazon DCA1 | MD | 91260 | 0 | 91260 |  | 0 | 0
NJ: Piscataway - LVMH DC | NJ | 24539 | 0 | 24539 |  | 0 | 0
NM: Edgewood - Walmart #4201 | NM | 45560 | 0 | 45560 |  | 0 | 0
NM: Gallup - Walmart #906 | NM | 48096 | 0 | 48096 |  | 0 | 0
NV: Las Vegas - Amazon - LAS5 | NV | 46426 | 0 | 46426 |  | 0 | 0
RI: Narragansett - Anchor Storage | RI | 5683 | 0 | 5683 |  | 0 | 0
RI: North Kingstown - Walmart #2261 | RI | 13530 | 0 | 13530 |  | 0 | 0
RI: Warwick - Walmart #2373 | RI | 12429 | 0 | 12429 |  | 0 | 0
TX: Seguin - Niagara Bottling LLC | TX | 262802 | 0 | 262802 |  | 0 | 0
|  | 0 | 0 | 0 |  | 0 | 0

## 1st Qtr
REC Solar |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 2233531.538 | 351433.54 | 1882097.998 | 535.5% | 373875.89 | 1859655.648 | 497.4%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Goodyear - Amazon GYR2 | AZ | 301975.2 | 302200.09 | -224.89 | -0.07442% | 298527.2 | 3448 | 1.155%
AZ: Tucson - Amazon - TUS2 | AZ | 300385 | 0 | 300385 |  | 0 | 0
CO: Denver - TruStile Doors | CO | 91741 | 0 | 91741 |  | 0 | 0
CO: Thornton - Amazon - DEN3 | CO | 388827 | 0 | 388827 |  | 0 | 0
CO: Greenwood Village - REC H5 Data Center | CO | 30729 | 0 | 30729 |  | 0 | 0
HI: Ewa Beach - Salvation Army Kroc Center | HI | 3029 | 0 | 3029 |  | 0 | 0
HI: Honolulu - Hawaii Foodbank | HI | 20685.95 | 28454.35 | -7768.4 | -27.3% | 29676.64 | -8990.69 | -30.3%
HI: Kailua-Kona - Home Depot #1704 | HI | 61869 | 0 | 61869 |  | 0 | 0
HI: Kapolei - Home Depot #1706 | HI | 46759 | 0 | 46759 |  | 0 | 0
HI: Laie - Polynesian Cultural Center | HI | 9 | 0 | 9 |  | 0 | 0
HI: Laie- BYU Hawaii (PW) | HI | 258088 | 0 | 258088 |  | 0 | 0
HI: Waianae - Makaha Surfside | HI | 21962.7 | 20779.1 | 1183.6 | 5.696% | 22747.2 | -784.5 | -3.449%
HI: Kahului - Home Depot #1703 | HI | 59924 | 0 | 59924 |  | 0 | 0
MA: Andover - Boston One Campus | MA | 6801.688 | 0 | 6801.688 |  | 22924.85 | -16123.162 | -70.33%
MA: Foxboro - Schneider Cocasset | MA | 5651 | 0 | 5651 |  | 0 | 0
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD | 84770 | 0 | 84770 |  | 0 | 0
MD: Sparrows Point - Amazon DCA1 | MD | 91260 | 0 | 91260 |  | 0 | 0
NJ: Piscataway - LVMH DC | NJ | 24539 | 0 | 24539 |  | 0 | 0
NM: Edgewood - Walmart #4201 | NM | 45560 | 0 | 45560 |  | 0 | 0
NM: Gallup - Walmart #906 | NM | 48096 | 0 | 48096 |  | 0 | 0
NV: Las Vegas - Amazon - LAS5 | NV | 46426 | 0 | 46426 |  | 0 | 0
RI: Narragansett - Anchor Storage | RI | 5683 | 0 | 5683 |  | 0 | 0
RI: North Kingstown - Walmart #2261 | RI | 13530 | 0 | 13530 |  | 0 | 0
RI: Warwick - Walmart #2373 | RI | 12429 | 0 | 12429 |  | 0 | 0
TX: Seguin - Niagara Bottling LLC | TX | 262802 | 0 | 262802 |  | 0 | 0
|  | 0 | 0 | 0 |  | 0 | 0

## 2nd Qtr
REC Solar |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Goodyear - Amazon GYR2 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: Tucson - Amazon - TUS2 | AZ | 0 | 0 | 0 |  | 0 | 0
CO: Denver - TruStile Doors | CO | 0 | 0 | 0 |  | 0 | 0
CO: Thornton - Amazon - DEN3 | CO | 0 | 0 | 0 |  | 0 | 0
CO: Greenwood Village - REC H5 Data Center | CO | 0 | 0 | 0 |  | 0 | 0
HI: Ewa Beach - Salvation Army Kroc Center | HI | 0 | 0 | 0 |  | 0 | 0
HI: Honolulu - Hawaii Foodbank | HI | 0 | 0 | 0 |  | 0 | 0
HI: Kailua-Kona - Home Depot #1704 | HI | 0 | 0 | 0 |  | 0 | 0
HI: Kapolei - Home Depot #1706 | HI | 0 | 0 | 0 |  | 0 | 0
HI: Laie - Polynesian Cultural Center | HI | 0 | 0 | 0 |  | 0 | 0
HI: Laie- BYU Hawaii (PW) | HI | 0 | 0 | 0 |  | 0 | 0
HI: Waianae - Makaha Surfside | HI | 0 | 0 | 0 |  | 0 | 0
HI: Kahului - Home Depot #1703 | HI | 0 | 0 | 0 |  | 0 | 0
MA: Andover - Boston One Campus | MA | 0 | 0 | 0 |  | 0 | 0
MA: Foxboro - Schneider Cocasset | MA | 0 | 0 | 0 |  | 0 | 0
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD | 0 | 0 | 0 |  | 0 | 0
MD: Sparrows Point - Amazon DCA1 | MD | 0 | 0 | 0 |  | 0 | 0
NJ: Piscataway - LVMH DC | NJ | 0 | 0 | 0 |  | 0 | 0
NM: Edgewood - Walmart #4201 | NM | 0 | 0 | 0 |  | 0 | 0
NM: Gallup - Walmart #906 | NM | 0 | 0 | 0 |  | 0 | 0
NV: Las Vegas - Amazon - LAS5 | NV | 0 | 0 | 0 |  | 0 | 0
RI: Narragansett - Anchor Storage | RI | 0 | 0 | 0 |  | 0 | 0
RI: North Kingstown - Walmart #2261 | RI | 0 | 0 | 0 |  | 0 | 0
RI: Warwick - Walmart #2373 | RI | 0 | 0 | 0 |  | 0 | 0
TX: Seguin - Niagara Bottling LLC | TX | 0 | 0 | 0 |  | 0 | 0
|  | 0 | 0 | 0 |  | 0 | 0

## 3rd Qtr
REC Solar |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Goodyear - Amazon GYR2 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: Tucson - Amazon - TUS2 | AZ | 0 | 0 | 0 |  | 0 | 0
CO: Denver - TruStile Doors | CO | 0 | 0 | 0 |  | 0 | 0
CO: Thornton - Amazon - DEN3 | CO | 0 | 0 | 0 |  | 0 | 0
CO: Greenwood Village - REC H5 Data Center | CO | 0 | 0 | 0 |  | 0 | 0
HI: Ewa Beach - Salvation Army Kroc Center | HI | 0 | 0 | 0 |  | 0 | 0
HI: Honolulu - Hawaii Foodbank | HI | 0 | 0 | 0 |  | 0 | 0
HI: Kailua-Kona - Home Depot #1704 | HI | 0 | 0 | 0 |  | 0 | 0
HI: Kapolei - Home Depot #1706 | HI | 0 | 0 | 0 |  | 0 | 0
HI: Laie - Polynesian Cultural Center | HI | 0 | 0 | 0 |  | 0 | 0
HI: Laie- BYU Hawaii (PW) | HI | 0 | 0 | 0 |  | 0 | 0
HI: Waianae - Makaha Surfside | HI | 0 | 0 | 0 |  | 0 | 0
HI: Kahului - Home Depot #1703 | HI | 0 | 0 | 0 |  | 0 | 0
MA: Andover - Boston One Campus | MA | 0 | 0 | 0 |  | 0 | 0
MA: Foxboro - Schneider Cocasset | MA | 0 | 0 | 0 |  | 0 | 0
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD | 0 | 0 | 0 |  | 0 | 0
MD: Sparrows Point - Amazon DCA1 | MD | 0 | 0 | 0 |  | 0 | 0
NJ: Piscataway - LVMH DC | NJ | 0 | 0 | 0 |  | 0 | 0
NM: Edgewood - Walmart #4201 | NM | 0 | 0 | 0 |  | 0 | 0
NM: Gallup - Walmart #906 | NM | 0 | 0 | 0 |  | 0 | 0
NV: Las Vegas - Amazon - LAS5 | NV | 0 | 0 | 0 |  | 0 | 0
RI: Narragansett - Anchor Storage | RI | 0 | 0 | 0 |  | 0 | 0
RI: North Kingstown - Walmart #2261 | RI | 0 | 0 | 0 |  | 0 | 0
RI: Warwick - Walmart #2373 | RI | 0 | 0 | 0 |  | 0 | 0
TX: Seguin - Niagara Bottling LLC | TX | 0 | 0 | 0 |  | 0 | 0
|  | 0 | 0 | 0 |  | 0 | 0

## 4th Qtr
REC Solar |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
AZ: Goodyear - Amazon GYR2 | AZ | 0 | 0 | 0 |  | 0 | 0
AZ: Tucson - Amazon - TUS2 | AZ | 0 | 0 | 0 |  | 0 | 0
CO: Denver - TruStile Doors | CO | 0 | 0 | 0 |  | 0 | 0
CO: Thornton - Amazon - DEN3 | CO | 0 | 0 | 0 |  | 0 | 0
CO: Greenwood Village - REC H5 Data Center | CO | 0 | 0 | 0 |  | 0 | 0
HI: Ewa Beach - Salvation Army Kroc Center | HI | 0 | 0 | 0 |  | 0 | 0
HI: Honolulu - Hawaii Foodbank | HI | 0 | 0 | 0 |  | 0 | 0
HI: Kailua-Kona - Home Depot #1704 | HI | 0 | 0 | 0 |  | 0 | 0
HI: Kapolei - Home Depot #1706 | HI | 0 | 0 | 0 |  | 0 | 0
HI: Laie - Polynesian Cultural Center | HI | 0 | 0 | 0 |  | 0 | 0
HI: Laie- BYU Hawaii (PW) | HI | 0 | 0 | 0 |  | 0 | 0
HI: Waianae - Makaha Surfside | HI | 0 | 0 | 0 |  | 0 | 0
HI: Kahului - Home Depot #1703 | HI | 0 | 0 | 0 |  | 0 | 0
MA: Andover - Boston One Campus | MA | 0 | 0 | 0 |  | 0 | 0
MA: Foxboro - Schneider Cocasset | MA | 0 | 0 | 0 |  | 0 | 0
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD | 0 | 0 | 0 |  | 0 | 0
MD: Sparrows Point - Amazon DCA1 | MD | 0 | 0 | 0 |  | 0 | 0
NJ: Piscataway - LVMH DC | NJ | 0 | 0 | 0 |  | 0 | 0
NM: Edgewood - Walmart #4201 | NM | 0 | 0 | 0 |  | 0 | 0
NM: Gallup - Walmart #906 | NM | 0 | 0 | 0 |  | 0 | 0
NV: Las Vegas - Amazon - LAS5 | NV | 0 | 0 | 0 |  | 0 | 0
RI: Narragansett - Anchor Storage | RI | 0 | 0 | 0 |  | 0 | 0
RI: North Kingstown - Walmart #2261 | RI | 0 | 0 | 0 |  | 0 | 0
RI: Warwick - Walmart #2373 | RI | 0 | 0 | 0 |  | 0 | 0
TX: Seguin - Niagara Bottling LLC | TX | 0 | 0 | 0 |  | 0 | 0
|  | 0 | 0 | 0 |  | 0 | 0

## Jan
REC Solar |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 2233531.538 | 351433.54 | 1882097.998 | 535.5% | 373875.89 | 1859655.648 | 497.4%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
AZ: Goodyear - Amazon GYR2 | AZ | 301975.2 | 302200.09 | -224.89 | -0.07442% | 298527.2 | 3448 | 1.155%
AZ: Tucson - Amazon - TUS2 | AZ | 300385 | N/A |  |  | N/A |  |  | 1. Inverter 9D was LOTO'd for whole month. 2. Site tripped offline at 10:40 on 01/29 and remained offline throught the month. | 1.SR113193 2. SR115296 | 1. pending 2. pending | SR115296
CO: Denver - TruStile Doors | CO | 91741 | N/A |  |  | N/A
CO: Thornton - Amazon - DEN3 | CO | 388827 | N/A |  |  | N/A |  |  | 1. Inverter 30 tripped offline on 09/13/25. 2. Inverter A26 tripped offline for whole month. 3. Inverter C23 tripped offline at 09:20AM on 01/21 and back online on 01/22. | 1. SR113197 2. SR113670, SR114825 3. SR114884 | 1. Closed 2. Closed, Pending 3. Closed | SR113670 | SR114825 | SR114884
CO: Greenwood Village - REC H5 Data Center | CO | 30729 | N/A |  |  | N/A |  |  | 1. Inverter 3 offline for whole month. 2. Inverter 7 experienced multiple irregular tripping events throughout the month. | 1. SR113195, SR114293 2. SR113195, SR114293 | 1. Closed, Pending 2. Closed, Pending | SR114293 | SR113195 | SR114293
HI: Ewa Beach - Salvation Army Kroc Center | HI | 3029 | N/A |  |  | N/A |  |  | 1. Inverter 1-7 and 10 stopped communicating 7/30, inverter 9 stopped communicating 9/4, inverter 8 stopped communicating 11/20 and No meter was available to verify the values. | 1. SR113199, SR112265, SR114997 | 1. Pending | SR112265 | SR114997
HI: Honolulu - Hawaii Foodbank | HI | 20685.95 | 28454.35 | -7768.4 | -27.3% | 29676.64 | -8990.69 | -30.3% | 1. Inverters 7 and 10 were underproduced by 5kW each for whole month. 2. Site production was low on 01/04 due to snow. | 1. SR114688 | 1. Pending
HI: Kailua-Kona - Home Depot #1704 | HI | 61869 | N/A |  |  | N/A
HI: Kapolei - Home Depot #1706 | HI | 46759 | N/A |  |  | N/A |  |  | 1. Site has stopped communicating at 11:40 on 12/13 and back online at 16:50 on 01/04. 2. Inverter 5 is derating midday; likely a fan issue through out the month and it is offline on 01/20, 01/21. | 1.SR113208 2. SR114814 | 1.Closed 2. Pending | SR114814
HI: Laie - Polynesian Cultural Center | HI | 9 | N/A |  |  | N/A |  |  | 1. Inverter 1 was offline from 12/23 to end of the month. 2. Inverters 2 to 8 were not communicated for whole month. | 1. SR113606, SR112267 2. SR112267 | 1. Closed, Pending 2. Pending | SR112267 | SR112267
HI: Laie- BYU Hawaii (PW) | HI | 258088 | N/A |  |  | N/A |  |  | 1. Inverters 5A,5G,7G,3E,4E,01D,3D,1C,2C,3C,4C,5C,6C,7C,2B,4B,6B was offline 2. Inverters Invs 4G, 5G, 4E, and 1-7C are not communicating. Admin Aloha Meter not communicating. 3. Inverter 11G offline, reporting inverter stopped since 12/26. Inverter 11F offline, reporting inverter stopped since 12/28. 4. Inverter 7A went offline on 12/30/2025 and back online on 01/03/2026 after self-resolving. 5. Inverters 1E & 4F are offline whole month. | 1. SR112273, SR114897 2. SR113204, SR114897 3.SR113759, SR114897 4. SR114049 5. SR114225, SR112273 | 1. Completed, Pending 2. Closed, Pending 3. Closed, Pending 4. Closed 5. Closed, Pending | SR114897 | SR113204 | SR114897 | SR113759 | SR114897 | SR114049 | SR114225 | SR112273
HI: Waianae - Makaha Surfside | HI | 21962.7 | 20779.1 | 1183.6 | 5.696% | 22747.2 | -784.5 | -3.449% | 1. Inverters 4 and 8 appear to be down a string each and Inverter 5 found with two floating strings. | 1. SR112226,SR115382 | 1. Completed, Pending | SR115382
HI: Kahului - Home Depot #1703 | HI | 59924 | N/A |  |  | N/A
MA: Andover - Boston One Campus | MA | 6801.688 | 0 | 6801.688 |  | 22924.85 | -16123.162 | -70.33% | 1. IMT Reference cell 2w/ Tmodule(LOT A&B), Roof 2 IMT Reference cell w/ Tmodule(North), Roof 1 IMT Reference cell w/ Tmodule(South) were not communicated for whole month. 2. Site was barely producing from 01/17 to end of the month due to snow | 1. SR114693 | 1. Pending
MA: Foxboro - Schneider Cocasset | MA | 5651 | N/A |  |  | N/A
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD | 84770 | N/A |  |  | N/A |  |  | 1. Inverters 64-76 being isolated due to a canopy strike and inverter 11 being possibly offline. 2. The weather station is not communicating and lost communications from 17:25 on 7/23/25. 3. Inverter 39 is offline whole month. 4. Site production low from 01/25 due to snow | 1. SR113200 2. SR114012 | 1.pending 2.Pending | SR114012
MD: Sparrows Point - Amazon DCA1 | MD | 91260 | N/A |  |  | N/A |  |  | 1. The weather station is not communicating from 02:45 on 11/25. | 1.SR114032 | 1.pending
NJ: Piscataway - LVMH DC | NJ | 24539 | N/A |  |  | N/A
NM: Edgewood - Walmart #4201 | NM | 45560 | N/A |  |  | N/A |  |  | 1.Inverter 1 is underproducing by about 20kw. Down 10kw beginning 7/31/24, down 20kw beginning 6/09/25.
NM: Gallup - Walmart #906 | NM | 48096 | N/A |  |  | N/A
NV: Las Vegas - Amazon - LAS5 | NV | 46426 | N/A |  |  | N/A |  |  | 1.Inverters 3, 7, and 9 are not communicating and may be offline. Inverters 3 lost comms on 11/25/24. Inv 7 lost comms on 09/18/25. Inv 9 lost comms on 07/01/25
RI: Narragansett - Anchor Storage | RI | 5683 | N/A |  |  | N/A |  |  | 1. Site was barely producing from 01/17 to 01/21, 01/25 to end of the month due to snow. 2. Inverter 4 being RMA'd | 2. SR113373 | 2. Closed
RI: North Kingstown - Walmart #2261 | RI | 13530 | N/A |  |  | N/A |  |  | 1.Weather station lost communication | 1.SR113352 | 1.Closed
RI: Warwick - Walmart #2373 | RI | 12429 | N/A |  |  | N/A
TX: Seguin - Niagara Bottling LLC | TX | 262802 | N/A |  |  | N/A |  |  | 1. Inverter C6 being LOTO'd and meters were also not communicated for whole month. PAD C ad PAD D inverters were not communicated for whole month due to Data logger need to be replaced. 2. The actual value was taken from PAD A and PAD B inverters as the Meter, PAD C and PAD D inverters were not communicating | 1. SR112263, SR113988 | 1. Closed, Pending | SR113988

## Feb
REC Solar |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Mar
REC Solar |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Apr
REC Solar |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## May
REC Solar |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Jun
REC Solar |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Jul
` |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Aug
REC Solar |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Sep
REC Solar |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Oct
REC Solar |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Nov
REC Solar |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Dec
REC Solar |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 0 | 0 | 0 | 0% | 0 | 0 | 0% | Some sites are missing actual data; if new sites were added, make sure they are aligned correctly (including prior months!)
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
AZ: Goodyear - Amazon GYR2 | AZ
AZ: Tucson - Amazon - TUS2 | AZ
CO: Denver - TruStile Doors | CO
CO: Thornton - Amazon - DEN3 | CO
CO: Greenwood Village - REC H5 Data Center | CO
HI: Ewa Beach - Salvation Army Kroc Center | HI
HI: Honolulu - Hawaii Foodbank | HI
HI: Kailua-Kona - Home Depot #1704 | HI
HI: Kapolei - Home Depot #1706 | HI
HI: Laie - Polynesian Cultural Center | HI
HI: Laie- BYU Hawaii (PW) | HI
HI: Waianae - Makaha Surfside | HI
HI: Kahului - Home Depot #1703 | HI
MA: Andover - Boston One Campus | MA
MA: Foxboro - Schneider Cocasset | MA
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD
MD: Sparrows Point - Amazon DCA1 | MD
NJ: Piscataway - LVMH DC | NJ
NM: Edgewood - Walmart #4201 | NM
NM: Gallup - Walmart #906 | NM
NV: Las Vegas - Amazon - LAS5 | NV
RI: Narragansett - Anchor Storage | RI
RI: North Kingstown - Walmart #2261 | RI
RI: Warwick - Walmart #2373 | RI
TX: Seguin - Niagara Bottling LLC | TX

## Sites
Portfolio: | REC Solar
Site DAS Name | Site | State | Update | DAS
AZ: Goodyear - Amazon GYR2 | AZ: Goodyear - Amazon GYR2 | AZ |  | Powertrack
AZ: Tucson - Amazon - TUS2 | AZ: Tucson - Amazon - TUS2 | AZ |  | Green Power Monitor
CO: Denver - TruStile Doors | CO: Denver - TruStile Doors | CO |  | Green Power Monitor
CO: Thornton - Amazon - DEN3 | CO: Thornton - Amazon - DEN3 | CO |  | Green Power Monitor
CO: Greenwood Village - REC H5 Data Center | CO: Greenwood Village - REC H5 Data Center | CO |  | Green Power Monitor
HI: Ewa Beach - Salvation Army Kroc Center | HI: Ewa Beach - Salvation Army Kroc Center | HI |  | SolarEdge Platform
HI: Honolulu - Hawaii Foodbank | HI: Honolulu - Hawaii Foodbank | HI |  | Also Energy
HI: Kailua-Kona - Home Depot #1704 | HI: Kailua-Kona - Home Depot #1704 | HI |  | Green Power Monitor
HI: Kapolei - Home Depot #1706 | HI: Kapolei - Home Depot #1706 | HI |  | Green Power Monitor
HI: Laie - Polynesian Cultural Center | HI: Laie - Polynesian Cultural Center | HI |  | SolarEdge Platform
HI: Laie- BYU Hawaii (PW) | HI: Laie- BYU Hawaii (PW) | HI |  | Green Power Monitor
HI: Waianae - Makaha Surfside | HI: Waianae - Makaha Surfside | HI |  | Also Energy
HI: Kahului - Home Depot #1703 | HI: Kahului - Home Depot #1703 | HI |  | Green Power Monitor
MA: Andover - Boston One Campus | MA: Andover - Boston One Campus | MA |  | Also Energy
MA: Foxboro - Schneider Cocasset | MA: Foxboro - Schneider Cocasset | MA |  | Green Power Monitor
MD: Gaithersburg - Montgomery Cnty - PSHQ | MD: Gaithersburg - Montgomery Cnty - PSHQ | MD |  | Green Power Monitor
MD: Sparrows Point - Amazon DCA1 | MD: Sparrows Point - Amazon DCA1 | MD |  | Green Power Monitor
NJ: Piscataway - LVMH DC | NJ: Piscataway - LVMH DC | NJ |  | Green Power Monitor
NM: Edgewood - Walmart #4201 | NM: Edgewood - Walmart #4201 | NM |  | Green Power Monitor
NM: Gallup - Walmart #906 | NM: Gallup - Walmart #906 | NM |  | Green Power Monitor
NV: Las Vegas - Amazon - LAS5 | NV: Las Vegas - Amazon - LAS5 | NV |  | Green Power Monitor
RI: Narragansett - Anchor Storage | RI: Narragansett - Anchor Storage | RI |  | Green Power Monitor
RI: North Kingstown - Walmart #2261 | RI: North Kingstown - Walmart #2261 | RI |  | Green Power Monitor
RI: Warwick - Walmart #2373 | RI: Warwick - Walmart #2373 | RI |  | Green Power Monitor
TX: Seguin - Niagara Bottling LLC | TX: Seguin - Niagara Bottling LLC | TX |  | Green Power Monitor