## Year to Date
Burt Process Equipment |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 236577.985 | 0 | 236577.985 | 0% | 300327.461 | -63749.476 | -21.23%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hamden - Burt Process Equipment | CT | 236577.985 | 0 | 236577.985 |  | 300327.461 | -63749.476 | -21.23%

## 1st Qtr
Burt Process Equipment |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 37754.9247 | 0 | 37754.9247 | 0% | 55227 | -17472.0753 | -31.64%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hamden - Burt Process Equipment | CT | 37754.9247 | 0 | 37754.9247 |  | 55227 | -17472.0753 | -31.64%

## 2nd Qtr
Burt Process Equipment |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 79529.016 | 0 | 79529.016 | 0% | 105423.916 | -25894.9 | -24.56%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hamden - Burt Process Equipment | CT | 79529.016 | 0 | 79529.016 |  | 105423.916 | -25894.9 | -24.56%

## 3rd Qtr
Burt Process Equipment |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 83815.3144 | 0 | 83815.3144 | 0% | 95425.07 | -11609.7557 | -12.17%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hamden - Burt Process Equipment | CT | 83815.3144 | 0 | 83815.3144 |  | 95425.07 | -11609.7556 | -12.17%

## 4th Qtr
Burt Process Equipment |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 35478.73 | 0 | 35478.73 | 0% | 44251.475 | -8772.745 | -19.82%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
CT: Hamden - Burt Process Equipment | CT | 35478.73 | 0 | 35478.73 |  | 44251.475 | -8772.745 | -19.82%

## Jan
Burt Process Equipment |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 8464.09 | 0 | 8464.09 | 0% | 12910 | -4445.91 | -34.44%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 8464.09 | N/A |  |  | 12910 | -4445.91 | -34.44% | 1. Low production due to snow/rain.

## Feb
Burt Process Equipment |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 6972.03 | 0 | 6972.03 | 0% | 17368 | -10395.97 | -59.86%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 6972.03 | N/A |  |  | 17368 | -10395.97 | -59.86% | 1. Low production due to snow/rain.

## Mar
Burt Process Equipment |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 22318.8047 | 0 | 22318.8047 | 0% | 24949 | -2630.1953 | -10.54%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 22318.8047 | N/A |  |  | 24949 | -2630.1953 | -10.54% | 1. Site production was low on 03/05, 03/24 due to rain.

## Apr
Burt Process Equipment |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 26949.84 | 0 | 26949.84 | 0% | 32612 | -5662.16 | -17.36%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 26949.84 | N/A |  |  | 32612 | -5662.16 | -17.36% | 1.Site was low production on 04/03, 04/05, 04/06, 04/07, 04/12 and 04/26 due to low irradiance.

## May
Burt Process Equipment |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 24929.806 | 0 | 24929.806 | 0% | 36206.798 | -11276.992 | -31.15%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 24929.806 | N/A |  |  | 36206.798 | -11276.992 | -31.15% | 1.Site has low productionon 05/05,05/09 and 05/022 due to low irradiance

## Jun
Burt Process Equipment |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 27649.37 | 0 | 27649.37 | 0% | 36605.118 | -8955.748 | -24.47%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 27649.37 | N/A |  |  | 36605.118 | -8955.748 | -24.47% | 1. Site has low production/generation on 06/07,06/09, 06/14,06/15,06/17and 06/18 due to low irradiance.

## Jul
Burt Process Equipment |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 30331.8946 | 0 | 30331.8946 | 0% | 36385.93 | -6054.0354 | -16.64%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 30331.8946 | N/A |  |  | 36385.93 | -6054.0354 | -16.64%

## Aug
Burt Process Equipment |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 19777.1297 | 0 | 19777.1297 | 0% | 32546.14 | -12769.0103 | -39.23%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 19777.1297 | N/A |  |  | 32546.14 | -12769.0103 | -39.23% | 1. No communication to the DAS from 07:30 on 08/21, but site is online. | 1.SR105309

## Sep
Burt Process Equipment |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 33706.29 | 0 | 33706.29 | 0% | 26493 | 7213.29 | 27.23%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 33706.29 | 0 | 33706.29 |  | 26493 | 7213.29 | 27.23% | 1. Site regained its communication at 19:00 on 09/11, energy has backfilled.

## Oct
Burt Process Equipment |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 17792 | 0 | 17792 | 0% | 20797 | -3005 | -14.45%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 17792 | N/A |  |  | 20797 | -3005 | -14.45% | 1. Site production low on 10/12, 10/30 due to bad weather.

## Nov
Burt Process Equipment |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 10967.27 | 0 | 10967.27 | 0% | 12592 | -1624.73 | -12.9%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 10967.27 | N/A |  |  | 12592 | -1624.73 | -12.9% | 1. Site production low on 11/10, 11/26, 11/30 due to bad weather.

## Dec
Burt Process Equipment |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 6719.46 | 0 | 6719.46 | 0% | 10862.475 | -4143.015 | -38.14%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
CT: Hamden - Burt Process Equipment | CT | 6719.46 | N/A |  |  | 10862.475 | -4143.015 | -38.14% | 1.Site production was low on 12/14,12/19,12/27 to 12/29

## Sites
Portfolio: | Burt Process Equipment
Site DAS Name | Site | State | Update | DAS
Burt Process Equipment | CT: Hamden - Burt Process Equipment | CT | AF | PowerTrack