## Year to Date
MA: Norton - Wheaton College |  |  | Year to Date Actual v. Expected |  |  | Year to Date Actual v. Forecasted
Total |  | 375994 | 0 | 375994 | 0% | 0 | 375994 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Norton - Wheaton College | MA | 375994 | 0 | 375994 |  | 0 | 25561

## 1st Qtr
MA: Norton - Wheaton College |  |  | 1st Quarter Actual v. Expected |  |  | 1st Quarter Actual v. Forecasted
Total |  | 67281 | 0 | 67281 | 0% | 0 | 67281 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Norton - Wheaton College | MA | 67281 | 0 | 67281 |  | 0 | 13777

## 2nd Qtr
MA: Norton - Wheaton College |  |  | 2nd Quarter Actual v. Expected |  |  | 2nd Quarter Actual v. Forecasted
Total |  | 123905 | 0 | 123905 | 0% | 0 | 123905 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Norton - Wheaton College | MA | 123905 | 0 | 123905 |  | 0 | 0

## 3rd Qtr
MA: Norton - Wheaton College |  |  | 3rd Quarter Actual v. Expected |  |  | 3rd Quarter Actual v. Forecasted
Total |  | 129932 | 0 | 129932 | 0% | 0 | 129932 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Norton - Wheaton College | MA | 129932 | 0 | 129932 |  | 0 | 0

## 4th Qtr
MA: Norton - Wheaton College |  |  | 4th Quarter Actual v. Expected |  |  | 4th Quarter Actual v. Forecasted
Total |  | 54876 | 0 | 54876 | 0% | 0 | 54876 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | %
MA: Norton - Wheaton College | MA | 54876 | 0 | 54876 |  | 0 | 11784

## Jan
MA: Norton - Wheaton College |  |  | January Actual v. Expected |  |  | January Actual v. Forecasted
Total |  | 13777 | 0 | 13777 | 0% | 0 | 13777 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Norton - Wheaton College | MA | 13777 | 0 | 13777 |  | 0 | 13777 |  | 1. Weather station reporting erraneous values since 03/12/2024. | 1. SR081787

## Feb
MA: Norton - Wheaton College |  |  | February Actual v. Expected |  |  | February Actual v. Forecasted
Total |  | 18434 | 0 | 18434 | 0% | 0 | 18434 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Norton - Wheaton College | MA | 18434 | N/A |  |  | N/A |  |  | 1.Inverter 16 went offline on 02/01 and came back online at 7:15 AM on 02/02. However, the inverter started production late at 2:25 PM on 02/04. It tripped offline again at 12:35 PM on 02/19. On 02/20, upon the technician's arrival, several faults were identified: "Isolation Error, grid voltage fault, and protect 0260." The inverter was brought back online on 02/20. 2.Inverter 16 was offline on 02/25 and back online at 02:35PM on same day. 3.Inverter 12 was taken offline from 09:15AM to 09:55AM on 02/26 to replace damaged screen 4. Weather station reporting erraneous values since 03/12/2024. | 1.SR096218 2.SR097773 3.SR097591 4. SR081787 | SR097773 | SR097591 | SR081787

## Mar
MA: Norton - Wheaton College |  |  | March Actual v. Expected |  |  | March Actual v. Forecasted
Total |  | 35070 | 0 | 35070 | 0% | 0 | 35070 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Norton - Wheaton College | MA | 35070 | N/A |  |  | N/A |  |  | 1. Weather station reporting erraneous values since 03/12/2024. | 1. SR081787

## Apr
MA: Norton - Wheaton College |  |  | April Actual v. Expected |  |  | April Actual v. Forecasted
Total |  | 38389 | 0 | 38389 | 0% | 0 | 38389 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Norton - Wheaton College | MA | 38389 | N/A |  |  | N/A |  |  | 1. Inverter 16 was offline from 07:00 on 04/07 to 17:00 on 04/09; issue self-resolved. 2. Inverter 10 was offline on 04/21 and back online at 17:30 the same day, it again offline from 04/23 and back online on 04/27, and it was again offline on 04/29 and back online at 10:40 on 04/30. 3. Inverter 12 went offline on 04/01, back online on 04/02, then offline again from 04/03 to 06:25 on 04/19. It tripped on 04/20, recovered on 04/23, late started on 04/24, and went offline again on 04/25, remaining down for the rest of the month. Parts are needed to restore operation. 4. Weather station reporting erraneous values since 03/12/2024. | 1. SR099479 2. SR100077 3. SR097591, PM4612, SR098351 4. SR081787 | SR100077 | SR097591 | SR098351 | SR081787

## May
MA: Norton - Wheaton College |  |  | May Actual v. Expected |  |  | May Actual v. Forecasted
Total |  | 39667 | 0 | 39667 | 0% | 0 | 39667 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Norton - Wheaton College | MA | 39667 | N/A |  |  | N/A |  |  | 1. Inverter 12 was offline from 04/25 and came back online at 11:35 on 05/20; issue self-resolved. 2. Invertre 10 is offline from 05/01 and back online at 08:15 on 05/06, it again offline from 05/07 and back online on 05/10; issue self-resolved. 3. Weather station reporting erraneous values since 03/12/2024. | 1. SR098351 2. SR100077 3. SR081787 | SR100077 | SR081787

## Jun
MA: Norton - Wheaton College |  |  | June Actual v. Expected |  |  | June Actual v. Forecasted
Total |  | 45849 | 0 | 45849 | 0% | 0 | 45849 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Norton - Wheaton College | MA | 45849 | N/A |  |  | N/A |  |  | 1.Weather station reporting erraneous values since 03/12/2024. | 1. SR081787

## Jul
MA: Norton - Wheaton College |  |  | July Actual v. Expected |  |  | July Actual v. Forecasted
Total |  | 47667 | 0 | 47667 | 0% | 0 | 47667 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Norton - Wheaton College | MA | 47667 | N/A |  |  | N/A |  |  | 1. Weather station reporting erraneous values since 03/12/2024. 2. Inverter 1 has been operating with one string down since 07/08/25. | 1. SR081787 2. SR105558 | SR105558

## Aug
MA: Norton - Wheaton College |  |  | August Actual v. Expected |  |  | August Actual v. Forecasted
Total |  | 47508 | 0 | 47508 | 0% | 0 | 47508 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Norton - Wheaton College | MA | 47508 | N/A |  |  | N/A |  |  | 1. Weather station reporting erraneous values since 03/12/2024. 2. Inverter 1 has been operating with one string down since 07/08/25. | 1. SR081787 2. SR105558

## Sep
MA: Norton - Wheaton College |  |  | September Actual v. Expected |  |  | September Actual v. Forecasted
Total |  | 34757 | 0 | 34757 | 0% | 0 | 34757 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests
MA: Norton - Wheaton College | MA | 34757 | N/A |  |  | N/A |  |  | 1. Weather station reporting erraneous values since 03/12/2024. 2. Inverter 1 has been operating with one string down since 07/08/25. 3. Inverter 6 was offline on most of the days throughout the month. | 1. SR081787 2. SR105558 3. SR105141

## Oct
MA: Norton - Wheaton College |  |  | October Actual v. Expected |  |  | October Actual v. Forecasted
Total |  | 26150 | 0 | 26150 | 0% | 0 | 26150 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
MA: Norton - Wheaton College | MA | 26150 | N/A |  |  | N/A |  |  | 1. Weather station reporting erraneous values since 03/12/2024. 2. Inverter 1 has been operating with one string down since 07/08/25. 3. Inverter 6 was offline on most of the days throughout the month. | 1. SR081787 2. SR105558 3. SR105141 | 1. pending 2. pending 3. pending | SR105558 | SR105141

## Nov
MA: Norton - Wheaton College |  |  | November Actual v. Expected |  |  | November Actual v. Forecasted
Total |  | 16942 | 0 | 16942 | 0% | 0 | 16942 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
MA: Norton - Wheaton College | MA | 16942 | N/A |  |  | N/A |  |  | 1. Weather station reporting erraneous values since 03/12/2024. 2. Inverter 1 has been operating with one string down since 07/08/25. 3. Inverter 6 was offline on most of the days throughout the month. | 1. SR081787 2. SR105558 3. SR105141 | 1. pending 2. pending 3. pending | SR105558 | SR105141

## Dec
MA: Norton - Wheaton College |  |  | December Actual v. Expected |  |  | December Actual v. Forecasted
Total |  | 11784 | 0 | 11784 | 0% | 0 | 11784 | 0%
Site | State | Actual | Expected | Delta | % | Forecasted | Delta | % | Notes | Service Requests | Status
MA: Norton - Wheaton College | MA | 11784 | 0 | 11784 |  | 0 | 11784 |  | 1. Weather station reporting erraneous values since 03/12/2024. 2. Inverter 1 has been operating with one string down since 07/08/25. 3. Inverter 6 was offline on most of the days throughout the month. | 1. SR081787 2. SR105558 3. SR105141 | 1. pending 2. pending 3. pending | SR105558 | SR105141

## Sites
Portfolio: | MA: Norton - Wheaton College
Site DAS Name | Site | State | Update | DAS
Wheaton College | MA: Norton - Wheaton College | MA | A | Solrenview